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Purpose 
The information collected through this form will be used by the National Park Service (NPS), National Heritage Areas (NHA) Program Office and regional program offices to track each heritage area management or coordinating entity’s (coordinating entity) progress on management plan implementation.  The progress measures outlined in the categories below capture information about the diverse heritage area activities and approaches to these activities (process measures), direct products or services offered (output measures), and the results of the products or services (outcome measures).  

The NPS will use the responses to the questions reported here in annual program reports and publications and to inform individual heritage area evaluations.  

Reporting Instructions 
The progress measures in this form are grouped under eight categories, capturing the diverse work of the coordinating entities throughout the country.  We recognize that each heritage area and coordinating entity is unique.  Therefore, not all of the categories or measures presented below will apply.   

· The data reported here shall reflect the work that the coordinating entity led, funded or partnered with others to complete this year.  

· Report all work that the coordinating entity was involved in to implement the National Heritage Area Management Plan.  Include work supported by Heritage Partnership Program (HPP) funding and other heritage area funding sources.  

· Report data for the same 12-month cycle (calendar, federal, and fiscal) that you reported last year.  
 
· Measures under categories 2 – 7 are sequenced to capture work in progress, work that is completed, and the outcomes of completed work.  
   
· Follow the specific instructions for each category and measure.  Please be consistent in how you categorize your work.  When deciding how to categorize a specific project or program, it may be helpful to consider the project or program purpose in relation to your NHA goals. 

· If you are implementing or funding multicomponent projects, please count each component separately.  For example, you might be working on a project that involves the preservation of a building or site, site interpretation, and an event.  Using this example, each component would be counted as a separate project under the preservation, education and interpretation, and promotion categories.  If it is not possible to separate project components, please report on the project under the category that is most appropriate given the funding amount.      

· Retain all supporting documentation used in filling out this form in your office files until a program evaluation has been completed for your heritage area.  Per 2CFR Part 215.53, the NPS, as well as the Inspector General or Comptroller General, reserve the right to review supporting documents.  The NPS NHA Program Office reviews these forms and may contact you periodically to insure consistent and accurate reporting.  



Form Submittal 
Identify the name of the heritage area you represent at the top of this page.  The complete form includes your NHA name, goals, responses to applicable categories and metrics, and a scanned copy of page 2 with your name, signature, and date verifying the accuracy of the information provided.  

Email this form to the NHA Program Office at nha@nps.gov and copy your regional coordinator and agreements technical representative by close-of-business on the date listed at the top of this form.  

Assurance Statement
As the authorized representative of the local coordinating entity, I certify that the progress indicators reported below are supported by documentation that is verifiable in our records.  

	Name: Monte Bona

	[image: A picture containing invertebrate, arthropod, smoke, hydrozoan

Description automatically generated]Signature: 

	Date: 24 January 2023



Heritage Area Goals
In the space below please identify the heritage area goals that appear in your management plan or management plan update. 

Please identify your reporting cycle here by name (Federal fiscal, state, calendar, etc.): Click here to enter text. 
	1.  Financial Assistance and Capacity Building

	The numbers captured here reflect the work of the coordinating entity only.  Leverage metrics are intended to capture the economic contribution of NHAs.     

	LEVERAGE
Leverage is using what you already have, in this case HPP funding, to bring about more support than would be possible otherwise.  Include all sources that you secured this past fiscal year that you would not have had unless HPP funds were available. Other federal funds (not including HPP funds) may be included.     
1A.1 Total amount of funding leveraged, including other Federal funds, to implement heritage area activities this year $ 2,298,577
1A.2 Provide a breakdown of leveraged funds, include cash and in-kind donations in totals. 
State $ 1,594,000
Local Government $ 543,677
Private $ 160,900
Other Federal Funding (not HPP, but include other NPS funding) 
(Specify funding source): N/A $ N/A
Other (please specify): N/A $ N/A 
· Mat

	GRANTS
Grants are the transfer of money from a national heritage area coordinating entity to a recipient whose project proposal is selected through a review process.  Grants are awarded to recipients to accomplish the goals of the national heritage area.  Grants do not include sponsorships, contracts, or donations. 
1B.1 Total number of grants disbursed[footnoteRef:2] this year 24  [2:  Disbursed is defined as funds that have left the heritage area’s account and gone to a grant recipient. 
] 

1B.2 Total grant dollars disbursed this year $ 434,713
Please provide a breakdown of the grant funds distributed this year under the categories (2 - 7) below.

	
CAPACITY BUILDING
Capacity building assistance includes guidance related to historic preservation, education, heritage tourism, natural resource conservation, etc., or the organizational capacity of a partner organization.  Capacity building assistance does not include oversight related to administration of sub grants, phone calls directing the individuals to resources or informational meetings, etc.  
Count the number of organizations, not people.  For example, if one person represents two organizations, the number of organizations is two. 


1C.1 Number of organizations to which you provided capacity building assistance through trainings, workshops, onsite assessments, etc.  0
1C.2 Number of capacity building grants awarded this year 0
1C.3 Total dollar amount awarded $ 0
1C.4 In the space provided below, share any outcomes that have resulted from your capacity building assistance this year or in previous years.  Provide a short description with the project name, year project was completed, and indicator and data source for outcome.  

N/A


	2.  Historic Preservation & Other Community Enhancement Projects 

	If you did not engage in historic preservation or community enhancement work this year, please skip these metrics and move on to Category 3: Collections.

	WORK in PROGRESS.  The numbers reported under 2A – 2B below capture work that is advancing, but not yet completed.

	HISTORIC PRESERVATION GRANTS DISBURSED 
2A.1 Number of historic or cultural resource preservation grants disbursed this year 9
2A.2 Total dollar amount disbursed $ 293,150

	PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to enhance listed or eligible National Register properties (e.g., condition assessments, plans, research, etc.).  The same project can be reported on over multiple years, until it is completed.  
2B. Number of historic preservation projects begun or continued: 7

	COMPLETED WORK.  The numbers and information reported under 2C – 2F below captures completed work that the coordinating entity funded, led, or partnered-on with other parties.    

	2C. NOMINATIONS COMPLETED - Number of historic or cultural resources nominated to the National Register of Historic Places 0

	SITES PRESERVED - Historic sites (i.e. those listed or eligible for listing on the National Register of Historic Places) preserved through restoration, rehabilitation or adaptive reuse, and reconstruction 
2D.1 Number of sites preserved 9 (for a grouping of buildings indicate 1 district/number of contributing buildings)
2D.2 Total acreage of preserved landscapes, such as battlefields, etc. 0 

	SITES MAINTAINED – Historic properties (i.e. listed or eligible for listing on the National Register of Historic Places) maintained through monitoring and small-scale maintenance projects.  Note: If you own or manage historic building(s) or site(s) this is where you can capture your on-going maintenance efforts. 
2E.1 Number of sites maintained 19 (for a grouping of buildings indicate 1 district/number of contributing buildings)
2E.2 Total acreage of preserved landscapes, such as battlefields, etc. 0

	2F. OTHER COMMUNITY ENHANCEMENT PROJECTS COMPLETED – In the space provided, provide name and a short description of streetscape or façade improvement projects, as well as other projects that are intended to enhance communities (e.g., art projects or business development projects).  
Subrecipient: Panquitch City
Historic Main Street Revitalization Project 
Total Project Cost:  $75,000         	Federal: $25,000      	Matching Funds: $50,000
 
This project is a partnership with the Utah Dept. of Transportation, Panquitch City and Business Owners on the Historic Main Street that is listed on the National Register of Historic Places.
 
The purpose of the project is to slow traffic on U.S. Highway 89 and attract travelers to stop and visit the shops on Main Street. Work includes developing new sidewalks for better visitor access to the shops, creating a “strolling atmosphere” that is visitor friendly and providing parking by the shops to “keep heritage tourists downtown”. This project will follow Section 106 compliance. 

Subrecipient: Mt. Pleasant Main Street Program
Façade Projects 
Total Funding: $5,000             	Federal: $2500       	Matching Funds: $2500
 
Mt. Pleasant has been a Main Street Community since 1994. It functions in coordination with the National Main Street Center. This project consists of providing a small grant of $1,000 for façade work on a building located at 76 West Main. The project is being coordinated with SHPO for Section 106 because Mt. Pleasant’s Main Street is listed on the National Register of Historic Places. An additional $1500 is being set aside for another façade project.

Subrecipient: Sanpete County
North Sanpete Arts-Native American Statue project
Total Project Cost: $60,000   	Federal: $30,000	Matching Funds: $30,000
 
A life-sized bronze statue Chief Sanpitch will be unveiled this summer.  The project will continue telling the story of prominent historic Sanpete County Native Americans with an additional bronze of Chiefs Balckhawk and Wakara. MPNHA Request:  $30,000.

Subrecipient: Garfield County
Main Street Revitalization project
Total Project Cost: $60,000   	Federal: $30,000	Matching Funds: $30,000
 
Sanpete County, in behalf of Panguitch City, would like to request $30,000 as part of our Main Street Revitalization project.  We would use the funds with matching funds from each store owner to update and improve the facade of the historical buildings.  Awning would be replaced and with some vertical signage.

Subrecipient: Mt. Pleasant City
Main Street Facade Restoration Projects
Total Project Cost: $74,000   	Federal: $37,000	Matching Funds: $37,000
 
In conjunction with the Utah Main Street Program and the National Main Street Center. The projects will be on Mt. Pleasant Main Street and coordinated with Roger Roper, SHPO Officer.


	OUTCOMES OF COMPLETED WORK.  The outcomes reported under question 2G captures the results of your historic preservation and community development activities.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	2G. HISTORIC PRESERVATION & COMMUNITY ENHANCEMENT OUTCOMES - In the space provided below, please share outcomes that have resulted from your historic preservation work, including grant work, reported this year or in previous years.  Provide a short description that includes the project name, year project was completed, project partners, and indicator and data source for outcome. 
1. Restoration of Historic Presbyterian Church- Manti, Utah. Building now used by American Legion. Partners include Veterans Groups and Manti City. Work completed 11/10/2013. Grant$ 9,600
2. Casino Star Theater Restoration- Active historic movie theater for movies and live performances. Partners: Casino Star Theater Foundation and State of Utah (earmark), Utah Division of State History. Grant $31,000. Ongoing.
3. Kane County - Restoration of historic Mt. Carmel Church, now used as Visitor's Center.Partners: Kane County, State of Utah. Grant $20,000. Completed Sept 30, 2013.
4. Wayne County-Teasdale Daughters of Utah Pioneers Museum- Partners: Wayne County, Teasdale Town. Grant $13,000. Completed Sept 30, 2013.
5. Centerfield Historic Social Hall- Partner: Centerfield Town. Grant $10,000. Completed 9/30/12. 
6. Historic Panguitch City Grandstand- Partners: Garfield County, Panguitch. Grant $10, 000. Complete Sept. 30, 2018.
7. Historic Presbyterian Building- Partners: American Legion and Sanpete County Economic Development. Grant$ 9,600. Completed 11/15/13.
8. Fountain Green Social Hall and Theater- Partners: Fountain Green City. Grant $14,000. Completed 9/30/12.
9. Wayne County Cemetery Restoration Project- Partners: Wayne County Commission. Grant $12,600. Completed 9/30/12.
10. Snow College Alpine Station- Partner: Snow College. Grant $16,500. Completed 9/30/12. 
11. Spring City School- Partners: George S. and Dolores Dore' Eccles Foundation, Spring City Historic Preservation Commission, Save America's Treasures and numerous other donors. Grant $25,000. Sept. 30, 2017.
12. Manti Main Street historic building restoration- Partners: Manti City, Sanpete County Economic Development. Grant $7,000. Completed 9/30/12.
13. Manti historic City Hall- Partners: Manti city, Sanpete County Economic Development. Grant $14,450. Completed 9/30/12.
14. Ephraim Co-op historic building- Partners: Ephraim City, Sanpete County Economic Development. Grant $ 6,650. Completed 9/30/12.
15. Manti Daughters of Utah Pioneers Museum- Partner: Manti City. Grant $1,900. Completed 9/30/12.
16. Manti Carnegie Library restoration- Partners: Manti City, George S. and Delores Dore' Eccles Foundation. Grant$ 25,000. Completed 9/30/11.
17. Fairview Social Hall- Fairview City, Community Impact Board, George S. and Delores Dore' Eccles Foundation and numerous other donors. Grant $25,000. Completed 9/30/11.
18. Ephraim Carnegie Library restoration- Partners: Ephraim city, George S. and Delores Dore' Eccles Foundation and numerous other donors. Grant $20,000. Completed 9/30/10.
19. Mt. Pleasant Carnegie Library restoration- Partners: George S. and Delores Dore' Eccles Foundation, US Department of Agriculture Rural Development grant, US Department of Energy grant, Utah Division of State History. Completed 9/30/11.
20. Mt. Pleasant Armory, Mt. Pleasant Main Street Program- Partners: Preserve America grant, Utah Division of State History. Completed 9/30/11.
21. Lizzie and Charlie's Rag Rug Factory-Partners: Monroe Preservation Society. Grant $25,000. Completed 9/30/12.
22. Marysvale Town Old Rock School House-Partners: Marysvale City. Grant: $4800. Used as a heritage crafts store. Completed November 2014.
23. Carol Theater, Monroe-Grant: $15,000. Restoration of historic theater by non-profit entity.Used for old movies and live performances. Completed November 2014. Partner: Scenic Canyons Preservation Society.
24. Orson Hyde Office/Allred School, Spring City. Grant $9,000. Used as an art studio. Completed November 2014. Partner: Allred Family.
25. Old General Store, Spring City. Grant $5,000. Award-winning project on historic Main Street. Used in conjunction with Victory Hall, where live radio performances are conducted. Completed November 2014. Partner: Scenic Canyons Preservation Society.
26. Wasatch Academy Music Conservatory ... A major project in Mt. Pleasant Historic District. Completed December 2014. Partner: Wasatch Academy.
27. Gunnison Legacy Wall and Clarion Interpretive Signs-This project, which enhances Gunnison's downtown, was funded with a $30,000 grant we provided with matching funds of an equal amount. Partners included the American Jewish Preservation Society and Gunnison City. Completed September 30, 2015.
28. Gem Theater, Panguitch City Main Street Program. Budget: $55,000. Completed September 30, 2015. Partner: Scenic Canyons Preservation Society.
29. Heritage Rag Museum. Budget: $11475. Completed September 30, 2015. Partners: Marysvale and Piute County.
30. Kanab Heritage Center. Budget: $60,000. Completed March 31, 2016 as set forth in Task Agreement. Partner: Kanab City.
31. Wayne County Visitors Center. Budget: $30,000. Completed in March 31, 2016. Partner: Wayne County.
32. Mt. Pleasant Equestrian Center. Budget: $125,000. Completed September 30, 2015. Partner: Mt. Pleasant City.
33. Wasatch Academy Pierce Hall. Budget: 305, 000. Completed in March 31, 2016. Partner: Wasatch Academy.
34. Casino Star Theater Restoration. Budget: $137,625. Completed in March 31, 2016. Partner: Casino Star Theater Foundation.
35. Panguitch Main Street Project. Budget: $26, 465. Completed September 30, 2015. Partner: Panguitch Main Street Project.
36. Salina CCC/POW Restoration. Budget: $103,000. Completed in March 31, 2016. Partner: Salina City.
37. Miss Mary's Museum Restoration. Budget: $20,000. Completed September 30, 2015. Partner: Salina City.
38. Ephraim City Granary Project. Budget: $11,300. Completed in March 31, 2016. Partner: Ephraim City.
39. Ephraim City Granary Project. Budget: $11,300. Completed in March 31, 2016. Partner: Ephraim City.
40. Restoration/Renovation of Wasatch Academy Historic Administration Building. Projects completed in September 2016. Total budgets: $26,182. Partner: Wasatch Academy.
41. Restoration work on Mt. Pleasant City Hall and Armory Building. Budget: $51,500. Completed September 30, 2016. Partners: Mt. Pleasant City and Utah Division of State History.
42. Hanksville Community Hall Restoration. Budget: $322,000. Completed March 31, 2017.Partner: Hanksville Town.
43. Bicknell Theater and Community Center. Budget: $65,000. Completed September 30, 2016.This is in addition to $20,000 budgeted in FY2015. Partner: Bicknell Town.
44. Spring City School Restoration/Renovation Phase III. Budget for this phase: $575,000. Ongoing. Partners: George S. and Delores Dore' Eccles Foundation, Spring City Historic Preservation Commission, Completed Sept. 20, 30127
45. Save America's Treasures and numerous other donors. Butch Cassidy Cabin Restoration: Budget $219,141. Completed March 31, 2017. Partners included Garfield and Piute Counties, State of Utah, and Utah Division of State History.
46. CCC/Pow Camp Building/ Site Restoration: This is the second phase of a project. Budget for this phase: $50,000. Partners included Salina City, Utah Division of State History, non-profits and private donors. Completed Sept. 30, 2017
47. Spring City Victory Hall Restoration: Budget: $7.000. Partners: Spring City, Utah Division of State History. Completed September 30, 2017.
48. Monroe Carol Theater Restoration: Budget: $18,475. $190,000. Project partner: Carol Theater Restoration Committee. Completed September 30, 2017.
49. Jacob Hamblin Heritage Park. Budget: $190,000. Partners: Kanab City, Kane County, State of Utah. Completed March 31, 2018
50. Wayne County DIP Project: Budget: $36,000 Partner: Wayne County Completion Date: September 30, 2017.
51. Bicknell People's Mere Restoration: Budget: $24,000. Partner: People's Mere Restoration Partner: Completion Date: September 30, 2017
52. Spring City Historic School Restoration: This is the final phase of the restoration project: Budget for this phase: $459,843. Partners: Friends of Spring City, State of Utah, George S. and Dolores Dare's Eccles Foundation. Completed May 31, 2017.
53. Denver Rio Grande 1890's Depot Restoration: Budget: $50,000. Partners, Mt. Pleasant City, Scenic Canyons Preservation Society. Completed September 30, 2017.
54. Mt. View DUP Historic Building Restoration: Budget: $8,000. Pa1iner: Mt. View Daughters of Utah Pioneers. Completed September 30, 2017.
55. Miss Mary's Historic School/Museum Restoration: This is the second phase of this project.Budget for this phase: $22,618. Partners: Salina City, Miss Mary's Museum Committee. Completed: September 30, 2017.
56. Kanab Carnegie Library; Budget: $37,000; Partners: Kane County, Kanab City. Scheduled to be completed on March 31, 2019
57. Fremont School Bell; Budget; $10,000; Partners: Fremont chapter of the Daughters of Utah Pioneers. Scheduled to be completed on March 31, 2019
58. Historic Presbyterian Church Building; Budget: $9,000; Partners: local American Legion.Completed Sept. 30, 2018.
59. Wayne County DUP records project; Budget: $8,000. Scheduled to be completed on March 31, 2019.
60. Marysvale Historic Outdoor Dance Hall Restoration; Budget: $140,000; Partners: Marysvale Town. Scheduled to be completed on March 31, 2019
61. Garfield County Historic Fairgrounds Grandstand restoration; Budget: $10,000. Partners: Garfield County. Completed Sept. 30, 2018.
62. Wayne County DUP Historic Records Building Restoration: Budget: $8,000. Scheduled to be completed on March 31, 2019
63. Sanpete County Fairgrounds project: Budget: $160,000. Partners: Sanpete County. Completed Sept. 30, 2018.
64. Casino Star Theater restoration: Budget $92,000; Partners Casino Star Theater Foundation, George S. and Dolores Dore' Eccles Foundation. To be completed by March 31, 2019
65. Wasatch Academy Craighead vocational building restoration; Budget: $180,000; Partners: Wasatch Academy, George S. and Dolores Dore' Eccles Foundation. To be completed by March 31, 2019
66. Historic Denver Rio Grande Project: Budget: $13,000; Partners: Mt. Pleasant City CDRA. Completed Sept. 30, 2018.
67. Sanpete County CLG historic Homes Restoration project; Budget: $26,000; Partners; Sanpete County Certified Local Government, building owners. Completed Sept. 30, 2018.
68. Wayne County Teasdale Restoration Project. Total Project Cost: $125000, Federal Funding: $20000, Matching Funds: $105000. To be completed August 1, 2020.
69. Garfield County Historic Fairgrounds Restoration Project. Total Project Cost: $78900, Federal Funding: $20000, Matching Funds: $58900. Completed in 2019.
70. Casino Star Theatre “Take a Seat” Project. Total Project Cost: $105564, Federal Funding: $20000, Matching Funds: $85564. Completed in 2019.
71. Bishop’s Storehouse project. Total Project Cost: $68000, Federal Funding: $30000, Matching Funds: $38000. To be completed August 1, 2020.
72. Historic Manti City Hall. Total Project Cost: $3000, Federal Funding: $1500, Matching Funds: $1500. Completed in 2019.
73. Wayne County Heritage Park project. Total Project Cost: $40000, Federal Funding: $18000, Matching Funds: $22000. Completed in 2019.
74. The Scout House project. Total Project Cost: $60000, Federal Funding: $25000, Matching Funds: $35000. To be completed August 1, 2020.
75. Moroni Veterans’ Memorial. Total Project Cost: $67000, Federal Funding: $5000, Matching Funds: $62000. Completed in 2019.
76. Mt. Pleasant Depot project. Total Project Cost: $21500, Federal Funding: $10000, Matching Funds: $11500. Completed in 2019.
77. Mining Museum project. Total Project Cost: $40000, Federal Funding: $20000, Matching Funds: $20000. To be completed August 1, 2020.
78. Wayne County Fairgrounds Project. Total Project Cost: $200000, Federal Funding: $20000, Matching Funds: $180000. Completed in 2019.
79. Monroe City Hot Springs Park Project. Total Project Cost: $59418, Federal Funding: $25000, Matching Funds: $34418. Completed in 2020.
80. Miss Mary’s Museum Project. Total Project Cost: $22678.82, Federal Funding: $10000, Matching Funds: $12678.82. Completed in 2020.
81. Historic Spring City Firehouse. Total Project Cost: $8877, Federal Funding: $4439, Matching Funds: $4438. Still in progress as of January 2021.
82. Mt. Pleasant Relic House Project. Total Project Cost: $12370, Federal Funding: $5000, Matching Funds: $7370. Still in progress as of January 2021.
83. Ephraim City DUP Pioneer Park and DUP Museum Project. Total Project Cost: $56427.50,Federal Funding: $25000, Matching Funds: $31427.50. Still in progress as of January 2021.
84. Track 89 Boxcar Restoration and Train Depot project. Total Project Cost: $11,453.65. Federal Funding: $10,000. Matching Funds: $1,453.65. Still in Progress as of January 2022.
85. Boxcar Motel Visitor Experience Project. Total Project Cost: $135,108.79 Federal Funding: $10,000 Matching Funds: $125,108.79. Completed in the summer of 2021.
86. Mt. Pleasant and Fairview Historic Preservation Projects. Federal: $1,671.49 Match: $0. Still in progress as of January 2022.
87. Mt. Pleasant Relic House project. Federal: $5,000 Match: $18,351. Completed in August 2021.
88. Sindi’s Salon project. Federal: $3,000 Match: $3,000. Completed in September 2021.
89. Spring City Inn project. Federal: $8,000 Match: $16,585.17. Completed in July 2021.
90. Moroni Opera House project. Total Project: $27,000. Federal: $13,500. Match: $13,500. Completed in March 2021.
91. Subrecipient: Mt. Pleasant City
Denver Rio-Grande Depot and Boxcar Motel Project 
Total Project Cost: $105,000    	Federal: $10,000  	Cash Match: $95,000
92. Subrecipient: Manti City
Patton House Project
Total Project Cost: $7500	Federal: $3750 	Cash Match: $3750
93. Subrecipient: Salina City
Salina CCC/POW Camp Project
Total Project Cost: $12,800   	Federal: $6,400    	Cash Match: $6400
94. Subrecipient: Sanpete County
Casino-Star Theater Project
Total Project Cost: $110,000   	Federal: $15,000	Cash Match: $95,000
95. Subrecipient: Sanpete County
Pioneer Cemetery Project
Total Project Cost: $12,000	Federal: $6,000	Cash Match: $6,000
96. Subrecipient: Sanpete County
Mt. Pleasant Pioneer Historical Association (Relic House Museum) project
Total Project Cost: $20,000   	Federal: $10,000	Cash Match: $10,000
97. Subrecipient: Sanpete County
Sanpete County Courthouse project
Total Project Cost: $50,000   	Federal: $20,000	Cash Match: $30,000
98. Subrecipient: Piute County
Marysvale Mercantile Restoration
Total Project Cost: $75,000   	Federal: $37,500	Cash Match: $37,500
99. Subrecipient: Kane County
Historic Maynard Dixon Home project
Total Project Cost: $50,900   	Federal: $25,000	Cash Match: $25,900

	3.  Collections: Documentation and Conservation Projects
Paintings, Artifacts, Archives, Oral Histories, Video Histories, etc.

	Report here the work in which the primary purpose is to document cultural traditions or conserve artifacts.  If you are working on projects that use collections to develop interpretive or educational materials, please report these projects under Category 6: Education and Interpretation Programs.  

If you did not engage in work to develop or conserve cultural collections this year, please skip these metrics and move on to the Category 4: Land, Water and Environmental Conservation Projects. 

	WORK in PROGRESS.  The numbers reported under 3A – 3B capture work that is advancing, but not yet completed.

	GRANTS FOR COLLECTIONS DISBURSED
3A.1 Number of collections-related grants disbursed this year 1
3A.2 Total dollar amount disbursed this year $ 9,000

	PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) – Number of projects begun or continued to conserve heritage area artifacts (e.g., condition assessments, plans, research, etc.).  The same project can be reported on over multiple years, until it is completed.  
3B. Number of collections projects begun or continued: 1

	COMPLETED WORK.  The information reported under 3C below captures completed work that the coordinating entity funded, led, or partnered-on with other parties.    

	3C. COLLECTION PROJECTS – Provide the name and a brief description of the collections created, documented, or conserved.  Collections include oral histories, paintings, murals, historic documents, textiles, archaeology collections or material culture, such as boats or ships.  
Subrecipient: Wayne County
Wayne County Historical Society Project
Total Project Cost: $14,000    	Federal: $9000   	Matching Funds: $5000
 
This is a Wayne County Historical Society project that includes oral histories, video recordings, material compilation, printing, and distribution. A county and state depreciation schedule is being followed for the part of the project that includes the purchase of Xerox ED70 and Fiery EX-1 equipment.


	OUTCOMES OF COMPLETED WORK.  The outcomes reported under question 3D capture the results of your the collections conservation activities.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	3D. COLLECTIONS OUTCOMES - In the space provided below, please share outcomes that have resulted from your collections related work, including grants, reported this year or unreported in previous years.  Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome.  
N/A


	4.  Land, Water & Environmental Conservation Projects

	Note: Include wetland work under land restoration, instead of waterway restoration.   
If you did not engage in natural resource conservation work this year, please skip these metrics and move on to category 5: recreation development projects.  

	WORK in PROGRESS.  The numbers reported under 4A – 4B below capture work that is advancing, but not yet completed.

	LAND AND WATER CONSERVATION GRANTS AWARDED
4A.1. Number of natural resource conservation grants disbursed this year 0
4A.2 Total dollar amount disbursed this year $0

	PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to conserve natural or scenic areas (i.e., surveys, condition assessments, plans, etc.). The same project can be reported on over multiple years, until it is completed.  
4B. Number of conservation projects begun or continued: 0

	COMPLETED WORK.  The numbers reported under 4C – 4D below capture completed work that the coordinating entity funded, led, or partnered-on with other parties.    

	LAND RESTORATION
4C.1. Number of acres of land restored through invasive species removal, replanting, and toxic site clean-up. (one time) 0
4C.2. Number of acres of land maintained through monitoring and clean-up efforts 0

	WATERWAY RESTORATION (Streams, rivers, creeks, canals, etc.)
4D.1. Number of feet of waterways restored through appropriate in-water and bank restoration techniques (one time) 0
4D.2. Number of miles of waterways maintained through monitoring and clean-up efforts (please round to the ¼ mile) 0

	OTHER ENVIRONMENTAL CONSERVATION PROJECTS
4E. Provide name and a short description of other environmental conservation projects, such as climate change monitoring.  
N/A

	OUTCOMES OF COMPLETED WORK.  The outcomes reported in question 4E capture the results of your conservation activities.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	4F. CONSERVATION OUTCOMES - In the space provided below, please share outcomes that have resulted from your conservation work, including grants, reported this year or unreported in previous years.  Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome. 
N/A

	5.  Recreation Development Projects

	Note: This category does not include recreational events, programs or marketing materials.  Please include recreational events and marketing materials (such as brochures, maps, guides) under Category 7: Outreach and Marketing.   
If you did not engage in recreation development projects this year, please skip these metrics and move on to Category 6: Education & Interpretation Programs.   

	WORK in PROGRESS.  The numbers reported under 5A – 5B below capture work that is advancing, but not yet completed.

	RECREATION GRANTS AWARDED
5A.1 Number of recreation development grants disbursed this year: 5
5A.2 Total dollar amount disbursed this year $ 102,563

	PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to enhance recreational amenities (e.g., feasibility studies, plans, engineering, permitting, etc.).  The same project can be reported on over multiple years, until it is completed.  
5B. Number of recreation projects begun or continued: 1

	COMPLETED WORK.  The numbers reported under 5C – 5E below capture completed work that the coordinating entity funded, led, or partnered-on with other parties.    

	NEW TRAILS COMPLETED - Number of new miles of on or off road trails developed 
5C.1. On-road miles: 4
5C.2. Off-road miles: 43

	TRAILS MAINTAINED - Number of miles of on or off-road trails maintained through monitoring, clean-up and maintenance projects construction
5D.1. On-road miles: 0
5D.2. Off-road miles: US Forest Service and Counties maintain trails

	OTHER RECREATION DEVELOPMENT PROJECTS 
5E. Provide name and a short description of other trail or park enhancement projects, such as parking, signage, trail heads, lighting, etc. or trail designation projects.  For trail designations please identify the mileage. 
Subrecipient: Sanpete County
Gunnison Biking/Walking Trail Signage project
Total Project Cost: $10,000   	Federal: $5,000		Matching Funds: $5,000
 
The City has begun construction on 6.5 miles of Biking/Walking Trails a G-Hill, on the edge of town.  The trails will be completed by September 2022.  The City also plans to add another 2 miles of biking/walking trails to connect the G Hill with the in-town River Walk path next year.  The project will install kiosks and interpretive signs at G-Hill, as well as at the connection point of the River Walk path.  MPNHA Request:  $5,000.

Subrecipient: Wayne County
Historic Trails Project
Total Project Cost: $45,000   	Federal: $22,500	Matching Funds: $22,500
 
The Wayne County Office of Economic Development in conjunction with the Wayne County GIS / Road Department is proposing a Historical Trails Project to restore, document and produce sign age for trails in Wayne County with historical significance in regards to Logging on Boulder and Thousand Lake Mountains. In addition is the documentation and signage for the 19 43 World War II era plane crash in the Moroni Slopes area of the San Rafael desert. MPHNA Funds will be used for Documentation and publication of materials and Informational Kiosk (3).


	OUTCOMES OF COMPLETED WORK.  The outcomes reported under question 5G capture the results of your recreation work.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	5F. RECREATION OUTCOMES - In the space provided below, please share outcomes that have resulted from your recreation work, including grants, reported this year or unreported in previous years.  Provide a short description with the project name, year project was completed, project partners and indicator and data source for outcome. 
Subrecipient: Kane County
East Zion Trails Project
Total Project Cost: $100,000   	Federal: $15,000       	Matching Funds: $85,000
 
This project will complete the non-motorized trail network on the east side of Zion National Park, located on non-federal county land. The East Zion trails project is being established for public benefit as part of a collaboration and public/private partnership between the State of Utah, Kane County, Zion Forever, Zion Mountain Ranch and the American Conservation Experience—Mountain West Division (ACE). CEBA will be coordinating compliance work for NEPA. 

Subrecipient: Mt. Pleasant City and Sanpete County
Mt. Pleasant to Spring City Bike Path Project and Sanpete Trails Project
Total Project Cost: $717,594   	Federal: $45,063	Matching Funds:  $672,531

This is Phase II of a major non-motorized trail project sponsored by Mt. Pleasant City and including Spring City and Sanpete County as partners. The trail is being developed in compliance with a feasibility study conducted by Sunrise Engineering. UDOT paid for the study. 
The trail will connect Mt. Pleasant City to Spring City (both communities are on the National Register of Historic Places).
	
The Sanpete Trails Project is a coordinated project between Sanpete County and the U.S. Forest Service to improve outdoor recreation in Sanpete County. Work includes upgrading OHV routes on recreation roads, trailheads, signage, bike trails, and restrooms, and related improvements. Forest Service funds are not counted as matching. The Sanpete County Travel and Heritage Council is providing the match. 

Subrecipient: Sanpete County
Contoy Arena Project
Total Project Cost: $904,000   	Federal: $15,000		Matching Funds: $899,000
 
A warm-up building west of the Arena, other improvements, and/or equestrian trail maintenance on public lands. Received $340k from the Legislature for the warm-up building. MPNHA Request: $5,000. The $5000 will go to the warm-up building.


	6. Education and Interpretation Programs 

	The goal of education and interpretation programs is to increase people’s understanding of heritage area sites and stories.    
Note: Do not include annual meetings, conference presentations, awards ceremonies, open houses, annual fundraisers, and events.  These activities are reported under category 7: outreach and marketing.   
If you did not conduct interpretation work this year, please skip these metrics and move on to category 7: outreach and marketing.


	WORK in PROGRESS.  The numbers reported under 6A - 6B capture work that is advancing, but not yet ready to be offered to the public.

	EDUCATION GRANTS AWARDED
6A.1 Number of education and interpretation related grants disbursed this year: 2
6A.2 Total dollar amount disbursed this year:  $ 40,000 

	PROJECTS in DEVELOPMENT (Do Not Include Grant Projects Reported Above) - Number of education and interpretation projects in development (e.g., assessments, research, etc.).  The same project can be reported on over multiple years, until it is offered or made available to the public.  
6B. Number of education and interpretation projects in development: 0

	OFFERED PROGRAMS AND PRODUCTS.  The information reported under 6C – 6D below captures the work that the coordinating entity funded, led, or partnered with other parties to offer this year.  

	6C. PROGRAMS OFFERED - In the space below, provide name and a short description of the interpretive or educational programs supported by the NHA coordinating entity this year.  
Discovery Road TV Series in cooperation with Utah Education Network (UEN).
Town Track and Sanpete Art and History Tour.

	6D. PRODUCTS OFFERED - In the space below, provide name and a short description of the interpretive or educational products (print, web, or multi-media) supported by the NHA coordinating entity this year. 
We have completed 63 TV shows in total. This year seven were produced and distributed to TV stations and to schools through the Utah Education Network (UEN).
DVDs of Discovery Road episodes
MPNHA Books: Legends, Lore, and True Tales in Mormon Country, published by Arcadia Publishing / History Press. Available in Utah libraries and for purchase.
MPNHA YouTube Channel: https://www.youtube.com/channel/UCwY8IF4uHOhMHopvi-DQkdQ
MPNHA Website: MormonPioneerHeritage.org
Blackhawk War: Cultures in Conflict educational DVD, distributed to schools and other entities as an educational tool.

	OUTCOMES of PROGRAM AND PRODUCTS OFFERED.  The outcomes reported under question 6E capture the results of your education work.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	6E. EDUCATION OUTCOMES - In the space provided below, please share any outcomes that have resulted from heritage area educational work, including grants, reported this year or unreported in previous years.  Provide a short description with the project name, year project was completed, project partners and indicator and data source for outcome.  
Subrecipient: Discovery Road TV Series
“Thrive 125” Project 
Total Project Cost: $20,000 	Federal: $10,000       	Matching Funds: $10,000
 
This project includes the production costs associated with the on-going show that runs of four TV stations and is embedded on mormonpioneerheritage.org. The show is produced in coordination with public television station KUEN and the Utah Education Network.
 
The show being produced is titled “Banking on Statehood” and is being produced in conjunction with  Utah’s “Thrive 125”—the 125th Anniversary of Utah Statehood that was granted in 1896.

Subrecipient: Discovery Road TV Series
Discovery Road Project
Total Project Cost: $60,000   	Federal: $30,000	Matching Funds: $30,000
 
This is an on-going TV series that runs on four TV stations and is embedded on mormonpioneerheritage.org. The show is produced in conjunction with public television station KUEN and the Utah Education Network. Also includes a follow up book to our very successful “Legends, Lore and True Tales in Mormon Country.” This book would continue themes from the previous book but would correlate with shows we have aired. We would coordinate with KUEN.


	7.  Outreach and Marketing (include presentations, sponsorships, and other outreach activities here)

	Note: Include economic impact studies under products offered.   
If you did not conduct outreach or marketing work this year, please skip these metrics and move on to Category 8: Community Engagement.  

	WORK in PROGRESS.  The numbers reported under 7A – 7B capture work that is advancing, but not yet ready to be offered to the public.

	OUTREACH & MARKETING GRANTS AWARDED
7A.1 Number of outreach and marketing grants disbursed this year 1
7A.2 Total dollar amount disbursed this year $ $5,000 

	PROJECTS in DEVELOPMENT (Do Not Include Grant Projects Reported Above) - Number of promotion and marketing projects in development (e.g., assessments, research, etc.).  The same project can be reported on over multiple years, until it is offered or made available to the public.  
7B. Number of promotion and marketing projects in development: 0

	OFFERED EVENTS AND PRODUCTS.  The numbers reported under 7C – 7D below capture work that the coordinating entity funded, led, or partnered with other parties to offer to the public this year.  

	7C. EVENTS OFFERED (RACES, CELEBRATIONS, AWARDS CEREMONIES, FAM TOURS, ETC.) - In the space below, provide name and a short description of promotional activities supported by the coordinating entity. 
We supported events in the five heritage districts of the Mormon Pioneer National Heritage Area. These districts are Little Denmark, Sevier Valley, Headwaters, Under the Rim and Boulder Loop. Each event has its focus in the pioneer and cultural heritage of the respective district in which it is held.
1- Western Legends Roundup
2- Scandinavian Days
3- Mormon Pioneer Heritage Festival
4- Spring City Heritage Days
5- Everett Reuss Festival
6- Jacob Hamblin Days
7- Butch Cassidy Days 
8- Panguitch Quilt Walk
9- Map N Tour Project – This project promotes heritage and cultural tourism in multiple counties within the Heritage Area. This project will allow for integration of the MapNTour Web and Mobile App which will enhance user experience for both web and mobile platforms. It is a unique notification system that draws people to sites and has story telling capability and multi-media options. It centers on destination experiences and scalability to expand locations and content in phases.


	7D. PRODUCTS OFFERED (BROCHURES, ECONOMIC IMPACT STUDIES, WEBSITES, ETC.) - In the space below, provide name and a short description of promotional products supported by the coordinating entity.  
MPNHA website: MormonPioneerHeritage.org
MPNHA YouTube Channel: https://www.youtube.com/channel/UCwY8IF4uHOhMHopvi-DQkdQ
We continue to print and distribute a travel planner, maintain an active website and distribute "Discovery Road" shows via internet and broadcast. See Mormonpioneerheritage.org for an overview.
Map N Tour mobile tourism application.


	OUTCOMES of EVENTS AND PRODUCTS OFFERED.  The outcomes reported under question 7E capture the results of your promotion and marketing work.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	7E. OUTREACH & MARKETING OUTCOMES - In the space provided below, please share outcomes that have resulted from heritage area marketing activities reported this year or offered in previous years.  Outcomes could include increases in visitation to heritage area sites generated by marketing products.  Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome.  
· Travel Planner Re-Print
· Western Legends Roundup
· Scandinavian Days
· Mormon Pioneer Heritage Festival
· Spring City Heritage Days
· Everett Reuss Festival
· Jacob Hamblin Days
· Butch Cassidy Days 
· Panguitch Quilt Walk
· Map N Tour Project – This project promotes heritage and cultural tourism in multiple counties within the Heritage Area. This project will allow for integration of the MapNTour Web and Mobile App which will enhance user experience for both web and mobile platforms. It is a unique notification system that draws people to sites and has story telling capability and multi-media options. It centers on destination experiences and scalability to expand locations and content in phases.

	8.  Community Engagement

	The numbers captured here reflect the work of the NHA coordinating entity and partnership.  Please answer all questions below.      

	PARTNERSHIPS   
A partnership is a relationship between parties to accomplish a common goal, such as developing or implementing a heritage area project or offering heritage area programs.  Partnerships are characterized by mutual interest, commitment, and communication.  Please count partners one time, either as formal or informal partners. 
8A.1 Formal Partners are the organizations who you directly collaborate with on heritage area projects and programs and who are substantially involved in those projects or programs.  You may have an agreement in place to formalize your partnership with these organizations, but having an agreement is not a requirement for being a formal partner.  
Number of formal partners substantially engaged in National Heritage Area activities this year: 13

8A.2 Informal Partners are those organizations who you cooperate or coordinate with on projects and programs.  These organizations are not substantially involved in your projects or programs. 
Number of informal partners engaged in National Heritage Area activities this year: 72


	VOLUNTEERISM
Volunteer Count. Please count volunteers who are working on projects or programs that are coordinated and/or funded by the national heritage area coordinating entity.  Do not include volunteers at park units or other sites for which there was no investment of heritage area staff time or funding. 

8B.1 Total number of volunteers engaged in heritage area projects, programs or activities 340
8B.2 Total number of volunteer hours 8500 (please round-up to the nearest hour)
8B.3 Hourly value of volunteer time for your state or region (refer to www.independentsector.org/volunteer_time for your region) $ 24.14 
8B.4 Total dollar value of volunteer hours $ 205,190

	PROGRAM & EVENT PARTICIPANTS 
Program and Event Participant Count.  Please count participants who attended events or programs that were coordinated and/or funded by the national heritage area coordinating entity.  Do not include participants in programs at parks or other sites where there was no investment of heritage area staff time or funding. 
8C.1 Number of people who participated in heritage area educational programs this year: 22,000
8C.2 Number of people who participated in heritage area events (races, celebrations, ceremonies, etc.) this year: 32,000


	OTHER ACTIVITIES  
8D.1 In the space below, identify any other activities including community development, economic development or community engagement projects that do not fit into the seven categories above.  
N/A





















	Best Practice : Highlight a Successful Project or Program

	In the space below, please describe a creative, successful project or program undertaken or completed this year.  Please include images with captions and credit information.  
Also, include numbers if applicable – dollars invested and leveraged, communities or residents involved or impacted, properties preserved, miles of trails improved, etc.  Word count recommendation is 200 words.

	BEST PRACTICE

Sanpete County
The Heritage Trail Project Phases I and II
(Referred to in this document sometimes as the Mt. Pleasant to Spring City Bike Path Project and Sanpete Trails Project)

Total Project Cost:  $717,594      Federal Funding:  $45,063      Matching Funds:  $672,531

[image: ]This project is Phase II of a multi-phased trail project that has been in the planning and implementation stages since 2018 and was a project sparked and ignited from the MPNHA Management Plan.  

The Spring City Youth Council first came forward with the idea of building a multi-use trail between the communities of Mt Pleasant and Spring City.  Their idea captured the attention and interest of the local community leaders and from there has gained momentum to a point where there is now serious high-level discussion with other communities and groups to expand the Heritage Trail to other parts of the region.

[image: ]Phase I of approximately .60 miles was completed in 2020 with funding through the Federal Highway Administration channeled through the Utah Department of Transportation and Utah Office of Outdoor Recreation.  Along with the MPNHA, these partners have made this project not only possible but also successful.  The trail has been a real benefit and is used on a steady basis by a variety of users.

Grant funding will continue into fiscal year 2023 through a partnership with Utah Department of Transportation, Utah Office of Outdoor Recreation, Utah State Parks Recreational Trails Program, and others is now in place for the design and construction of phase II, approximately 4 miles of paved trail which will link the communities of Mt Pleasant and Spring City.  The environmental phase is just getting underway, and phase II of the trail is scheduled to be complete by the end of 2023 at which time the total project cost will be $2,317,000.

Other Best Practices

In addition to the trails project highlighted above, other best practices included revitalizing and restoring historic main streets.

[image: ][image: ]These images of Mt. Pleasant Main Street are a highlight of these main street projects.



NOTICES


PRIVACY ACT STATEMENT

General:  This information is provided pursuant to Public Law 93-579 (Privacy Act of 1974), December 21, 1984, for individuals completing this form.

Authority:  54 USC Ch. 3201, Historic Sites Act of 1935, as amended; 44 U.S.C. 3501, et seq., Paperwork Reduction Act of 1995; and individual pieces of legislation and associated amendments in 54 USC 100702 that enable the NPS, on behalf of the Secretary of the Interior, to provide federal financial, technical, and other assistance for the preservation of natural, cultural, historic, and scenic resources.

Purposes and Uses:  The NPS intends to track the progress of each heritage area on implementing its management plan and meeting performance goals. The information collected is used by the NHA program office in monitoring the progress of each heritage area. The collection of this information is necessary to allow for national oversight, analysis, coordination, technical and financial assistance, and support to National Heritage Areas to ensure consistency and accountability across the country.

Effects of Nondisclosure:  Financial disclosure is in accordance with 54 USC Ch. 3201, Pub. L. 113–291, div. B, title XXX, §3052(a)(2), Dec. 19, 2014, 128 Stat. 3802.

Information Regarding Disclosure of Your Social Security Number Under Public Law 93-579 Section 7(b): Your Social Security Number is not needed to complete this form.  


PAPERWORK REDUCTION ACT STATEMENT

We are collecting this information subject to the Paperwork Reduction Act (44 U.S.C. 3501) in response to the NHAs individual authorizing legislation requiring annual reporting as mandated by Congress. The information provided by NHA Coordinating Entities allows the NHA program office to allocate funding to heritage area management, prepare NPS budget justifications, and track management planning and implementation across NHAs. We may not conduct or sponsor and you are not required to respond to a collection of information unless it displays a currently valid OMB Control Number. OMB has reviewed and approved this survey and assigned OMB Control Number 1024-###, which expires ##/##/####.

ESTIMATED BURDEN STATEMENT

Public Reporting burden for this form is estimated to average 42 minutes per response, including the time it takes for reviewing instructions, gathering and maintaining data, and completing and reviewing the form. Comments regarding this burden estimate or any aspect of this form should be sent to the Information Collection Clearance Officer, National Park Service, 1201 Oakridge Drive, Fort Collins, CO 80525. 
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