| Heritage Area Name: | Mormon Pioneer National Heritage Area | Deadline: Jan. 26, 2024 |  |
| --- | --- | --- | --- |

Purpose

The information collected through this form will be used by the National Park Service (NPS), National Heritage Areas (NHA) Program Office and regional program offices to track each heritage area management or coordinating entity’s (coordinating entity) progress on management plan implementation.  The progress measures outlined in the categories below capture information about the diverse heritage area activities and approaches to these activities (process measures), direct products or services offered (output measures), and the results of the products or services (outcome measures).

The NPS will use the responses to the questions reported here in annual program reports and publications and to inform individual heritage area evaluations.

#### Reporting Instructions

The progress measures in this form are grouped under eight categories, capturing the diverse work of the coordinating entities throughout the country.  We recognize that each heritage area and coordinating entity is unique.  Therefore, not all of the categories or measures presented below will apply.

- The data reported here shall reflect the work that the coordinating entity led, funded or partnered with others to complete this year.

- Report all work that the coordinating entity was involved in to implement the National Heritage Area Management Plan.  Include work supported by Heritage Partnership Program (HPP) funding and other heritage area funding sources.

- Report data for the same 12-month cycle (calendar, federal, and fiscal) that you reported last year.

- Measures under categories 2 – 7 are sequenced to capture work in progress, work that is completed, and the outcomes of completed work.

- Follow the specific instructions for each category and measure.  Please be consistent in how you categorize your work.  When deciding how to categorize a specific project or program, it may be helpful to consider the project or program purpose in relation to your NHA goals.

- If you are implementing or funding multicomponent projects, please count each component separately.  For example, you might be working on a project that involves the preservation of a building or site, site interpretation, and an event.  Using this example, each component would be counted as a separate project under the preservation, education and interpretation, and promotion categories.  If it is not possible to separate project components, please report on the project under the category that is most appropriate given the funding amount.

- Retain all supporting documentation used in filling out this form in your office files until a program evaluation has been completed for your heritage area.  Per 2CFR Part 215.53, the NPS, as well as the Inspector General or Comptroller General, reserve the right to review supporting documents.  The NPS NHA Program Office reviews these forms and may contact you periodically to insure consistent and accurate reporting.

Form Submittal

Identify the name of the heritage area you represent at the top of this page.  The complete form includes your NHA name, goals, responses to applicable categories and metrics, and a scanned copy of page 2 with your name, signature, and date verifying the accuracy of the information provided.

Email this form to the NHA Program Office at nha@nps.gov and copy your regional coordinator and agreements technical representative by close-of-business on the date listed at the top of this form.

#### Assurance Statement

As the authorized representative of the local coordinating entity, I certify that the progress indicators reported below are supported by documentation that is verifiable in our records.

Name: Monte Bona

Signature:

Date: 24 January 2024

Heritage Area Goals

In the space below please identify the heritage area goals that appear in your management plan or management plan update.

Please identify your reporting cycle here by name (Federal fiscal, state, calendar, etc.): Click here to enter text.

1. Financial Assistance and Capacity Building

The numbers captured here reflect the work of the coordinating entity only. Leverage metrics are intended to capture the economic contribution of NHAs.

LEVERAGE Leverage is using what you already have, in this case HPP funding, to bring about more support than would be possible otherwise. Include all sources that you secured this past fiscal year that you would not have had unless HPP funds were available. Other federal funds (not including HPP funds) may be included. 1A.1 Total amount of funding leveraged, including other Federal funds, to implement heritage area activities this year $ 2,833,537.44 1A.2 Provide a breakdown of leveraged funds, include cash and in-kind donations in totals. State $ 1,968,462 Local Government $ 865,075.44 Private $ 0 Other Federal Funding (not HPP, but include other NPS funding) (Specify funding source): N/A $ N/A Other (please specify): N/A $ N/A - Mat

GRANTS Grants are the transfer of money from a national heritage area coordinating entity to a recipient whose project proposal is selected through a review process. Grants are awarded to recipients to accomplish the goals of the national heritage area. Grants do not include sponsorships, contracts, or donations. 1B.1 Total number of grants disbursed this year 26 1B.2 Total grant dollars disbursed this year $ 500,000 Please provide a breakdown of the grant funds distributed this year under the categories (2 - 7) below.

CAPACITY BUILDING Capacity building assistance includes guidance related to historic preservation, education, heritage tourism, natural resource conservation, etc., or the organizational capacity of a partner organization. Capacity building assistance does not include oversight related to administration of sub grants, phone calls directing the individuals to resources or informational meetings, etc. Count the number of organizations, not people. For example, if one person represents two organizations, the number of organizations is two. 1C.1 Number of organizations to which you provided capacity building assistance through trainings, workshops, onsite assessments, etc. 0 1C.2 Number of capacity building grants awarded this year 0 1C.3 Total dollar amount awarded $ 0 1C.4 In the space provided below, share any outcomes that have resulted from your capacity building assistance this year or in previous years. Provide a short description with the project name, year project was completed, and indicator and data source for outcome. N/A

2. Historic Preservation & Other Community Enhancement Projects

If you did not engage in historic preservation or community enhancement work this year, please skip these metrics and move on to Category 3: Collections.

WORK in PROGRESS. The numbers reported under 2A – 2B below capture work that is advancing, but not yet completed.

HISTORIC PRESERVATION GRANTS DISBURSED 2A.1 Number of historic or cultural resource preservation grants disbursed this year 9 2A.2 Total dollar amount disbursed $ 264,229

PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to enhance listed or eligible National Register properties (e.g., condition assessments, plans, research, etc.). The same project can be reported on over multiple years, until it is completed. 2B. Number of historic preservation projects begun or continued: 6

COMPLETED WORK. The numbers and information reported under 2C – 2F below captures completed work that the coordinating entity funded, led, or partnered-on with other parties.

2C. NOMINATIONS COMPLETED - Number of historic or cultural resources nominated to the National Register of Historic Places 0

SITES PRESERVED - Historic sites (i.e. those listed or eligible for listing on the National Register of Historic Places) preserved through restoration, rehabilitation or adaptive reuse, and reconstruction 2D.1 Number of sites preserved 9 (for a grouping of buildings indicate 1 district/number of contributing buildings) 2D.2 Total acreage of preserved landscapes, such as battlefields, etc. 0

SITES MAINTAINED – Historic properties (i.e. listed or eligible for listing on the National Register of Historic Places) maintained through monitoring and small-scale maintenance projects. Note: If you own or manage historic building(s) or site(s) this is where you can capture your on-going maintenance efforts. 2E.1 Number of sites maintained 19 (for a grouping of buildings indicate 1 district/number of contributing buildings) 2E.2 Total acreage of preserved landscapes, such as battlefields, etc. 0

2F. OTHER COMMUNITY ENHANCEMENT PROJECTS COMPLETED – In the space provided, provide name and a short description of streetscape or façade improvement projects, as well as other projects that are intended to enhance communities (e.g., art projects or business development projects). Subrecipient; Project; Federal; Match; Description. Casino Star Theatre; Casino Star Theatre Project; $ 45,000.00; $ 105,626.00; The budget for the restroom renovation of the historic theatre has changed since the FY22 grant was awarded. The current attached budget includes the expansion of restroom capacity and provides ADA access for patrons during large events, concerts, and major movie nights.. Kanab City; Kanab Museum Project; $ 20,000.00; $ 26,601.88; The purpose of this project is to help complete a renovation of the Kanab Museum. The Kanab Museum, located in a historic Public Library building, is currently undergoing a renovation project aimed at enhancing the preservation of its valuable collections. The project, which began in 2019, involved major interior renovations and the assessment and replacement of damaged museum cases. Despite significant progress being made by September 2021, the restoration was temporarily stopped due to difficulties in repairing the historical wood floors. However, with the help of a capital project grant awarded in November 2022, the project has resumed, and the primary focus is on completing the floor repairs and securing funding for new museum cases. The new cases will be instrumental in ensuring the preservation of the museum’s collections by providing adequate protection from environmental factors, such as dust, humidity, and light, while also enhancing their presentation.. Moroni; Moroni Opera House Project; $ 6,866.00; $ 6,442.77; Historic Moroni Opera House- replace HVAC and add large security boulders out front to prevent vehicles that miss the turn from colliding with the historic building.. Mt. Pleasant City Community Development and Renewal Agency; Mt. Pleasant CDRA Railroad Park Project; $ 27,510.00; $ -; Pages 35-37 of the Management Plan outline the important role railroads played in the area’s heritage. The historic Denver Rio-Grande Depot in Mt. Pleasant is highlighted as Figure 47 on page 36 of the Plan. This project is being developed as a public/private partnership to emphasize our railroad heritage and thereby promote heritage tourism and recreation. Supporting Railroad equipment, signals, and railroad theme enhancement materials.. Mt. Pleasant City Community Development and Renewal Agency; Mt. Pleasant Railroad Park Project; $ 67,403.00; $ 93,893.00. Redmond Town; Redmond Town Hall Project; $ 15,000.00; $ 15,000.00; The city will hire a contractor to make some substantial repairs and restoration work on the 1881/1890s structure. This will include the following: reroofing the original 1881 section, including repairing/replacing rafters as necessary and replacing the roof deck; making repairs to some sections of the walls on the 1881 section; repair, prep and repaint exterior woodwork on both sections, including the wood windows; install simple, non-obtrusive store windows to help protect the original windows and reduce energy costs; weatherize the bell tower so it doesn't leak; and replace the rain gutters and downspouts to direct rainwater and snowmelt away from the building. Section 106 consultation has been completed for this project and received SHPO approval.. Redmond Town Hall Rehab Project; $ 22,000.00; $ 22,000.00. Salina City; Salina CCC/POW Camp Rehab Project; $ 10,450.00; $ 10,450.00; The city will hire a contractor to re-roof some of the four structures and install new siding material on several walls where the material has failed or is in poor condition. The rolled roofing with wood battens that was installed a decade or so ago has not weathered well, so this time 30-year architectural-grade asphalt shingles will be installed. Likewise, the tar-paper sheathing and wood batterns that were installed on some of the walls has not weathered well over the past decade, so Hardie Board siding (painted black to resemble tar paper) with battens will be used as the replacement material. This was used on some of the walls a decade or so ago and it has held up extremely well and conveys a very historically accurate look. While this complex is historically important, it is not eligible for National Register listing due to substantial new construction and other significant modifications to the camp layout.. Spring City; 1916 Spring City Junior High Project; $ 50,000.00; $ 97,347.98; 1916 Spring City Junior High School building thorough rehabilitation, including repairs and stabilization. The restrooms are not ADA compliant; the building has some subsidence in the southwest corner which is causing exterior brick deterioration, it has some foundation and soffit and fascia issues which cause leaking during high water levels due to weather, etc. Replace the windows with high-quality, energy efficient windows that would restore the facade to its original appearance. This is a multi-phase project that will be developed over a three-year period. The budget for the total project is $350,000. The first phase is budgeted for $100,000 to repair exterior brick that has deteriorated, stabilize the foundation, correct soffit, and fascia issues..

OUTCOMES OF COMPLETED WORK. The outcomes reported under question 2G captures the results of your historic preservation and community development activities. Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred. Outcomes related to individual and cumulative grant activities may be included.

2G. HISTORIC PRESERVATION & COMMUNITY ENHANCEMENT OUTCOMES - In the space provided below, please share outcomes that have resulted from your historic preservation work, including grant work, reported this year or in previous years. Provide a short description that includes the project name, year project was completed, project partners, and indicator and data source for outcome. #; Project Title; Recipients and partners; Other entities; Federal Funds; Matching Funds; Total Project; Completion Date; Status; Notes. 1; Restoration of Historic Presbyterian Church - Manti; Manti City; Veterans Groups; $9,600.00; 11-10-2013; Completed. 2; Casino Star Theater Restoration; Casino Star Theater Foundation; State of Utah, Utah Division of State History; $31,000.00; Completed. 3; Restoration of historic Mt. Carmel Church; Kane County; State of Utah; $20,000.00; 09-30-2013; Completed. 4; Wayne County-Teasdale Daughters of Utah Pioneers Museum; Teasdale Town; Wayne County; $13,000.00; 09-30-2013; Completed. 5; Centerfield Historic Social Hall; Centerfield Town; $10,000.00; 09-30-2012; Completed. 6; Historic Panguitch City Grandstand; Panguitch; Garfield County; $10,000.00; 09-30-2018; Completed. 7; Historic Presbyterian Building; Sanpete County Economic Development; American Legion; $9,600.00; 11-15-2013; Completed. 8; Fountain Green Social Hall and Theater; Fountain Green City; $14,000.00; 09-30-2012; Completed. 9; Wayne County Cemetery Restoration Project; Wayne County Commission; $12,600.00; 09-30-2012; Completed. 10; Snow College Alpine Station; Snow College; $16,500.00; 09-30-2012; Completed. 11; Spring City School; Spring City Historic Preservation Commission, Save America's Treasures, numerous other donors; George S. and Dolores Dore' Eccles Foundation; $25,000.00; 09-30-2017; Completed. 12; Manti Main Street historic building restoration; Manti City; Sanpete County Economic Development; $7,000.00; 09-30-2012; Completed. 13; Manti historic City Hall; Manti City; Sanpete County Economic Development; $14,450.00; 09-30-2012; Completed. 19; Ephraim Co-op historic building; Ephraim City; Sanpete County Economic Development; $6,650.00; 09-30-2012; Completed. 20; Manti Daughters of Utah Pioneers Museum; Manti City; $1,900.00; 09-30-2012; Completed. 21; Manti Carnegie Library restoration; Manti City; George S. and Delores Dore' Eccles Foundation; $25,000.00; 09-30-2011; Completed. 22; Fairview Social Hall; Fairview City; Community Impact Board, numerous other donors; $25,000.00; 09-30-2011; Completed. 23; Ephraim Carnegie Library restoration; Ephraim City; George S. and Delores Dore' Eccles Foundation; $20,000.00; 09-30-2010; Completed. 24; Mt. Pleasant Carnegie Library restoration; George S. and Delores Dore' Eccles Foundation; US Department of Agriculture Rural Development grant, Utah Division of State History; 09-30-2011; Completed. 25; Mt. Pleasant Armory; Mt. Pleasant Main Street Program; Preserve America grant, Utah Division of State History; 09-30-2011; Completed. 26; Lizzie and Charlie's Rag Rug Factory; Monroe Preservation Society; $25,000.00; 09-30-2012; Completed. 27; Marysvale Town Old Rock School House; Marysvale City; $4,800.00; 11-01-2014; Completed; Used as a heritage crafts store. 28; Carol Theater; Monroe; Scenic Canyons Preservation Society; $15,000.00; 11-01-2014; Completed; Restoration of historic theater by non-profit entity,. 29; Orson Hyde Office/Allred School; Spring City; Allred Family; $9,000.00; 11-01-2014; Completed; Used as an art studio. 30; Old General Store; Spring City; $5,000.00; 11-01-2014; Completed; Award-winning project on historic Main Street, Used in conjunction with Victory Hall where live radio performances are conducted. 31; Wasatch Academy Music Conservatory; Wasatch Academy; 12-01-2014; Completed; A major project in Mt. Pleasant Historic District. 32; Gunnison Legacy Wall and Clarion Interpretive Signs; Gunnison City; American Jewish Preservation Society; $30,000.00; 09-30-2015; Completed. 33; Gem Theater; Panguitch City Main Street Program; Scenic Canyons Preservation Society; $55,000.00; 09-30-2015; Completed. 34; Heritage Rag Museum; Marysvale and Piute County; $11,475.00; 09-30-2015; Completed. 35; Kanab Heritage Center; Kanab City; $60,000.00; 03-31-2016; Completed; as set forth in Task Agreement. 36; Wayne County Visitors Center; Wayne County; $30,000.00; 03-31-2016; Completed. 37; Mt. Pleasant Equestrian Center; Mt. Pleasant City; $125,000.00; 09-30-2015; Completed. 38; Wasatch Academy Pierce Hall; Wasatch Academy; $305,000.00; 03-31-2016; Completed. 39; Casino Star Theater Restoration; Casino Star Theater Foundation; $137,625.00; 03-31-2016; Completed. 40; Panguitch Main Street Project; Panguitch Main Street Project; $26,465.00; 09-30-2015; Completed. 41; Salina CCC/POW Restoration; Salina City; $103,000.00; 03-31-2016; Completed. 42; Miss Mary's Museum Restoration; Salina City; $20,000.00; 09-30-2015; Completed. 43; Ephraim City Granary Project; Ephraim City; $11,300.00; 03-31-2016; Completed. 44; Restoration/Renovation of Wasatch Academy Historic Administration Building; Wasatch Academy; $26,182.00; 09-30-2016; Completed; Projects completed in September 2016. 45; Restoration work on Mt. Pleasant City Hall and Armory Building; Mt. Pleasant City; Utah Division of State History; $51,500.00; 09-30-2016; Completed. 46; Hanksville Community Hall Restoration; Hanksville Town; $322,000.00; 03-31-2017; Completed. 47; Bicknell Theater and Community Center; Bicknell Town; $65,000.00; 09-30-2016; Completed; This is in addition to 20000 budgeted in FY2015. 48; Spring City School Restoration/Renovation Phase III; George S. and Delores Dore' Eccles Foundation; Spring City Historic Preservation Commission; $575,000.00; 09-20-2017; Completed. 49; Save America's Treasures and numerous other donors; Garfield and Piute Counties; State of Utah, Utah Division of State History; $219,141.00; 03-31-2017; Completed; Butch Cassidy Cabin Restoration. 50; CCC/Pow Camp Building/Site Restoration; Salina City; Utah Division of State History, non-profits and private donors; $50,000.00; 09-30-2017; Completed; This is the second phase of a project. 51; Spring City Victory Hall Restoration; Spring City; Utah Division of State History; $7,000.00; 09-30-2017; Completed. 52; Monroe Carol Theater Restoration; Carol Theater Restoration Committee; $18,475.00; $190,000.00; $208,475.00; 09-30-2017; Completed. 53; Jacob Hamblin Heritage Park; Kanab City; Kane County, State of Utah; $190,000.00; 03-31-2018; Completed. 54; Wayne County DIP Project; Wayne County; $36,000.00; 09-30-2017; Completed. 55; Bicknell People's Mere Restoration; People's Mere Restoration Partner; $24,000.00; 09-30-2017; Completed. 56; Spring City Historic School Restoration; Friends of Spring City; State of Utah, George S. and Dolores Dare's Eccles Foundation; $459,843.00; 05-31-2017; Completed; This is the final phase of the restoration project. 57; Denver Rio Grande 1890's Depot Restoration; Mt. Pleasant City; Scenic Canyons Preservation Society; $50,000.00; 09-30-2017; Completed. 58; Mt. View DUP Historic Building Restoration; Mt. View Daughters of Utah Pioneers; $8,000.00; 09-30-2017; Completed. 59; Miss Mary's Historic School/Museum Restoration; Salina City; Miss Mary's Museum Committee; $22,618.00; 09-30-2017; Completed; This is the second phase of this project. 60; Kanab Carnegie Library; Kane County; Kanab City; $37,000.00; 03-31-2019; Scheduled. 61; Fremont School Bell; Fremont chapter of the Daughters of Utah Pioneers; $10,000.00; 03-31-2019; Scheduled. 62; Historic Presbyterian Church Building; local American Legion; $9,000.00; 09-30-2018; Completed. 63; Wayne County DUP records project; $8,000.00; 03-31-2019; Scheduled. 64; Marysvale Historic Outdoor Dance Hall Restoration; Marysvale Town; $140,000.00; 03-31-2019; Scheduled. 65; Garfield County Historic Fairgrounds Grandstand restoration; Garfield County; $10,000.00; 09-30-2018; Completed. 66; Wayne County DUP Historic Records Building Restoration; $8,000.00; 03-31-2019; Scheduled. 67; Sanpete County Fairgrounds project; Sanpete County; $160,000.00; 09-30-2018; Completed. 68; Casino Star Theater restoration; Casino Star Theater Foundation; George S. and Dolores Dore' Eccles Foundation; $92,000.00; 03-31-2019; Scheduled. 69; Wasatch Academy Craighead vocational building restoration; Wasatch Academy; George S. and Dolores Dore' Eccles Foundation; $180,000.00; 03-31-2019; Scheduled. 70; Historic Denver Rio Grande Project; Mt. Pleasant City CDRA; $13,000.00; 09-30-2018; Completed. 71; Sanpete County CLG historic Homes Restoration project; Sanpete County Certified Local Government; building owners; $26,000.00; 09-30-2018; Completed. 72; Wayne County Teasdale Restoration Project; $20,000.00; $105,000.00; $125,000.00; 08-01-2020; Scheduled. 73; Garfield County Historic Fairgrounds Restoration Project; $20,000.00; $58,900.00; $78,900.00; $2,019.00; Completed. 74; Casino Star Theatre “Take a Seat” Project; $20,000.00; $85,564.00; $105,564.00; $2,019.00; Completed. 75; Bishop’s Storehouse project; $30,000.00; $38,000.00; $68,000.00; 08-01-2020; Scheduled. 76; Historic Manti City Hall; $1,500.00; $1,500.00; $3,000.00; $2,019.00; Completed. 77; Wayne County Heritage Park project; $18,000.00; $22,000.00; $40,000.00; $2,019.00; Completed. 78; The Scout House project; $25,000.00; $35,000.00; $60,000.00; 08-01-2020; Scheduled. 79; Moroni Veterans’ Memorial; $5,000.00; $62,000.00; $67,000.00; $2,019.00; Completed. 80; Mt. Pleasant Depot project; $10,000.00; $11,500.00; $21,500.00; $2,019.00; Completed. 81; Mining Museum project; $20,000.00; $20,000.00; $40,000.00; 08-01-2020; Scheduled. 82; Wayne County Fairgrounds Project; $20,000.00; $180,000.00; $200,000.00; $2,019.00; Completed. 83; Monroe City Hot Springs Park Project; $25,000.00; $34,418.00; $59,418.00; $2,020.00; Completed. 84; Miss Mary’s Museum Project; $10,000.00; $12,678.82; $22,678.82; $2,020.00; Completed. 85; Historic Spring City Firehouse; $4,439.00; $4,438.00; $8,877.00; Completed. 86; Mt. Pleasant Relic House Project; $5,000.00; $7,370.00; $12,370.00; Completed. 87; Ephraim City DUP Pioneer Park and DUP Museum Project; $25,000.00; $31,427.50; $56,427.50; Completed. 88; Track 89 Boxcar Restoration and Train Depot project; $10,000.00; $1,453.65; $11,453.65; Completed. 89; Boxcar Motel Visitor Experience Project; $10,000.00; $125,108.79; $135,108.79; Summer 2021; Completed. 90; Mt. Pleasant and Fairview Historic Preservation Projects; $1,671.49; $0.00; $1,671.49; In Progress; Federal. 91; Mt. Pleasant Relic House project; $5,000.00; $18,351.00; $23,351.00; August 2021; Completed. 92; Sindi’s Salon project; $3,000.00; $3,000.00; $6,000.00; September 2021; Completed. 93; Spring City Inn project; $8,000.00; $16,585.17; $24,585.17; July 2021; Completed. 94; Moroni Opera House project; $13,500.00; $13,500.00; $27,000.00; March 2021; Completed. 95; Denver Rio-Grande Depot and Boxcar Motel Project; Subrecipient: Mt. Pleasant City; $10,000.00; $95,000.00; $105,000.00; Summer 2021; Completed. 96; Patton House Project; Subrecipient: Manti City; $3,750.00; $3,750.00; $7,500.00. 97; Salina CCC/POW Camp Project; Subrecipient: Salina City; $6,400.00; $6,400.00; $12,800.00. 98; Casino-Star Theater Project; Subrecipient: Sanpete County; $15,000.00; $95,000.00; $110,000.00. 99; Pioneer Cemetery Project; Subrecipient: Sanpete County; $6,000.00; $6,000.00; $12,000.00. 100; Mt. Pleasant Pioneer Historical Association Relic House Museum project; Subrecipient: Sanpete County; $10,000.00; $10,000.00; $20,000.00. 101; Sanpete County Courthouse project; Subrecipient: Sanpete County; $20,000.00; $30,000.00; $50,000.00. 102; Marysvale Mercantile Restoration; Subrecipient: Piute County; $37,500.00; $37,500.00; $75,000.00. 103; Historic Maynard Dixon Home project; Subrecipient: Kane County; $25,000.00; $25,900.00; $50,900.00. 104; Casino Star Theatre Project; Casino Star Theatre; $45,000.00; $105,626.00; $150,626.00. 105; Kanab Museum Project; Kanab City; $20,000.00; $26,601.88; $46,601.88. 106; Moroni Opera House project; Moroni City; $6,866.00; $6,442.77; $13,308.77. 107; Mt. Pleasant CDRA Railroad Park Project; Mt. Pleasant CDRA; $27,510.00; $27,510.00; $55,020.00. 108; Mt. Pleasant Railroad Park Project; Mt. Pleasant CDRA; $67,893.00; $67,893.00; $135,786.00. 109; Redmond Town Hall Project; Redmond; $15,000.00; $15,000.00; $30,000.00. 110; Redmond Town Hall Rehab Project; Redmond; $22,000.00; $22,000.00; $44,000.00. 111; Salina CCC/POW Camp Rehab Project; Salina; $10,450.00; $10,450.00; $20,900.00. 112; 1916 Spring City Junior High Project; Spring City; $50,000.00; $97,347.98; $147,347.98.

3. Collections: Documentation and Conservation Projects Paintings, Artifacts, Archives, Oral Histories, Video Histories, etc.

Report here the work in which the primary purpose is to document cultural traditions or conserve artifacts. If you are working on projects that use collections to develop interpretive or educational materials, please report these projects under Category 6: Education and Interpretation Programs. If you did not engage in work to develop or conserve cultural collections this year, please skip these metrics and move on to the Category 4: Land, Water and Environmental Conservation Projects.

WORK in PROGRESS. The numbers reported under 3A – 3B capture work that is advancing, but not yet completed.

GRANTS FOR COLLECTIONS DISBURSED 3A.1 Number of collections-related grants disbursed this year 0 3A.2 Total dollar amount disbursed this year $ 0

PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) – Number of projects begun or continued to conserve heritage area artifacts (e.g., condition assessments, plans, research, etc.). The same project can be reported on over multiple years, until it is completed. 3B. Number of collections projects begun or continued: 0

COMPLETED WORK. The information reported under 3C below captures completed work that the coordinating entity funded, led, or partnered-on with other parties.

3C. COLLECTION PROJECTS – Provide the name and a brief description of the collections created, documented, or conserved. Collections include oral histories, paintings, murals, historic documents, textiles, archaeology collections or material culture, such as boats or ships.

OUTCOMES OF COMPLETED WORK. The outcomes reported under question 3D capture the results of your the collections conservation activities. Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred. Outcomes related to individual and cumulative grant activities may be included.

3D. COLLECTIONS OUTCOMES - In the space provided below, please share outcomes that have resulted from your collections related work, including grants, reported this year or unreported in previous years. Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome. N/A

4. Land, Water & Environmental Conservation Projects

Note: Include wetland work under land restoration, instead of waterway restoration. If you did not engage in natural resource conservation work this year, please skip these metrics and move on to category 5: recreation development projects.

WORK in PROGRESS. The numbers reported under 4A – 4B below capture work that is advancing, but not yet completed.

LAND AND WATER CONSERVATION GRANTS AWARDED 4A.1. Number of natural resource conservation grants disbursed this year 0 4A.2 Total dollar amount disbursed this year $0

PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to conserve natural or scenic areas (i.e., surveys, condition assessments, plans, etc.). The same project can be reported on over multiple years, until it is completed. 4B. Number of conservation projects begun or continued: 0

COMPLETED WORK. The numbers reported under 4C – 4D below capture completed work that the coordinating entity funded, led, or partnered-on with other parties.

LAND RESTORATION 4C.1. Number of acres of land restored through invasive species removal, replanting, and toxic site clean-up. (one time) 0 4C.2. Number of acres of land maintained through monitoring and clean-up efforts 0

WATERWAY RESTORATION (Streams, rivers, creeks, canals, etc.) 4D.1. Number of feet of waterways restored through appropriate in-water and bank restoration techniques (one time) 0 4D.2. Number of miles of waterways maintained through monitoring and clean-up efforts (please round to the ¼ mile) 0

OTHER ENVIRONMENTAL CONSERVATION PROJECTS 4E. Provide name and a short description of other environmental conservation projects, such as climate change monitoring. N/A

OUTCOMES OF COMPLETED WORK. The outcomes reported in question 4E capture the results of your conservation activities. Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred. Outcomes related to individual and cumulative grant activities may be included.

4F. CONSERVATION OUTCOMES - In the space provided below, please share outcomes that have resulted from your conservation work, including grants, reported this year or unreported in previous years. Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome. N/A

5. Recreation Development Projects

Note: This category does not include recreational events, programs or marketing materials. Please include recreational events and marketing materials (such as brochures, maps, guides) under Category 7: Outreach and Marketing. If you did not engage in recreation development projects this year, please skip these metrics and move on to Category 6: Education & Interpretation Programs.

WORK in PROGRESS. The numbers reported under 5A – 5B below capture work that is advancing, but not yet completed.

RECREATION GRANTS AWARDED 5A.1 Number of recreation development grants disbursed this year: 2 5A.2 Total dollar amount disbursed this year $ 70,000

PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to enhance recreational amenities (e.g., feasibility studies, plans, engineering, permitting, etc.). The same project can be reported on over multiple years, until it is completed. 5B. Number of recreation projects begun or continued: 2

COMPLETED WORK. The numbers reported under 5C – 5E below capture completed work that the coordinating entity funded, led, or partnered-on with other parties.

NEW TRAILS COMPLETED - Number of new miles of on or off road trails developed 5C.1. On-road miles: 0 5C.2. Off-road miles: 0

TRAILS MAINTAINED - Number of miles of on or off-road trails maintained through monitoring, clean-up and maintenance projects construction 5D.1. On-road miles: 4 5D.2. Off-road miles: 43, Sanpete County and US Forest Service and Counties maintained off-road trails

OTHER RECREATION DEVELOPMENT PROJECTS 5E. Provide name and a short description of other trail or park enhancement projects, such as parking, signage, trail heads, lighting, etc. or trail designation projects. For trail designations please identify the mileage. Subrecipient; Project; Federal; Match; Description. Mt. Pleasant City; Heritage Trail Project - Mt. Pleasant to Spring City path project; $ 45,000.00; $ 2,272,000.00; This is Phase II of a major non-motorized trail project sponsored by Mt. Pleasant City and including Spring City and Sanpete County as partners. The trail is being developed in compliance with a feasibility study conducted by Sunrise Engineering. UDOT paid for the study. The trail will connect Mt. Pleasant City to Spring City (both communities are on the National Register of Historic Places).. Sanpete County; Sanpete Recreation Infrastructure Projects; $ 25,000.00; $ 107,977.00; Hiking & Biking Trails; OHV Routes/Recreational Roads; Trailheads; Trailside Restrooms, Recreation infrastructure, cultural survey; and Signage..

OUTCOMES OF COMPLETED WORK. The outcomes reported under question 5G capture the results of your recreation work. Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred. Outcomes related to individual and cumulative grant activities may be included.

5F. RECREATION OUTCOMES - In the space provided below, please share outcomes that have resulted from your recreation work, including grants, reported this year or unreported in previous years. Provide a short description with the project name, year project was completed, project partners and indicator and data source for outcome. Subrecipient; Project; Federal; Match; Description. Mt. Pleasant City; Heritage Trail Project - Mt. Pleasant to Spring City path project; $ 45,000.00; $ 2,272,000.00; This is Phase II of a major non-motorized trail project sponsored by Mt. Pleasant City and including Spring City and Sanpete County as partners. The trail is being developed in compliance with a feasibility study conducted by Sunrise Engineering. UDOT paid for the study. The trail will connect Mt. Pleasant City to Spring City (both communities are on the National Register of Historic Places).. Sanpete County; Sanpete Recreation Infrastructure Projects; $ 25,000.00; $ 107,977.00; Hiking & Biking Trails; OHV Routes/Recreational Roads; Trailheads; Trailside Restrooms, Recreation infrastructure, cultural survey; and Signage..

6. Education and Interpretation Programs

The goal of education and interpretation programs is to increase people’s understanding of heritage area sites and stories. Note: Do not include annual meetings, conference presentations, awards ceremonies, open houses, annual fundraisers, and events. These activities are reported under category 7: outreach and marketing. If you did not conduct interpretation work this year, please skip these metrics and move on to category 7: outreach and marketing.

WORK in PROGRESS. The numbers reported under 6A - 6B capture work that is advancing, but not yet ready to be offered to the public.

EDUCATION GRANTS AWARDED 6A.1 Number of education and interpretation related grants disbursed this year: 7 6A.2 Total dollar amount disbursed this year: $ 68,665.37

PROJECTS in DEVELOPMENT (Do Not Include Grant Projects Reported Above) - Number of education and interpretation projects in development (e.g., assessments, research, etc.). The same project can be reported on over multiple years, until it is offered or made available to the public. 6B. Number of education and interpretation projects in development: 0

OFFERED PROGRAMS AND PRODUCTS. The information reported under 6C – 6D below captures the work that the coordinating entity funded, led, or partnered with other parties to offer this year.

6C. PROGRAMS OFFERED - In the space below, provide name and a short description of the interpretive or educational programs supported by the NHA coordinating entity this year. Discovery Road TV Series in cooperation with Utah Education Network (UEN). Town Track and Sanpete Art and History Tour.

6D. PRODUCTS OFFERED - In the space below, provide name and a short description of the interpretive or educational products (print, web, or multi-media) supported by the NHA coordinating entity this year. We have completed 65 TV shows in total. This year seven were produced and distributed to TV stations and to schools through the Utah Education Network (UEN). DVDs of Discovery Road episodes MPNHA Books: Legends, Lore, and True Tales in Mormon Country, published by Arcadia Publishing / History Press. Available in Utah libraries and for purchase. MPNHA YouTube Channel: https://www.youtube.com/channel/UCwY8IF4uHOhMHopvi-DQkdQ MPNHA Website: MormonPioneerHeritage.org Blackhawk War: Cultures in Conflict educational DVD, distributed to schools and other entities as an educational tool.

OUTCOMES of PROGRAM AND PRODUCTS OFFERED. The outcomes reported under question 6E capture the results of your education work. Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred. Outcomes related to individual and cumulative grant activities may be included.

6E. EDUCATION OUTCOMES - In the space provided below, please share any outcomes that have resulted from heritage area educational work, including grants, reported this year or unreported in previous years. Provide a short description with the project name, year project was completed, project partners and indicator and data source for outcome. Subrecipient; Project; Federal; Match; Description. Ephraim City; Ephraim Pioneer Park Project; $9,870.00; $0.00; Ephraim Pioneer Park Peace Tree- Construct a bronze statue of Antonga Blackhawk and Canute Peterson in honor of their initiation of a Peace Parley at the Juniper Tree on the grounds of the Ephraim City Pioneer Park.. Kanab City; All-Women Town Council Monument Project; $28,500.00; $0.00; The Kanab City Heritage and Historic Preservation Board is seeking funding on behalf of Kanab City to create an interpretive monument honoring the historic all-women town board who served from 1912-1914. This town board was the first all-female town council in the state of Utah and one of the earliest all-female elected municipal governments in the country. The proposed project involves designing, engineering, constructing, and installing a permanent monument on Kanab City property. The monument will serve as an educational and cultural resource, providing insight into the significant role of women in the area’s development and the state of Utah. Funding support for this project will ensure the legacy of the Kanab all-women town board is remembered for future generations.. North Star Video; Discovery Road Project; $18,452.41; $18,452.41; This is an on-going TV series that runs on four TV stations and is embedded on mormonpioneerheritage.org. The show is produced in conjunction with public television station KUEN and the Utah Education Network. Also includes a follow up book to our very successful “Legends, Lore and True Tales in Mormon Country.” This book would continue themes from the previous book but would correlate with shows we have aired. We would coordinate with KUEN.. Discovery Road Project; $5,943.84; $6,056.16. Discovery Road Project; $1,592.75; $0.00. Discovery Road; $651.37; $0.00. Sanpete County; Restoration of the Daughters of Utah Pioneers Manti Camp Pioneer Monument Project; $3,655.00; $0.00; Restoration of the Daughters of Utah Pioneers Manti Camp Pioneer Monument, built in 1938, located in the Heritage Gardens, west of the Manti Temple. Restoration may include: Replace bases of the pilasters, replace the plinths, resurface stones and repoint the missing mortar, replace 2 Voussoirs on the left side of the arch, resurface the keystone and patch a top stone corner, replace the springer with the Manti limestone, replace the right spandrel on the west corner, and wash the entire monument to remove the trace of pollution and black moss..

7. Outreach and Marketing (include presentations, sponsorships, and other outreach activities here)

Note: Include economic impact studies under products offered. If you did not conduct outreach or marketing work this year, please skip these metrics and move on to Category 8: Community Engagement.

WORK in PROGRESS. The numbers reported under 7A – 7B capture work that is advancing, but not yet ready to be offered to the public.

OUTREACH & MARKETING GRANTS AWARDED 7A.1 Number of outreach and marketing grants disbursed this year 6 7A.2 Total dollar amount disbursed this year $ $50,385.63

PROJECTS in DEVELOPMENT (Do Not Include Grant Projects Reported Above) - Number of promotion and marketing projects in development (e.g., assessments, research, etc.). The same project can be reported on over multiple years, until it is offered or made available to the public. 7B. Number of promotion and marketing projects in development: 0

OFFERED EVENTS AND PRODUCTS. The numbers reported under 7C – 7D below capture work that the coordinating entity funded, led, or partnered with other parties to offer to the public this year.

7C. EVENTS OFFERED (RACES, CELEBRATIONS, AWARDS CEREMONIES, FAM TOURS, ETC.) - In the space below, provide name and a short description of promotional activities supported by the coordinating entity. We supported events in the five heritage districts of the Mormon Pioneer National Heritage Area. These districts are Little Denmark, Sevier Valley, Headwaters, Under the Rim and Boulder Loop. Each event has its focus in the pioneer and cultural heritage of the respective district in which it is held. 1- Western Legends Roundup 2- Scandinavian Days 3- Mormon Pioneer Heritage Festival 4- Spring City Heritage Days 5- Everett Reuss Festival 6- Jacob Hamblin Days 7- Butch Cassidy Days 8- Panguitch Quilt Walk 9- Map N Tour Project – This project promotes heritage and cultural tourism in multiple counties within the Heritage Area. This project will allow for integration of the MapNTour Web and Mobile App which will enhance user experience for both web and mobile platforms. It is a unique notification system that draws people to sites and has story telling capability and multi-media options. It centers on destination experiences and scalability to expand locations and content in phases.

7D. PRODUCTS OFFERED (BROCHURES, ECONOMIC IMPACT STUDIES, WEBSITES, ETC.) - In the space below, provide name and a short description of promotional products supported by the coordinating entity. MPNHA website: MormonPioneerHeritage.org MPNHA YouTube Channel: https://www.youtube.com/channel/UCwY8IF4uHOhMHopvi-DQkdQ We continue to print and distribute a travel planner, maintain an active website and distribute "Discovery Road" shows via internet and broadcast. See Mormonpioneerheritage.org for an overview. Map N Tour mobile tourism application.

OUTCOMES of EVENTS AND PRODUCTS OFFERED. The outcomes reported under question 7E capture the results of your promotion and marketing work. Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred. Outcomes related to individual and cumulative grant activities may be included.

7E. OUTREACH & MARKETING OUTCOMES - In the space provided below, please share outcomes that have resulted from heritage area marketing activities reported this year or offered in previous years. Outcomes could include increases in visitation to heritage area sites generated by marketing products. Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome. - Travel Planner - Western Legends Roundup - Scandinavian Days - Mormon Pioneer Heritage Festival - Spring City Heritage Days - Everett Reuss Festival - Jacob Hamblin Days - Butch Cassidy Days - Panguitch Quilt Walk - Map N Tour Project – This project promotes heritage and cultural tourism in multiple counties within the Heritage Area. This project will allow for integration of the MapNTour Web and Mobile App which will enhance user experience for both web and mobile platforms. It is a unique notification system that draws people to sites and has story telling capability and multi-media options. It centers on destination experiences and scalability to expand locations and content in phases.

8. Community Engagement

The numbers captured here reflect the work of the NHA coordinating entity and partnership. Please answer all questions below.

PARTNERSHIPS A partnership is a relationship between parties to accomplish a common goal, such as developing or implementing a heritage area project or offering heritage area programs. Partnerships are characterized by mutual interest, commitment, and communication. Please count partners one time, either as formal or informal partners. 8A.1 Formal Partners are the organizations who you directly collaborate with on heritage area projects and programs and who are substantially involved in those projects or programs. You may have an agreement in place to formalize your partnership with these organizations, but having an agreement is not a requirement for being a formal partner. Number of formal partners substantially engaged in National Heritage Area activities this year: 15 8A.2 Informal Partners are those organizations who you cooperate or coordinate with on projects and programs. These organizations are not substantially involved in your projects or programs. Number of informal partners engaged in National Heritage Area activities this year: 72

VOLUNTEERISM Volunteer Count. Please count volunteers who are working on projects or programs that are coordinated and/or funded by the national heritage area coordinating entity. Do not include volunteers at park units or other sites for which there was no investment of heritage area staff time or funding. 8B.1 Total number of volunteers engaged in heritage area projects, programs or activities 340 8B.2 Total number of volunteer hours 8500 (please round-up to the nearest hour) 8B.3 Hourly value of volunteer time for your state or region (refer to www.independentsector.org/volunteer_time for your region) $ 24.14 8B.4 Total dollar value of volunteer hours $ 205,190

PROGRAM & EVENT PARTICIPANTS Program and Event Participant Count. Please count participants who attended events or programs that were coordinated and/or funded by the national heritage area coordinating entity. Do not include participants in programs at parks or other sites where there was no investment of heritage area staff time or funding. 8C.1 Number of people who participated in heritage area educational programs this year: 23,000 8C.2 Number of people who participated in heritage area events (races, celebrations, ceremonies, etc.) this year: 33,000

OTHER ACTIVITIES 8D.1 In the space below, identify any other activities including community development, economic development or community engagement projects that do not fit into the seven categories above. N/A

Best Practice : Highlight a Successful Project or Program

In the space below, please describe a creative, successful project or program undertaken or completed this year. Please include images with captions and credit information. Also, include numbers if applicable – dollars invested and leveraged, communities or residents involved or impacted, properties preserved, miles of trails improved, etc. Word count recommendation is 200 words.

BEST PRACTICE Mt. Pleasant Community Development and Renewal Agency Mt. Pleasant Railroad Park Project Total Project Cost: $ 188,806 Federal Funding: $ 94,403 Matching Funds: $94,403 In the heart of Utah, the Mt. Pleasant Railroad Park Project stands as a testament to a bygone yet impactful era, when the advent and expansion of the Denver and Rio Grande Western Railroad marked a period of significant prosperity for Little Denmark, often referred to as the 'golden era.' The project breathes life into this legacy, with the railroad once heralded as the lifeblood of the communities it served, symbolizing connection and progress. "The railroad era started moving toward a close" (MPNHA Management Plan, 16), yet its monumental impact resonates through history. Mt. Pleasant, pivotal in the railroad network, now showcases this heritage. Investments of $184,806 revived key reminders and relics of railroad history, including a Heber Valley Railroad engine, historic caboose, and water Tower, alongside landscaping around the Train Depot. The park proudly features the statue of Chief Sanpitch, paying tribute to the region's deep-rooted cultural narratives. Strategic cooperation with private partners and public entities like the State of Utah, Utah Main Street Program, Main Street America, Sanpete County, and Mt. Pleasant CDRA amplify the project's success. "By reviving and enhancing the infrastructure that once supported these critical industries, communities like Mt. Pleasant not only preserve their history but also lay the groundwork for future prosperity" (MPNHA Management Plan, 35-37). The completed unique boxcar hotel and upcoming children's train promise to further enrich the community's historical engagement. The Mt. Pleasant Railroad Park Project stands as a celebration of history and progress, preserving the past while fostering a future of continued growth and community unity, ensuring the railroad's enduring legacy. Additional Best Practices In addition to the trails project highlighted above, other best practices included revitalizing and restoring historic main streets. These images of Mt. Pleasant Main Street are a highlight of these main street projects.

NOTICES

Privacy Act Statement

General:  This information is provided pursuant to Public Law 93-579 (Privacy Act of 1974), December 21, 1984, for individuals completing this form.

Authority:  54 USC Ch. 3201, Historic Sites Act of 1935, as amended; 44 U.S.C. 3501, et seq., Paperwork Reduction Act of 1995; and individual pieces of legislation and associated amendments in 54 USC 100702 that enable the NPS, on behalf of the Secretary of the Interior, to provide federal financial, technical, and other assistance for the preservation of natural, cultural, historic, and scenic resources.

Purposes and Uses:  The NPS intends to track the progress of each heritage area on implementing its management plan and meeting performance goals. The information collected is used by the NHA program office in monitoring the progress of each heritage area. The collection of this information is necessary to allow for national oversight, analysis, coordination, technical and financial assistance, and support to National Heritage Areas to ensure consistency and accountability across the country.

Effects of Nondisclosure:  Financial disclosure is in accordance with 54 USC Ch. 3201, Pub. L. 113–291, div. B, title XXX, §3052(a)(2), Dec. 19, 2014, 128 Stat. 3802.

Information Regarding Disclosure of Your Social Security Number Under Public Law 93-579 Section 7(b): Your Social Security Number is not needed to complete this form.

Paperwork Reduction Act Statement

We are collecting this information subject to the Paperwork Reduction Act (44 U.S.C. 3501) in response to the NHAs individual authorizing legislation requiring annual reporting as mandated by Congress. The information provided by NHA Coordinating Entities allows the NHA program office to allocate funding to heritage area management, prepare NPS budget justifications, and track management planning and implementation across NHAs. We may not conduct or sponsor and you are not required to respond to a collection of information unless it displays a currently valid OMB Control Number. OMB has reviewed and approved this survey and assigned OMB Control Number 1024-###, which expires ##/##/####.

Estimated Burden Statement

Public Reporting burden for this form is estimated to average 42 minutes per response, including the time it takes for reviewing instructions, gathering and maintaining data, and completing and reviewing the form. Comments regarding this burden estimate or any aspect of this form should be sent to the Information Collection Clearance Officer, National Park Service, 1201 Oakridge Drive, Fort Collins, CO 80525.

Disbursed is defined as funds that have left the heritage area’s account and gone to a grant recipient.