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Purpose 
The information collected through this form will be used by the National Park Service (NPS), National Heritage Areas (NHA) Program Office and regional program offices to track each heritage area management or coordinating entity’s (coordinating entity) progress on management plan implementation.  The progress measures outlined in the categories below capture information about the diverse heritage area activities and approaches to these activities (process measures), direct products or services offered (output measures), and the results of the products or services (outcome measures).  

The NPS will use the responses to the questions reported here in annual program reports and publications and to inform individual heritage area evaluations.  

Reporting Instructions 
The progress measures in this form are grouped under eight categories, capturing the diverse work of the coordinating entities throughout the country.  We recognize that each heritage area and coordinating entity is unique.  Therefore, not all of the categories or measures presented below will apply.   

· The data reported here shall reflect the work that the coordinating entity led, funded or partnered with others to complete this year.  

· Report all work that the coordinating entity was involved in to implement the National Heritage Area Management Plan.  Include work supported by Heritage Partnership Program (HPP) funding and other heritage area funding sources.  

· Report data for the same 12-month cycle (calendar, federal, and fiscal) that you reported last year.  
 
· Measures under categories 2 – 7 are sequenced to capture work in progress, work that is completed, and the outcomes of completed work.  
   
· Follow the specific instructions for each category and measure.  Please be consistent in how you categorize your work.  When deciding how to categorize a specific project or program, it may be helpful to consider the project or program purpose in relation to your NHA goals. 

· If you are implementing or funding multicomponent projects, please count each component separately.  For example, you might be working on a project that involves the preservation of a building or site, site interpretation, and an event.  Using this example, each component would be counted as a separate project under the preservation, education and interpretation, and promotion categories.  If it is not possible to separate project components, please report on the project under the category that is most appropriate given the funding amount.      

· Retain all supporting documentation used in filling out this form in your office files until a program evaluation has been completed for your heritage area.  Per 2CFR Part 215.53, the NPS, as well as the Inspector General or Comptroller General, reserve the right to review supporting documents.  The NPS NHA Program Office reviews these forms and may contact you periodically to insure consistent and accurate reporting.  



Form Submittal 
Identify the name of the heritage area you represent at the top of this page.  The complete form includes your NHA name, goals, responses to applicable categories and metrics, and a scanned copy of page 2 with your name, signature, and date verifying the accuracy of the information provided.  

Email this form to the NHA Program Office at nha@nps.gov and copy your regional coordinator and agreements technical representative by close-of-business on the date listed at the top of this form.  

Assurance Statement
As the authorized representative of the local coordinating entity, I certify that the progress indicators reported below are supported by documentation that is verifiable in our records.  

	Name: Monte Bona

	[image: A picture containing invertebrate, arthropod, smoke, hydrozoan

Description automatically generated]Signature: 

	Date: 24 January 2024



Heritage Area Goals
In the space below please identify the heritage area goals that appear in your management plan or management plan update. 

Please identify your reporting cycle here by name (Federal fiscal, state, calendar, etc.): Click here to enter text. 
	1.  Financial Assistance and Capacity Building

	The numbers captured here reflect the work of the coordinating entity only.  Leverage metrics are intended to capture the economic contribution of NHAs.     

	LEVERAGE
Leverage is using what you already have, in this case HPP funding, to bring about more support than would be possible otherwise.  Include all sources that you secured this past fiscal year that you would not have had unless HPP funds were available. Other federal funds (not including HPP funds) may be included.     
1A.1 Total amount of funding leveraged, including other Federal funds, to implement heritage area activities this year $ 2,833,537.44
1A.2 Provide a breakdown of leveraged funds, include cash and in-kind donations in totals. 
State $ 1,968,462
Local Government $ 865,075.44
Private $ 0
Other Federal Funding (not HPP, but include other NPS funding) 
(Specify funding source): N/A $ N/A
Other (please specify): N/A $ N/A 
· Mat

	GRANTS
Grants are the transfer of money from a national heritage area coordinating entity to a recipient whose project proposal is selected through a review process.  Grants are awarded to recipients to accomplish the goals of the national heritage area.  Grants do not include sponsorships, contracts, or donations. 
1B.1 Total number of grants disbursed[footnoteRef:2] this year 26 [2:  Disbursed is defined as funds that have left the heritage area’s account and gone to a grant recipient. 
] 

1B.2 Total grant dollars disbursed this year $ 500,000
Please provide a breakdown of the grant funds distributed this year under the categories (2 - 7) below.

	
CAPACITY BUILDING
Capacity building assistance includes guidance related to historic preservation, education, heritage tourism, natural resource conservation, etc., or the organizational capacity of a partner organization.  Capacity building assistance does not include oversight related to administration of sub grants, phone calls directing the individuals to resources or informational meetings, etc.  
Count the number of organizations, not people.  For example, if one person represents two organizations, the number of organizations is two. 
1C.1 Number of organizations to which you provided capacity building assistance through trainings, workshops, onsite assessments, etc.  0
1C.2 Number of capacity building grants awarded this year 0
1C.3 Total dollar amount awarded $ 0
1C.4 In the space provided below, share any outcomes that have resulted from your capacity building assistance this year or in previous years.  Provide a short description with the project name, year project was completed, and indicator and data source for outcome.  

N/A


	2.  Historic Preservation & Other Community Enhancement Projects 

	If you did not engage in historic preservation or community enhancement work this year, please skip these metrics and move on to Category 3: Collections.

	WORK in PROGRESS.  The numbers reported under 2A – 2B below capture work that is advancing, but not yet completed.

	HISTORIC PRESERVATION GRANTS DISBURSED 
2A.1 Number of historic or cultural resource preservation grants disbursed this year 9
2A.2 Total dollar amount disbursed $ 264,229

	PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to enhance listed or eligible National Register properties (e.g., condition assessments, plans, research, etc.).  The same project can be reported on over multiple years, until it is completed.  
2B. Number of historic preservation projects begun or continued: 6

	COMPLETED WORK.  The numbers and information reported under 2C – 2F below captures completed work that the coordinating entity funded, led, or partnered-on with other parties.    

	2C. NOMINATIONS COMPLETED - Number of historic or cultural resources nominated to the National Register of Historic Places 0

	SITES PRESERVED - Historic sites (i.e. those listed or eligible for listing on the National Register of Historic Places) preserved through restoration, rehabilitation or adaptive reuse, and reconstruction 
2D.1 Number of sites preserved 9 (for a grouping of buildings indicate 1 district/number of contributing buildings)
2D.2 Total acreage of preserved landscapes, such as battlefields, etc. 0 

	SITES MAINTAINED – Historic properties (i.e. listed or eligible for listing on the National Register of Historic Places) maintained through monitoring and small-scale maintenance projects.  Note: If you own or manage historic building(s) or site(s) this is where you can capture your on-going maintenance efforts. 
2E.1 Number of sites maintained 19 (for a grouping of buildings indicate 1 district/number of contributing buildings)
2E.2 Total acreage of preserved landscapes, such as battlefields, etc. 0

	2F. OTHER COMMUNITY ENHANCEMENT PROJECTS COMPLETED – In the space provided, provide name and a short description of streetscape or façade improvement projects, as well as other projects that are intended to enhance communities (e.g., art projects or business development projects).  
	Subrecipient
	Project
	Federal
	Match
	Description

	Casino Star Theatre
	 Casino Star Theatre Project 
	 $                      45,000.00 
	 $                    105,626.00 
	The budget for the restroom renovation of the historic theatre has changed since the FY22 grant was awarded. The current attached budget includes the expansion of restroom capacity and provides ADA access for patrons during large events, concerts, and major movie nights.


	Kanab City
	 Kanab Museum Project 
	 $                      20,000.00 
	 $                      26,601.88 
	The purpose of this project is to help complete a renovation of the Kanab Museum. The Kanab Museum, located in a historic Public Library building, is currently undergoing a renovation project aimed at enhancing the preservation of its valuable collections. The project, which began in 2019, involved major interior renovations and the assessment and replacement of damaged museum cases. Despite significant progress being made by September 2021, the restoration was temporarily stopped due to difficulties in repairing the historical wood floors. However, with the help of a capital project grant awarded in November 2022, the project has resumed, and the primary focus is on completing the floor repairs and securing funding for new museum cases. The new cases will be instrumental in ensuring the preservation of the museum’s collections by providing adequate protection from environmental factors, such as dust, humidity, and light, while also enhancing their presentation.


	Moroni
	 Moroni Opera House Project 
	 $                        6,866.00 
	 $                        6,442.77 
	Historic Moroni Opera House- replace HVAC and add large security boulders out front to prevent vehicles that miss the turn from colliding with the historic building.

	Mt. Pleasant City Community Development and Renewal Agency
	 Mt. Pleasant CDRA Railroad Park Project 
	 $                      27,510.00 
	 $                                    -   
	Pages 35-37 of the Management Plan outline the important role railroads played in the area’s heritage. The historic Denver Rio-Grande Depot in Mt. Pleasant is highlighted as Figure 47 on page 36 of the Plan.
This project is being developed as a public/private partnership to emphasize our railroad heritage and thereby promote heritage tourism and recreation.
Supporting Railroad equipment, signals, and railroad theme enhancement materials.

	Mt. Pleasant City Community Development and Renewal Agency
	 Mt. Pleasant Railroad Park Project 
	 $                      67,403.00 
	 $                      93,893.00 
	

	Redmond Town
	 Redmond Town Hall Project 
	 $                      15,000.00 
	 $                      15,000.00 
	The city will hire a contractor to make some substantial repairs and restoration work on the 1881/1890s structure. This will include the following: reroofing the original 1881 section, including repairing/replacing rafters as necessary and replacing the roof deck; making repairs to some sections of the walls on the 1881 section; repair, prep and repaint exterior woodwork on both sections, including the wood windows; install simple, non-obtrusive store windows to help protect the original windows and reduce energy costs; weatherize the bell tower so it doesn't leak; and replace the rain gutters and downspouts to direct rainwater and snowmelt away from the building. Section 106 consultation has been completed for this project and received SHPO approval.


	
	 Redmond Town Hall Rehab Project 
	 $                      22,000.00 
	 $                      22,000.00 
	

	Salina City
	 Salina CCC/POW Camp Rehab Project 
	 $                      10,450.00 
	 $                      10,450.00 
	The city will hire a contractor to re-roof some of the four structures and install new siding material on several walls where the material has failed or is in poor condition. The rolled roofing with wood battens that was installed a decade or so ago has not weathered well, so this time 30-year architectural-grade asphalt shingles will be installed. Likewise, the tar-paper sheathing and wood batterns that were installed on some of the walls has not weathered well over the past decade, so Hardie Board siding (painted black to resemble tar paper) with battens will be used as the replacement material. This was used on some of the walls a decade or so ago and it has held up extremely well and conveys a very historically accurate look. While this complex is historically important, it is not eligible for National Register listing due to substantial new construction and other significant modifications to the camp layout.


	Spring City
	 1916 Spring City Junior High Project 
	 $                      50,000.00 
	 $                      97,347.98 
	1916 Spring City Junior High School building thorough rehabilitation, including repairs and stabilization.  The restrooms are not ADA compliant; the building has some subsidence in the southwest corner which is causing exterior brick deterioration, it has some foundation and soffit and fascia issues which cause leaking during high water levels due to weather, etc. Replace the windows with high-quality, energy efficient windows that would restore the facade to its original appearance.

This is a multi-phase project that will be developed over a three-year period. The budget for the total project is $350,000.

The first phase is budgeted for $100,000 to repair exterior brick that has deteriorated, stabilize the foundation, correct soffit, and fascia issues.





	OUTCOMES OF COMPLETED WORK.  The outcomes reported under question 2G captures the results of your historic preservation and community development activities.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	2G. HISTORIC PRESERVATION & COMMUNITY ENHANCEMENT OUTCOMES - In the space provided below, please share outcomes that have resulted from your historic preservation work, including grant work, reported this year or in previous years.  Provide a short description that includes the project name, year project was completed, project partners, and indicator and data source for outcome. 
	#
	Project Title
	Recipients and partners
	Other entities
	Federal Funds
	Matching Funds
	Total Project
	Completion Date
	Status
	Notes

	1
	Restoration of Historic Presbyterian Church - Manti
	 Manti City
	 Veterans Groups
	
	
	$9,600.00
	 11-10-2013
	 Completed
	

	2
	Casino Star Theater Restoration
	 Casino Star Theater Foundation
	 State of Utah, Utah Division of State History
	
	
	$31,000.00
	
	Completed
	

	3
	Restoration of historic Mt. Carmel Church
	 Kane County
	 State of Utah
	
	
	$20,000.00
	 09-30-2013
	 Completed
	

	4
	Wayne County-Teasdale Daughters of Utah Pioneers Museum
	 Teasdale Town
	 Wayne County
	
	
	$13,000.00
	 09-30-2013
	 Completed
	

	5
	Centerfield Historic Social Hall
	 Centerfield Town
	
	
	
	$10,000.00
	 09-30-2012
	 Completed
	

	6
	Historic Panguitch City Grandstand
	 Panguitch
	 Garfield County
	
	
	$10,000.00
	 09-30-2018
	 Completed
	

	7
	Historic Presbyterian Building
	 Sanpete County Economic Development
	 American Legion
	
	
	$9,600.00
	 11-15-2013
	 Completed
	

	8
	Fountain Green Social Hall and Theater
	 Fountain Green City
	
	
	
	$14,000.00
	 09-30-2012
	 Completed
	

	9
	Wayne County Cemetery Restoration Project
	 Wayne County Commission
	
	
	
	$12,600.00
	 09-30-2012
	 Completed
	

	10
	Snow College Alpine Station
	 Snow College
	
	
	
	$16,500.00
	 09-30-2012
	 Completed
	

	11
	Spring City School
	 Spring City Historic Preservation Commission,  Save America's Treasures, numerous other donors 
	 George S. and Dolores Dore' Eccles Foundation
	
	
	$25,000.00
	 09-30-2017
	 Completed
	

	12
	Manti Main Street historic building restoration
	 Manti City
	 Sanpete County Economic Development
	
	
	$7,000.00
	 09-30-2012
	 Completed
	

	13
	Manti historic City Hall
	 Manti City
	 Sanpete County Economic Development
	
	
	$14,450.00
	 09-30-2012
	 Completed
	

	19
	Ephraim Co-op historic building
	 Ephraim City
	 Sanpete County Economic Development
	 
	
	$6,650.00
	 09-30-2012
	 Completed
	 

	20
	Manti Daughters of Utah Pioneers Museum
	 Manti City
	
	 
	
	$1,900.00
	 09-30-2012
	 Completed
	 

	21
	Manti Carnegie Library restoration
	 Manti City
	 George S. and Delores Dore' Eccles Foundation
	 
	
	$25,000.00
	 09-30-2011
	 Completed
	 

	22
	Fairview Social Hall
	 Fairview City
	 Community Impact Board, numerous other donors
	 
	
	$25,000.00
	 09-30-2011
	 Completed
	 

	23
	Ephraim Carnegie Library restoration
	 Ephraim City
	 George S. and Delores Dore' Eccles Foundation
	 
	
	$20,000.00
	 09-30-2010
	 Completed
	 

	24
	Mt. Pleasant Carnegie Library restoration
	 George S. and Delores Dore' Eccles Foundation
	 US Department of Agriculture Rural Development grant, Utah Division of State History
	 
	
	 
	 09-30-2011
	 Completed
	 

	25
	Mt. Pleasant Armory
	 Mt. Pleasant Main Street Program
	 Preserve America grant, Utah Division of State History
	 
	
	 
	 09-30-2011
	 Completed
	 

	26
	Lizzie and Charlie's Rag Rug Factory
	 Monroe Preservation Society
	
	 
	
	$25,000.00
	 09-30-2012
	 Completed
	 

	27
	Marysvale Town Old Rock School House
	 Marysvale City
	
	 
	
	$4,800.00
	 11-01-2014
	 Completed
	 Used as a heritage crafts store

	28
	Carol Theater
	 Monroe
	 Scenic Canyons Preservation Society
	 
	
	$15,000.00
	 11-01-2014
	 Completed
	 Restoration of historic theater by non-profit entity, 

	29
	Orson Hyde Office/Allred School
	 Spring City
	 Allred Family
	 
	
	$9,000.00
	 11-01-2014
	 Completed
	 Used as an art studio

	30
	Old General Store
	 Spring City
	
	 
	
	$5,000.00
	 11-01-2014
	 Completed
	 Award-winning project on historic Main Street,  Used in conjunction with Victory Hall where live radio performances are conducted

	31
	Wasatch Academy Music Conservatory
	 Wasatch Academy
	
	
	
	
	 12-01-2014
	 Completed
	 A major project in Mt. Pleasant Historic District

	32
	Gunnison Legacy Wall and Clarion Interpretive Signs
	 Gunnison City
	 American Jewish Preservation Society
	
	
	$30,000.00
	 09-30-2015
	 Completed
	 

	33
	Gem Theater
	 Panguitch City Main Street Program
	 Scenic Canyons Preservation Society
	
	
	$55,000.00
	 09-30-2015
	 Completed
	 

	34
	Heritage Rag Museum
	 Marysvale and Piute County
	
	 
	
	$11,475.00
	 09-30-2015
	 Completed
	 

	35
	Kanab Heritage Center
	 Kanab City
	
	 
	
	$60,000.00
	 03-31-2016
	 Completed
	 as set forth in Task Agreement

	36
	Wayne County Visitors Center
	 Wayne County
	
	 
	
	$30,000.00
	 03-31-2016
	 Completed
	 

	37
	Mt. Pleasant Equestrian Center
	 Mt. Pleasant City
	
	 
	
	$125,000.00
	 09-30-2015
	 Completed
	 

	38
	Wasatch Academy Pierce Hall
	 Wasatch Academy
	
	 
	
	$305,000.00
	 03-31-2016
	 Completed
	 

	39
	Casino Star Theater Restoration
	 Casino Star Theater Foundation
	
	 
	
	$137,625.00
	 03-31-2016
	 Completed
	 

	40
	Panguitch Main Street Project
	 Panguitch Main Street Project
	
	 
	
	$26,465.00
	 09-30-2015
	 Completed
	 

	41
	Salina CCC/POW Restoration
	 Salina City
	
	 
	
	$103,000.00
	 03-31-2016
	 Completed
	 

	42
	Miss Mary's Museum Restoration
	 Salina City
	
	 
	
	$20,000.00
	 09-30-2015
	 Completed
	 

	43
	Ephraim City Granary Project
	 Ephraim City
	
	 
	
	$11,300.00
	 03-31-2016
	 Completed
	 

	44
	Restoration/Renovation of Wasatch Academy Historic Administration Building
	 Wasatch Academy
	
	 
	
	$26,182.00
	 09-30-2016
	 Completed
	 Projects completed in September 2016

	45
	Restoration work on Mt. Pleasant City Hall and Armory Building
	 Mt. Pleasant City
	 Utah Division of State History
	 
	
	$51,500.00
	 09-30-2016
	 Completed
	 

	46
	Hanksville Community Hall Restoration
	 Hanksville Town
	
	 
	
	$322,000.00
	 03-31-2017
	 Completed
	 

	47
	Bicknell Theater and Community Center
	 Bicknell Town
	
	 
	
	$65,000.00
	 09-30-2016
	 Completed
	 This is in addition to 20000 budgeted in FY2015

	48
	Spring City School Restoration/Renovation Phase III
	 George S. and Delores Dore' Eccles Foundation
	 Spring City Historic Preservation Commission
	 
	
	$575,000.00
	 09-20-2017
	 Completed
	 

	49
	Save America's Treasures and numerous other donors
	 Garfield and Piute Counties
	 State of Utah, Utah Division of State History
	
	
	$219,141.00
	 03-31-2017
	 Completed
	 Butch Cassidy Cabin Restoration

	50
	CCC/Pow Camp Building/Site Restoration
	 Salina City
	 Utah Division of State History, non-profits and private donors
	
	
	$50,000.00
	 09-30-2017
	 Completed
	 This is the second phase of a project

	51
	Spring City Victory Hall Restoration
	 Spring City
	 Utah Division of State History
	
	
	$7,000.00
	 09-30-2017
	 Completed
	 

	52
	Monroe Carol Theater Restoration
	 Carol Theater Restoration Committee
	
	$18,475.00
	$190,000.00
	$208,475.00
	 09-30-2017
	 Completed
	 

	53
	Jacob Hamblin Heritage Park
	 Kanab City
	 Kane County, State of Utah
	
	
	$190,000.00
	 03-31-2018
	 Completed
	 

	54
	Wayne County DIP Project
	 Wayne County
	
	
	
	$36,000.00
	 09-30-2017
	 Completed
	 

	55
	Bicknell People's Mere Restoration
	 People's Mere Restoration Partner
	
	
	
	$24,000.00
	 09-30-2017
	 Completed
	 

	56
	Spring City Historic School Restoration
	 Friends of Spring City
	 State of Utah, George S. and Dolores Dare's Eccles Foundation
	
	
	$459,843.00
	 05-31-2017
	 Completed
	 This is the final phase of the restoration project

	57
	Denver Rio Grande 1890's Depot Restoration
	 Mt. Pleasant City
	 Scenic Canyons Preservation Society
	
	
	$50,000.00
	 09-30-2017
	 Completed
	 

	58
	Mt. View DUP Historic Building Restoration
	 Mt. View Daughters of Utah Pioneers
	
	
	
	$8,000.00
	 09-30-2017
	 Completed
	 

	59
	Miss Mary's Historic School/Museum Restoration
	 Salina City
	 Miss Mary's Museum Committee
	
	
	$22,618.00
	 09-30-2017
	 Completed
	 This is the second phase of this project

	60
	Kanab Carnegie Library
	 Kane County
	 Kanab City
	
	
	$37,000.00
	 03-31-2019
	 Scheduled
	 

	61
	Fremont School Bell
	 Fremont chapter of the Daughters of Utah Pioneers
	
	
	
	$10,000.00
	 03-31-2019
	 Scheduled
	 

	62
	Historic Presbyterian Church Building
	 local American Legion
	
	
	
	$9,000.00
	 09-30-2018
	 Completed
	 

	63
	Wayne County DUP records project
	 
	
	
	
	$8,000.00
	 03-31-2019
	 Scheduled
	 

	64
	Marysvale Historic Outdoor Dance Hall Restoration
	 Marysvale Town
	
	
	
	$140,000.00
	 03-31-2019
	 Scheduled
	 

	65
	Garfield County Historic Fairgrounds Grandstand restoration
	 Garfield County
	
	
	
	$10,000.00
	 09-30-2018
	 Completed
	 

	66
	Wayne County DUP Historic Records Building Restoration
	 
	
	
	
	$8,000.00
	 03-31-2019
	 Scheduled
	 

	67
	Sanpete County Fairgrounds project
	 Sanpete County
	
	
	
	$160,000.00
	 09-30-2018
	 Completed
	 

	68
	Casino Star Theater restoration
	 Casino Star Theater Foundation
	 George S. and Dolores Dore' Eccles Foundation
	
	
	$92,000.00
	 03-31-2019
	 Scheduled
	 

	69
	Wasatch Academy Craighead vocational building restoration
	 Wasatch Academy
	 George S. and Dolores Dore' Eccles Foundation
	
	
	$180,000.00
	 03-31-2019
	 Scheduled
	 

	70
	Historic Denver Rio Grande Project
	 Mt. Pleasant City CDRA
	
	
	
	$13,000.00
	 09-30-2018
	 Completed
	 

	71
	Sanpete County CLG historic Homes Restoration project
	 Sanpete County Certified Local Government
	 building owners
	
	
	$26,000.00
	 09-30-2018
	 Completed
	 

	72
	Wayne County Teasdale Restoration Project
	
	
	$20,000.00
	$105,000.00
	$125,000.00
	 08-01-2020
	 Scheduled
	 

	73
	Garfield County Historic Fairgrounds Restoration Project
	
	
	$20,000.00
	$58,900.00
	$78,900.00
	$2,019.00
	 Completed
	 

	74
	Casino Star Theatre “Take a Seat” Project
	
	
	$20,000.00
	$85,564.00
	$105,564.00
	$2,019.00
	 Completed
	 

	75
	Bishop’s Storehouse project
	
	
	$30,000.00
	$38,000.00
	$68,000.00
	 08-01-2020
	 Scheduled
	 

	76
	Historic Manti City Hall
	
	
	$1,500.00
	$1,500.00
	$3,000.00
	$2,019.00
	 Completed
	 

	77
	Wayne County Heritage Park project
	
	
	$18,000.00
	$22,000.00
	$40,000.00
	$2,019.00
	 Completed
	 

	78
	The Scout House project
	
	
	$25,000.00
	$35,000.00
	$60,000.00
	 08-01-2020
	 Scheduled
	 

	79
	Moroni Veterans’ Memorial
	
	
	$5,000.00
	$62,000.00
	$67,000.00
	$2,019.00
	 Completed
	 

	80
	Mt. Pleasant Depot project
	
	
	$10,000.00
	$11,500.00
	$21,500.00
	$2,019.00
	 Completed
	 

	81
	Mining Museum project
	
	
	$20,000.00
	$20,000.00
	$40,000.00
	 08-01-2020
	 Scheduled
	 

	82
	Wayne County Fairgrounds Project
	
	
	$20,000.00
	$180,000.00
	$200,000.00
	$2,019.00
	 Completed
	 

	83
	Monroe City Hot Springs Park Project
	
	
	$25,000.00
	$34,418.00
	$59,418.00
	$2,020.00
	 Completed
	 

	84
	Miss Mary’s Museum Project
	
	
	$10,000.00
	$12,678.82
	$22,678.82
	$2,020.00
	 Completed
	 

	85
	Historic Spring City Firehouse
	
	
	$4,439.00
	$4,438.00
	$8,877.00
	
	 Completed
	 

	86
	Mt. Pleasant Relic House Project
	
	
	$5,000.00
	$7,370.00
	$12,370.00
	
	 Completed
	 

	87
	Ephraim City DUP Pioneer Park and DUP Museum Project
	
	
	$25,000.00
	$31,427.50
	$56,427.50
	
	 Completed
	 

	88
	Track 89 Boxcar Restoration and Train Depot project
	
	
	$10,000.00
	$1,453.65
	$11,453.65
	
	 Completed
	 

	89
	Boxcar Motel Visitor Experience Project
	
	
	$10,000.00
	$125,108.79
	$135,108.79
	 Summer 2021
	 Completed
	 

	90
	Mt. Pleasant and Fairview Historic Preservation Projects
	
	
	$1,671.49
	$0.00
	$1,671.49
	 In Progress
	 
	 Federal

	91
	Mt. Pleasant Relic House project
	
	
	$5,000.00
	$18,351.00
	$23,351.00
	 August 2021
	 Completed
	 

	92
	Sindi’s Salon project
	
	
	$3,000.00
	$3,000.00
	$6,000.00
	 September 2021
	 Completed
	 

	93
	Spring City Inn project
	
	
	$8,000.00
	$16,585.17
	$24,585.17
	 July 2021
	 Completed
	 

	94
	Moroni Opera House project
	
	
	$13,500.00
	$13,500.00
	$27,000.00
	 March 2021
	 Completed
	 

	95
	Denver Rio-Grande Depot and Boxcar Motel Project
	Subrecipient: Mt. Pleasant City
	
	$10,000.00
	$95,000.00
	$105,000.00
	 Summer 2021
	 Completed
	 

	96
	Patton House Project
	Subrecipient: Manti City
	
	$3,750.00
	$3,750.00
	$7,500.00
	 
	 
	 

	97
	Salina CCC/POW Camp Project
	Subrecipient: Salina City
	
	$6,400.00
	$6,400.00
	$12,800.00
	 
	 
	 

	98
	Casino-Star Theater Project
	Subrecipient: Sanpete County
	
	$15,000.00
	$95,000.00
	$110,000.00
	 
	 
	 

	99
	Pioneer Cemetery Project
	Subrecipient: Sanpete County
	
	$6,000.00
	$6,000.00
	$12,000.00
	 
	 
	 

	100
	Mt. Pleasant Pioneer Historical Association Relic House Museum project
	Subrecipient: Sanpete County
	
	$10,000.00
	$10,000.00
	$20,000.00
	 
	 
	 

	101
	Sanpete County Courthouse project
	Subrecipient: Sanpete County
	
	$20,000.00
	$30,000.00
	$50,000.00
	 
	 
	 

	102
	Marysvale Mercantile Restoration
	Subrecipient: Piute County
	
	$37,500.00
	$37,500.00
	$75,000.00
	 
	 
	 

	103
	Historic Maynard Dixon Home project
	Subrecipient: Kane County
	
	$25,000.00
	$25,900.00
	$50,900.00
	 
	 
	 

	104
	Casino Star Theatre Project 
	Casino Star Theatre
	
	$45,000.00
	$105,626.00
	$150,626.00
	 
	 
	 

	105
	Kanab Museum Project
	Kanab City
	
	$20,000.00
	$26,601.88
	$46,601.88
	 
	 
	 

	106
	Moroni Opera House project
	Moroni City
	
	$6,866.00
	$6,442.77
	$13,308.77
	 
	 
	 

	107
	Mt. Pleasant CDRA Railroad Park Project
	Mt. Pleasant CDRA
	
	$27,510.00
	$27,510.00
	$55,020.00
	 
	 
	 

	108
	Mt. Pleasant Railroad Park Project
	Mt. Pleasant CDRA
	
	$67,893.00
	$67,893.00
	$135,786.00
	 
	 
	 

	109
	Redmond Town Hall Project
	Redmond
	
	$15,000.00
	$15,000.00
	$30,000.00
	 
	 
	 

	110
	Redmond Town Hall Rehab Project
	Redmond
	
	$22,000.00
	$22,000.00
	$44,000.00
	 
	 
	 

	111
	Salina CCC/POW Camp Rehab Project
	Salina
	
	$10,450.00
	$10,450.00
	$20,900.00
	 
	 
	 

	112
	1916 Spring City Junior High Project
	Spring City
	
	$50,000.00
	$97,347.98
	$147,347.98
	 
	 
	 




	3.  Collections: Documentation and Conservation Projects
Paintings, Artifacts, Archives, Oral Histories, Video Histories, etc.

	Report here the work in which the primary purpose is to document cultural traditions or conserve artifacts.  If you are working on projects that use collections to develop interpretive or educational materials, please report these projects under Category 6: Education and Interpretation Programs.  

If you did not engage in work to develop or conserve cultural collections this year, please skip these metrics and move on to the Category 4: Land, Water and Environmental Conservation Projects. 

	WORK in PROGRESS.  The numbers reported under 3A – 3B capture work that is advancing, but not yet completed.

	GRANTS FOR COLLECTIONS DISBURSED
3A.1 Number of collections-related grants disbursed this year 0
3A.2 Total dollar amount disbursed this year $ 0 

	PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) – Number of projects begun or continued to conserve heritage area artifacts (e.g., condition assessments, plans, research, etc.).  The same project can be reported on over multiple years, until it is completed.  
3B. Number of collections projects begun or continued: 0

	COMPLETED WORK.  The information reported under 3C below captures completed work that the coordinating entity funded, led, or partnered-on with other parties.    

	3C. COLLECTION PROJECTS – Provide the name and a brief description of the collections created, documented, or conserved.  Collections include oral histories, paintings, murals, historic documents, textiles, archaeology collections or material culture, such as boats or ships.  

	OUTCOMES OF COMPLETED WORK.  The outcomes reported under question 3D capture the results of your the collections conservation activities.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	3D. COLLECTIONS OUTCOMES - In the space provided below, please share outcomes that have resulted from your collections related work, including grants, reported this year or unreported in previous years.  Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome.  
N/A


	4.  Land, Water & Environmental Conservation Projects

	Note: Include wetland work under land restoration, instead of waterway restoration.   
If you did not engage in natural resource conservation work this year, please skip these metrics and move on to category 5: recreation development projects.  

	WORK in PROGRESS.  The numbers reported under 4A – 4B below capture work that is advancing, but not yet completed.

	LAND AND WATER CONSERVATION GRANTS AWARDED
4A.1. Number of natural resource conservation grants disbursed this year 0
4A.2 Total dollar amount disbursed this year $0

	PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to conserve natural or scenic areas (i.e., surveys, condition assessments, plans, etc.). The same project can be reported on over multiple years, until it is completed.  
4B. Number of conservation projects begun or continued: 0

	COMPLETED WORK.  The numbers reported under 4C – 4D below capture completed work that the coordinating entity funded, led, or partnered-on with other parties.    

	LAND RESTORATION
4C.1. Number of acres of land restored through invasive species removal, replanting, and toxic site clean-up. (one time) 0
4C.2. Number of acres of land maintained through monitoring and clean-up efforts 0

	WATERWAY RESTORATION (Streams, rivers, creeks, canals, etc.)
4D.1. Number of feet of waterways restored through appropriate in-water and bank restoration techniques (one time) 0
4D.2. Number of miles of waterways maintained through monitoring and clean-up efforts (please round to the ¼ mile) 0

	OTHER ENVIRONMENTAL CONSERVATION PROJECTS
4E. Provide name and a short description of other environmental conservation projects, such as climate change monitoring.  
N/A

	OUTCOMES OF COMPLETED WORK.  The outcomes reported in question 4E capture the results of your conservation activities.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	4F. CONSERVATION OUTCOMES - In the space provided below, please share outcomes that have resulted from your conservation work, including grants, reported this year or unreported in previous years.  Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome. 
N/A

	5.  Recreation Development Projects

	Note: This category does not include recreational events, programs or marketing materials.  Please include recreational events and marketing materials (such as brochures, maps, guides) under Category 7: Outreach and Marketing.   
If you did not engage in recreation development projects this year, please skip these metrics and move on to Category 6: Education & Interpretation Programs.   

	WORK in PROGRESS.  The numbers reported under 5A – 5B below capture work that is advancing, but not yet completed.

	RECREATION GRANTS AWARDED
5A.1 Number of recreation development grants disbursed this year: 2
5A.2 Total dollar amount disbursed this year $ 70,000

	PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to enhance recreational amenities (e.g., feasibility studies, plans, engineering, permitting, etc.).  The same project can be reported on over multiple years, until it is completed.  
5B. Number of recreation projects begun or continued: 2

	COMPLETED WORK.  The numbers reported under 5C – 5E below capture completed work that the coordinating entity funded, led, or partnered-on with other parties.    

	NEW TRAILS COMPLETED - Number of new miles of on or off road trails developed 
5C.1. On-road miles: 0
5C.2. Off-road miles: 0

	TRAILS MAINTAINED - Number of miles of on or off-road trails maintained through monitoring, clean-up and maintenance projects construction
5D.1. On-road miles: 4
5D.2. Off-road miles: 43, Sanpete County and US Forest Service and Counties maintained off-road trails

	OTHER RECREATION DEVELOPMENT PROJECTS 
5E. Provide name and a short description of other trail or park enhancement projects, such as parking, signage, trail heads, lighting, etc. or trail designation projects.  For trail designations please identify the mileage. 
	Subrecipient
	Project
	Federal
	Match
	Description

	Mt. Pleasant City
	 Heritage Trail Project - Mt. Pleasant to Spring City path project 
	 $                      45,000.00 
	 $                 2,272,000.00 
	This is Phase II of a major non-motorized trail project sponsored by Mt. Pleasant City and including Spring City and Sanpete County as partners. The trail is being developed in compliance with a feasibility study conducted by Sunrise Engineering. UDOT paid for the study. The trail will connect Mt. Pleasant City to Spring City (both communities are on the National Register of Historic Places).

	Sanpete County
	 Sanpete Recreation Infrastructure Projects  
	 $                      25,000.00 
	 $                    107,977.00 
	Hiking & Biking Trails; OHV Routes/Recreational Roads; Trailheads; Trailside Restrooms, Recreation infrastructure, cultural survey; and Signage.




	OUTCOMES OF COMPLETED WORK.  The outcomes reported under question 5G capture the results of your recreation work.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	5F. RECREATION OUTCOMES - In the space provided below, please share outcomes that have resulted from your recreation work, including grants, reported this year or unreported in previous years.  Provide a short description with the project name, year project was completed, project partners and indicator and data source for outcome. 
	Subrecipient
	Project
	Federal
	Match
	Description

	Mt. Pleasant City
	 Heritage Trail Project - Mt. Pleasant to Spring City path project 
	 $                      45,000.00 
	 $                 2,272,000.00 
	This is Phase II of a major non-motorized trail project sponsored by Mt. Pleasant City and including Spring City and Sanpete County as partners. The trail is being developed in compliance with a feasibility study conducted by Sunrise Engineering. UDOT paid for the study. The trail will connect Mt. Pleasant City to Spring City (both communities are on the National Register of Historic Places).

	Sanpete County
	 Sanpete Recreation Infrastructure Projects  
	 $                      25,000.00 
	 $                    107,977.00 
	Hiking & Biking Trails; OHV Routes/Recreational Roads; Trailheads; Trailside Restrooms, Recreation infrastructure, cultural survey; and Signage.





	6. Education and Interpretation Programs 

	The goal of education and interpretation programs is to increase people’s understanding of heritage area sites and stories.    
Note: Do not include annual meetings, conference presentations, awards ceremonies, open houses, annual fundraisers, and events.  These activities are reported under category 7: outreach and marketing.   
If you did not conduct interpretation work this year, please skip these metrics and move on to category 7: outreach and marketing.


	WORK in PROGRESS.  The numbers reported under 6A - 6B capture work that is advancing, but not yet ready to be offered to the public.

	EDUCATION GRANTS AWARDED
6A.1 Number of education and interpretation related grants disbursed this year: 7
6A.2 Total dollar amount disbursed this year:  $ 68,665.37 

	PROJECTS in DEVELOPMENT (Do Not Include Grant Projects Reported Above) - Number of education and interpretation projects in development (e.g., assessments, research, etc.).  The same project can be reported on over multiple years, until it is offered or made available to the public.  
6B. Number of education and interpretation projects in development: 0

	OFFERED PROGRAMS AND PRODUCTS.  The information reported under 6C – 6D below captures the work that the coordinating entity funded, led, or partnered with other parties to offer this year.  

	6C. PROGRAMS OFFERED - In the space below, provide name and a short description of the interpretive or educational programs supported by the NHA coordinating entity this year.  
Discovery Road TV Series in cooperation with Utah Education Network (UEN).
Town Track and Sanpete Art and History Tour.

	6D. PRODUCTS OFFERED - In the space below, provide name and a short description of the interpretive or educational products (print, web, or multi-media) supported by the NHA coordinating entity this year. 
We have completed 65 TV shows in total. This year seven were produced and distributed to TV stations and to schools through the Utah Education Network (UEN).
DVDs of Discovery Road episodes
MPNHA Books: Legends, Lore, and True Tales in Mormon Country, published by Arcadia Publishing / History Press. Available in Utah libraries and for purchase.
MPNHA YouTube Channel: https://www.youtube.com/channel/UCwY8IF4uHOhMHopvi-DQkdQ
MPNHA Website: MormonPioneerHeritage.org
Blackhawk War: Cultures in Conflict educational DVD, distributed to schools and other entities as an educational tool.

	OUTCOMES of PROGRAM AND PRODUCTS OFFERED.  The outcomes reported under question 6E capture the results of your education work.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	6E. EDUCATION OUTCOMES - In the space provided below, please share any outcomes that have resulted from heritage area educational work, including grants, reported this year or unreported in previous years.  Provide a short description with the project name, year project was completed, project partners and indicator and data source for outcome.  
	Subrecipient
	Project
	Federal
	Match
	Description

	Ephraim City
	Ephraim Pioneer Park Project
	$9,870.00
	$0.00
	Ephraim Pioneer Park Peace Tree- Construct a bronze statue of Antonga Blackhawk and Canute Peterson in honor of their initiation of a Peace Parley at the Juniper Tree on the grounds of the Ephraim City Pioneer Park.

	Kanab City
	All-Women Town Council Monument Project
	$28,500.00
	$0.00
	The Kanab City Heritage and Historic Preservation Board is seeking funding on behalf of Kanab City to create an interpretive monument honoring the historic all-women town board who served from 1912-1914. This town board was the first all-female town council in the state of Utah and one of the earliest all-female elected municipal governments in the country. The proposed project involves designing, engineering, constructing, and installing a permanent monument on Kanab City property. The monument will serve as an educational and cultural resource, providing insight into the significant role of women in the area’s development and the state of Utah. Funding support for this project will ensure the legacy of the Kanab all-women town board is remembered for future generations.

	North Star Video
	Discovery Road Project
	$18,452.41
	$18,452.41
	This is an on-going TV series that runs on four TV stations and is embedded on mormonpioneerheritage.org. The show is produced in conjunction with public television station KUEN and the Utah Education Network. Also includes a follow up book to our very successful “Legends, Lore and True Tales in Mormon Country.” This book would continue themes from the previous book but would correlate with shows we have aired. We would coordinate with KUEN.

	
	Discovery Road Project
	$5,943.84
	$6,056.16
	

	
	Discovery Road Project
	$1,592.75
	$0.00
	

	
	Discovery Road
	$651.37
	$0.00
	

	Sanpete County
	Restoration of the Daughters of Utah Pioneers Manti Camp Pioneer Monument Project
	$3,655.00
	$0.00
	Restoration of the Daughters of Utah Pioneers Manti Camp Pioneer Monument, built in 1938, located in the Heritage Gardens, west of the Manti Temple. Restoration may include:  Replace bases of the pilasters, replace the plinths, resurface stones and repoint the missing mortar, replace 2 Voussoirs on the left side of the arch, resurface the keystone and patch a top stone corner, replace the springer with the Manti limestone, replace the right spandrel on the west corner, and wash the entire monument to remove the trace of pollution and black moss.





	7.  Outreach and Marketing (include presentations, sponsorships, and other outreach activities here)

	Note: Include economic impact studies under products offered.   
If you did not conduct outreach or marketing work this year, please skip these metrics and move on to Category 8: Community Engagement.  

	WORK in PROGRESS.  The numbers reported under 7A – 7B capture work that is advancing, but not yet ready to be offered to the public.

	OUTREACH & MARKETING GRANTS AWARDED
7A.1 Number of outreach and marketing grants disbursed this year 6
7A.2 Total dollar amount disbursed this year $ $50,385.63  

	PROJECTS in DEVELOPMENT (Do Not Include Grant Projects Reported Above) - Number of promotion and marketing projects in development (e.g., assessments, research, etc.).  The same project can be reported on over multiple years, until it is offered or made available to the public.  
7B. Number of promotion and marketing projects in development: 0

	OFFERED EVENTS AND PRODUCTS.  The numbers reported under 7C – 7D below capture work that the coordinating entity funded, led, or partnered with other parties to offer to the public this year.  

	7C. EVENTS OFFERED (RACES, CELEBRATIONS, AWARDS CEREMONIES, FAM TOURS, ETC.) - In the space below, provide name and a short description of promotional activities supported by the coordinating entity. 
We supported events in the five heritage districts of the Mormon Pioneer National Heritage Area. These districts are Little Denmark, Sevier Valley, Headwaters, Under the Rim and Boulder Loop. Each event has its focus in the pioneer and cultural heritage of the respective district in which it is held.
1- Western Legends Roundup
2- Scandinavian Days
3- Mormon Pioneer Heritage Festival
4- Spring City Heritage Days
5- Everett Reuss Festival
6- Jacob Hamblin Days
7- Butch Cassidy Days 
8- Panguitch Quilt Walk
9- Map N Tour Project – This project promotes heritage and cultural tourism in multiple counties within the Heritage Area. This project will allow for integration of the MapNTour Web and Mobile App which will enhance user experience for both web and mobile platforms. It is a unique notification system that draws people to sites and has story telling capability and multi-media options. It centers on destination experiences and scalability to expand locations and content in phases.

	7D. PRODUCTS OFFERED (BROCHURES, ECONOMIC IMPACT STUDIES, WEBSITES, ETC.) - In the space below, provide name and a short description of promotional products supported by the coordinating entity.  
MPNHA website: MormonPioneerHeritage.org
MPNHA YouTube Channel: https://www.youtube.com/channel/UCwY8IF4uHOhMHopvi-DQkdQ
We continue to print and distribute a travel planner, maintain an active website and distribute "Discovery Road" shows via internet and broadcast. See Mormonpioneerheritage.org for an overview.
Map N Tour mobile tourism application.

	OUTCOMES of EVENTS AND PRODUCTS OFFERED.  The outcomes reported under question 7E capture the results of your promotion and marketing work.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	7E. OUTREACH & MARKETING OUTCOMES - In the space provided below, please share outcomes that have resulted from heritage area marketing activities reported this year or offered in previous years.  Outcomes could include increases in visitation to heritage area sites generated by marketing products.  Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome.  
· Travel Planner
· Western Legends Roundup
· Scandinavian Days
· Mormon Pioneer Heritage Festival
· Spring City Heritage Days
· Everett Reuss Festival
· Jacob Hamblin Days
· Butch Cassidy Days 
· Panguitch Quilt Walk
· Map N Tour Project – This project promotes heritage and cultural tourism in multiple counties within the Heritage Area. This project will allow for integration of the MapNTour Web and Mobile App which will enhance user experience for both web and mobile platforms. It is a unique notification system that draws people to sites and has story telling capability and multi-media options. It centers on destination experiences and scalability to expand locations and content in phases.

	8.  Community Engagement

	The numbers captured here reflect the work of the NHA coordinating entity and partnership.  Please answer all questions below.      

	PARTNERSHIPS   
A partnership is a relationship between parties to accomplish a common goal, such as developing or implementing a heritage area project or offering heritage area programs.  Partnerships are characterized by mutual interest, commitment, and communication.  Please count partners one time, either as formal or informal partners. 
8A.1 Formal Partners are the organizations who you directly collaborate with on heritage area projects and programs and who are substantially involved in those projects or programs.  You may have an agreement in place to formalize your partnership with these organizations, but having an agreement is not a requirement for being a formal partner.  
Number of formal partners substantially engaged in National Heritage Area activities this year: 15

8A.2 Informal Partners are those organizations who you cooperate or coordinate with on projects and programs.  These organizations are not substantially involved in your projects or programs. 
Number of informal partners engaged in National Heritage Area activities this year: 72

	VOLUNTEERISM
Volunteer Count. Please count volunteers who are working on projects or programs that are coordinated and/or funded by the national heritage area coordinating entity.  Do not include volunteers at park units or other sites for which there was no investment of heritage area staff time or funding. 
8B.1 Total number of volunteers engaged in heritage area projects, programs or activities 340
8B.2 Total number of volunteer hours 8500 (please round-up to the nearest hour)
8B.3 Hourly value of volunteer time for your state or region (refer to www.independentsector.org/volunteer_time for your region) $ 24.14 
8B.4 Total dollar value of volunteer hours $ 205,190

	PROGRAM & EVENT PARTICIPANTS 
Program and Event Participant Count.  Please count participants who attended events or programs that were coordinated and/or funded by the national heritage area coordinating entity.  Do not include participants in programs at parks or other sites where there was no investment of heritage area staff time or funding. 
8C.1 Number of people who participated in heritage area educational programs this year: 23,000
8C.2 Number of people who participated in heritage area events (races, celebrations, ceremonies, etc.) this year: 33,000


	OTHER ACTIVITIES  
8D.1 In the space below, identify any other activities including community development, economic development or community engagement projects that do not fit into the seven categories above.  
N/A




















	Best Practice : Highlight a Successful Project or Program

	In the space below, please describe a creative, successful project or program undertaken or completed this year.  Please include images with captions and credit information.  
Also, include numbers if applicable – dollars invested and leveraged, communities or residents involved or impacted, properties preserved, miles of trails improved, etc.  Word count recommendation is 200 words.

	[image: ][image: ]
BEST PRACTICE
Mt. Pleasant Community Development and Renewal Agency

Mt. Pleasant Railroad Park Project

Total Project Cost:  $ 188,806    Federal Funding:  $ 94,403      Matching Funds:  $94,403

[image: ]In the heart of Utah, the Mt. Pleasant Railroad Park Project stands as a testament to a bygone yet impactful era, when the advent and expansion of the Denver and Rio Grande Western Railroad marked a period of significant prosperity for Little Denmark, often referred to as the 'golden era.'

The project breathes life into this legacy, with the railroad once heralded as the lifeblood of the communities it served, symbolizing connection and progress. "The railroad era started moving toward a [image: ]close" (MPNHA Management Plan, 16), yet its monumental impact resonates through history. Mt. Pleasant, pivotal in the railroad network, now showcases this heritage. Investments of $184,806 revived key reminders and relics of railroad history, including a Heber Valley Railroad engine, historic [image: ]caboose, and water Tower, alongside landscaping around the Train Depot. The park proudly features the statue of Chief Sanpitch, paying tribute to the region's deep-rooted cultural narratives.

[image: ][image: ]Strategic cooperation with private partners and public entities like the State of Utah, Utah Main Street Program, Main Street America, Sanpete County, and Mt. Pleasant CDRA amplify the project's success. "By reviving and enhancing the infrastructure that once supported these critical industries, communities like Mt. Pleasant not only preserve their history but also lay the groundwork for future prosperity" (MPNHA Management Plan, 35-37). The completed unique boxcar hotel and upcoming children's train promise to further enrich the community's historical engagement.

The Mt. Pleasant Railroad Park Project stands as a celebration of history and progress, preserving the past while fostering a future of continued growth and community unity, ensuring the railroad's enduring legacy.



Additional Best Practices

In addition to the trails project highlighted above, other best practices included revitalizing and restoring historic main streets.

[image: ][image: ]These images of Mt. Pleasant Main Street are a highlight of these main street projects.




NOTICES


PRIVACY ACT STATEMENT

General:  This information is provided pursuant to Public Law 93-579 (Privacy Act of 1974), December 21, 1984, for individuals completing this form.

Authority:  54 USC Ch. 3201, Historic Sites Act of 1935, as amended; 44 U.S.C. 3501, et seq., Paperwork Reduction Act of 1995; and individual pieces of legislation and associated amendments in 54 USC 100702 that enable the NPS, on behalf of the Secretary of the Interior, to provide federal financial, technical, and other assistance for the preservation of natural, cultural, historic, and scenic resources.

Purposes and Uses:  The NPS intends to track the progress of each heritage area on implementing its management plan and meeting performance goals. The information collected is used by the NHA program office in monitoring the progress of each heritage area. The collection of this information is necessary to allow for national oversight, analysis, coordination, technical and financial assistance, and support to National Heritage Areas to ensure consistency and accountability across the country.

Effects of Nondisclosure:  Financial disclosure is in accordance with 54 USC Ch. 3201, Pub. L. 113–291, div. B, title XXX, §3052(a)(2), Dec. 19, 2014, 128 Stat. 3802.

Information Regarding Disclosure of Your Social Security Number Under Public Law 93-579 Section 7(b): Your Social Security Number is not needed to complete this form.  


PAPERWORK REDUCTION ACT STATEMENT

We are collecting this information subject to the Paperwork Reduction Act (44 U.S.C. 3501) in response to the NHAs individual authorizing legislation requiring annual reporting as mandated by Congress. The information provided by NHA Coordinating Entities allows the NHA program office to allocate funding to heritage area management, prepare NPS budget justifications, and track management planning and implementation across NHAs. We may not conduct or sponsor and you are not required to respond to a collection of information unless it displays a currently valid OMB Control Number. OMB has reviewed and approved this survey and assigned OMB Control Number 1024-###, which expires ##/##/####.

ESTIMATED BURDEN STATEMENT

Public Reporting burden for this form is estimated to average 42 minutes per response, including the time it takes for reviewing instructions, gathering and maintaining data, and completing and reviewing the form. Comments regarding this burden estimate or any aspect of this form should be sent to the Information Collection Clearance Officer, National Park Service, 1201 Oakridge Drive, Fort Collins, CO 80525. 
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