| Heritage Area Name: Mormon Pioneer National Hertiage Area |  | Deadline: Jan. 29, 2026 |  |
| --- | --- | --- | --- |

Purpose

The information collected through this form will be used by the National Park Service (NPS), National Heritage Areas (NHA) Program Office and regional program offices to track each heritage area management or coordinating entity’s (coordinating entity) progress on management plan implementation.  The progress measures outlined in the categories below capture information about the diverse heritage area activities and approaches to these activities (process measures), direct products or services offered (output measures), and the results of the products or services (outcome measures).

The NPS will use the responses to the questions reported here in annual program reports and publications and to inform individual heritage area evaluations.

#### Reporting Instructions

The progress measures in this form are grouped under eight categories, capturing the diverse work of the coordinating entities throughout the country.  We recognize that each heritage area and coordinating entity is unique.  Therefore, not all of the categories or measures presented below will apply.

- The data reported here shall reflect the work that the coordinating entity led, funded or partnered with others to complete this year.

- Report all work that the coordinating entity was involved in to implement the National Heritage Area Management Plan.  Include work supported by Heritage Partnership Program (HPP) funding and other heritage area funding sources.

- Report data for the same 12-month cycle (calendar, federal, and fiscal) that you reported last year.

- Measures under categories 2 – 7 are sequenced to capture work in progress, work that is completed, and the outcomes of completed work.

- Follow the specific instructions for each category and measure.  Please be consistent in how you categorize your work.  When deciding how to categorize a specific project or program, it may be helpful to consider the project or program purpose in relation to your NHA goals.

- If you are implementing or funding multicomponent projects, please count each component separately.  For example, you might be working on a project that involves the preservation of a building or site, site interpretation, and an event.  Using this example, each component would be counted as a separate project under the preservation, education and interpretation, and promotion categories.  If it is not possible to separate project components, please report on the project under the category that is most appropriate given the funding amount.

- Retain all supporting documentation used in filling out this form in your office files until a program evaluation has been completed for your heritage area.  Per 2CFR Part 215.53, the NPS, as well as the Inspector General or Comptroller General, reserve the right to review supporting documents.  The NPS NHA Program Office reviews these forms and may contact you periodically to insure consistent and accurate reporting.

Form Submittal

Identify the name of the heritage area you represent at the top of this page.  The complete form includes your NHA name, goals, responses to applicable categories and metrics, and your name, signature, and date verifying the accuracy of the information provided.

Sign and scan in or save as PDF and sign electronically. Email this form to the NHA Program Office at NHA@nps.gov and copy your regional coordinator and agreements technical representative by close-of-business on the date listed at the top of this form.

#### Assurance Statement

As the authorized representative of the local coordinating entity, I certify that the progress indicators reported below are supported by documentation that is verifiable in our records.

Name: Monte Bona

Signature:

Date: 9 January 2026

Heritage Area Goals

In the space below please identify the heritage area goals that appear in your management plan or management plan update.

Please identify your reporting cycle here by name (Federal fiscal, state, calendar, etc.): Click here to enter text.

1. Financial Assistance and Capacity Building

The numbers captured here reflect the work of the coordinating entity only. Leverage metrics are intended to capture the economic contribution of NHAs.

LEVERAGE Leverage is using what you already have, in this case HPP funding, to bring about more support than would be possible otherwise. Include all sources that you secured this past fiscal year that you would not have had unless HPP funds were available. Other federal funds (not including HPP funds) may be included. 1A.1 Total amount of funding leveraged, including other Federal funds, to implement heritage area activities this year $ 2,653,888.81 1A.2 Provide a breakdown of leveraged funds, include cash and in-kind donations in totals. State $ 2,237,853.00 Local Government $ 290,089.21 Private $ 125,946.60 Other Federal Funding (not HPP, but include other NPS funding) (Specify funding source): Click here to enter text. $ 0 Other (please specify): Click here to enter text. $ 0 - Mat

GRANTS Grants are the transfer of money from a national heritage area coordinating entity to a recipient whose project proposal is selected through a review process. Grants are awarded to recipients to accomplish the goals of the national heritage area. Grants do not include sponsorships, contracts, or donations. 1B.1 Total number of grants disbursed this year 31 1B.2 Total grant dollars disbursed this year $ 500,000 Please provide a breakdown of the grant funds distributed this year under the categories (2 - 7) below.

CAPACITY BUILDING Capacity building assistance includes guidance related to historic preservation, education, heritage tourism, natural resource conservation, etc., or the organizational capacity of a partner organization. Capacity building assistance does not include oversight related to administration of sub grants, phone calls directing the individuals to resources or informational meetings, etc. Count the number of organizations, not people. For example, if one person represents two organizations, the number of organizations is two. 1C.1 Number of organizations to which you provided capacity building assistance through trainings, workshops, onsite assessments, etc. 0 1C.2 Number of capacity building grants awarded this year 0 1C.3 Total dollar amount awarded $ 0 1C.4 In the space provided below, share any outcomes that have resulted from your capacity building assistance this year or in previous years. Provide a short description with the project name, year project was completed, and indicator and data source for outcome. N/A

2. Historic Preservation & Other Community Enhancement Projects

If you did not engage in historic preservation or community enhancement work this year, please skip these metrics and move on to Category 3: Collections.

WORK in PROGRESS. The numbers reported under 2A – 2B below capture work that is advancing, but not yet completed.

HISTORIC PRESERVATION GRANTS DISBURSED 2A.1 Number of historic or cultural resource preservation grants disbursed this year 5 2A.2 Total dollar amount disbursed $ 72,939.00

PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to enhance listed or eligible National Register properties (e.g., condition assessments, plans, research, etc.). The same project can be reported on over multiple years, until it is completed. 2B. Number of historic preservation projects begun or continued: 5

COMPLETED WORK. The numbers and information reported under 2C – 2F below captures completed work that the coordinating entity funded, led, or partnered-on with other parties.

2C. NOMINATIONS COMPLETED - Number of historic or cultural resources nominated to the National Register of Historic Places 0

SITES PRESERVED - Historic sites (i.e. those listed or eligible for listing on the National Register of Historic Places) preserved through restoration, rehabilitation or adaptive reuse, and reconstruction 2D.1 Number of sites preserved 9 (for a grouping of buildings indicate 1 district/number of contributing buildings) 2D.2 Total acreage of preserved landscapes, such as battlefields, etc. 0

SITES MAINTAINED – Historic properties (i.e. listed or eligible for listing on the National Register of Historic Places) maintained through monitoring and small-scale maintenance projects. Note: If you own or manage historic building(s) or site(s) this is where you can capture your on-going maintenance efforts. 2E.1 Number of sites maintained 19 (for a grouping of buildings indicate 1 district/number of contributing buildings) 2E.2 Total acreage of preserved landscapes, such as battlefields, etc. 0

2F. OTHER COMMUNITY ENHANCEMENT PROJECTS COMPLETED – In the space provided, provide name and a short description of streetscape or façade improvement projects, as well as other projects that are intended to enhance communities (e.g., art projects or business development projects). Mt. Pleasant Main Street Program; Mt. Pleasant Main Street Program Fund; $95,000.00; $83,003.20; $178,003.20. Mt. Pleasant CDRA; Mt. Pleasant City Historic Hall Restoration; $13,000.00; $13,000.00. Mt. Pleasant Main Street Program; Mt Pleasant Main Street Historic Preservation and Restoration Fund; $38,750.00; $38,750.00; $77,500.00. Mt. Pleasant CDRA; Train Depot Infrastructure Project; $9,189.00; $9,000.00; $18,189.00.

OUTCOMES OF COMPLETED WORK. The outcomes reported under question 2G captures the results of your historic preservation and community development activities. Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred. Outcomes related to individual and cumulative grant activities may be included.

2G. HISTORIC PRESERVATION & COMMUNITY ENHANCEMENT OUTCOMES - In the space provided below, please share outcomes that have resulted from your historic preservation work, including grant work, reported this year or in previous years. Provide a short description that includes the project name, year project was completed, project partners, and indicator and data source for outcome. #; Project Title; Recipients and partners; Other entities; Federal Funds; Matching Funds; Total Project. 1; Restoration of Historic Presbyterian Church - Manti; Manti City; Veterans Groups; $9,600.00. 2; Casino Star Theater Restoration; Casino Star Theater Foundation; State of Utah, Utah Division of State History; $31,000.00. 3; Restoration of historic Mt. Carmel Church; Kane County; State of Utah; $20,000.00. 4; Wayne County-Teasdale Daughters of Utah Pioneers Museum; Teasdale Town; Wayne County; $13,000.00. 5; Centerfield Historic Social Hall; Centerfield Town; $10,000.00. 6; Historic Panguitch City Grandstand; Panguitch; Garfield County; $10,000.00. 7; Historic Presbyterian Building; Sanpete County Economic Development; American Legion; $9,600.00. 8; Fountain Green Social Hall and Theater; Fountain Green City; $14,000.00. 9; Wayne County Cemetery Restoration Project; Wayne County Commission; $12,600.00. 10; Snow College Alpine Station; Snow College; $16,500.00. 11; Spring City School; Spring City Historic Preservation Commission, Save America's Treasures, numerous other donors; George S. and Dolores Dore' Eccles Foundation; $25,000.00. 12; Manti Main Street historic building restoration; Manti City; Sanpete County Economic Development; $7,000.00. 13; Manti historic City Hall; Manti City; Sanpete County Economic Development; $14,450.00. 19; Ephraim Co-op historic building; Ephraim City; Sanpete County Economic Development; $6,650.00. 20; Manti Daughters of Utah Pioneers Museum; Manti City; $1,900.00. 21; Manti Carnegie Library restoration; Manti City; George S. and Delores Dore' Eccles Foundation; $25,000.00. 22; Fairview Social Hall; Fairview City; Community Impact Board, numerous other donors; $25,000.00. 23; Ephraim Carnegie Library restoration; Ephraim City; George S. and Delores Dore' Eccles Foundation; $20,000.00. 24; Mt. Pleasant Carnegie Library restoration; George S. and Delores Dore' Eccles Foundation; US Department of Agriculture Rural Development grant, Utah Division of State History. 25; Mt. Pleasant Armory; Mt. Pleasant Main Street Program; Preserve America grant, Utah Division of State History. 26; Lizzie and Charlie's Rag Rug Factory; Monroe Preservation Society; $25,000.00. 27; Marysvale Town Old Rock School House; Marysvale City; $4,800.00. 28; Carol Theater; Monroe; Scenic Canyons Preservation Society; $15,000.00. 29; Orson Hyde Office/Allred School; Spring City; Allred Family; $9,000.00. 30; Old General Store; Spring City; $5,000.00. 31; Wasatch Academy Music Conservatory; Wasatch Academy. 32; Gunnison Legacy Wall and Clarion Interpretive Signs; Gunnison City; American Jewish Preservation Society; $30,000.00. 33; Gem Theater; Panguitch City Main Street Program; Scenic Canyons Preservation Society; $55,000.00. 34; Heritage Rag Museum; Marysvale and Piute County; $11,475.00. 35; Kanab Heritage Center; Kanab City; $60,000.00. 36; Wayne County Visitors Center; Wayne County; $30,000.00. 37; Mt. Pleasant Equestrian Center; Mt. Pleasant City; $125,000.00. 38; Wasatch Academy Pierce Hall; Wasatch Academy; $305,000.00. 39; Casino Star Theater Restoration; Casino Star Theater Foundation; $137,625.00. 40; Panguitch Main Street Project; Panguitch Main Street Project; $26,465.00. 41; Salina CCC/POW Restoration; Salina City; $103,000.00. 42; Miss Mary's Museum Restoration; Salina City; $20,000.00. 43; Ephraim City Granary Project; Ephraim City; $11,300.00. 44; Restoration/Renovation of Wasatch Academy Historic Administration Building; Wasatch Academy; $26,182.00. 45; Restoration work on Mt. Pleasant City Hall and Armory Building; Mt. Pleasant City; Utah Division of State History; $51,500.00. 46; Hanksville Community Hall Restoration; Hanksville Town; $322,000.00. 47; Bicknell Theater and Community Center; Bicknell Town; $65,000.00. 48; Spring City School Restoration/Renovation Phase III; George S. and Delores Dore' Eccles Foundation; Spring City Historic Preservation Commission; $575,000.00. 49; Save America's Treasures and numerous other donors; Garfield and Piute Counties; State of Utah, Utah Division of State History; $219,141.00. 50; CCC/Pow Camp Building/Site Restoration; Salina City; Utah Division of State History, non-profits and private donors; $50,000.00. 51; Spring City Victory Hall Restoration; Spring City; Utah Division of State History; $7,000.00. 52; Monroe Carol Theater Restoration; Carol Theater Restoration Committee; $18,475.00; $190,000.00; $208,475.00. 53; Jacob Hamblin Heritage Park; Kanab City; Kane County, State of Utah; $190,000.00. 54; Wayne County DIP Project; Wayne County; $36,000.00. 55; Bicknell People's Mere Restoration; People's Mere Restoration Partner; $24,000.00. 56; Spring City Historic School Restoration; Friends of Spring City; State of Utah, George S. and Dolores Dare's Eccles Foundation; $459,843.00. 57; Denver Rio Grande 1890's Depot Restoration; Mt. Pleasant City; Scenic Canyons Preservation Society; $50,000.00. 58; Mt. View DUP Historic Building Restoration; Mt. View Daughters of Utah Pioneers; $8,000.00. 59; Miss Mary's Historic School/Museum Restoration; Salina City; Miss Mary's Museum Committee; $22,618.00. 60; Kanab Carnegie Library; Kane County; Kanab City; $37,000.00. 61; Fremont School Bell; Fremont chapter of the Daughters of Utah Pioneers; $10,000.00. 62; Historic Presbyterian Church Building; local American Legion; $9,000.00. 63; Wayne County DUP records project; $8,000.00. 64; Marysvale Historic Outdoor Dance Hall Restoration; Marysvale Town; $140,000.00. 65; Garfield County Historic Fairgrounds Grandstand restoration; Garfield County; $10,000.00. 66; Wayne County DUP Historic Records Building Restoration; $8,000.00. 67; Sanpete County Fairgrounds project; Sanpete County; $160,000.00. 68; Casino Star Theater restoration; Casino Star Theater Foundation; George S. and Dolores Dore' Eccles Foundation; $92,000.00. 69; Wasatch Academy Craighead vocational building restoration; Wasatch Academy; George S. and Dolores Dore' Eccles Foundation; $180,000.00. 70; Historic Denver Rio Grande Project; Mt. Pleasant City CDRA; $13,000.00. 71; Sanpete County CLG historic Homes Restoration project; Sanpete County Certified Local Government; building owners; $26,000.00. 72; Wayne County Teasdale Restoration Project; $20,000.00; $105,000.00; $125,000.00. 73; Garfield County Historic Fairgrounds Restoration Project; $20,000.00; $58,900.00; $78,900.00. 74; Casino Star Theatre “Take a Seat” Project; $20,000.00; $85,564.00; $105,564.00. 75; Bishop’s Storehouse project; $30,000.00; $38,000.00; $68,000.00. 76; Historic Manti City Hall; $1,500.00; $1,500.00; $3,000.00. 77; Wayne County Heritage Park project; $18,000.00; $22,000.00; $40,000.00. 78; The Scout House project; $25,000.00; $35,000.00; $60,000.00. 79; Moroni Veterans’ Memorial; $5,000.00; $62,000.00; $67,000.00. 80; Mt. Pleasant Depot project; $10,000.00; $11,500.00; $21,500.00. 81; Mining Museum project; $20,000.00; $20,000.00; $40,000.00. 82; Wayne County Fairgrounds Project; $20,000.00; $180,000.00; $200,000.00. 83; Monroe City Hot Springs Park Project; $25,000.00; $34,418.00; $59,418.00. 84; Miss Mary’s Museum Project; $10,000.00; $12,678.82; $22,678.82. 85; Historic Spring City Firehouse; $4,439.00; $4,438.00; $8,877.00. 86; Mt. Pleasant Relic House Project; $5,000.00; $7,370.00; $12,370.00. 87; Ephraim City DUP Pioneer Park and DUP Museum Project; $25,000.00; $31,427.50; $56,427.50. 88; Track 89 Boxcar Restoration and Train Depot project; $10,000.00; $1,453.65; $11,453.65. 89; Boxcar Motel Visitor Experience Project; $10,000.00; $125,108.79; $135,108.79. 90; Mt. Pleasant and Fairview Historic Preservation Projects; $1,671.49; $0.00; $1,671.49. 91; Mt. Pleasant Relic House project; $5,000.00; $18,351.00; $23,351.00. 92; Sindi’s Salon project; $3,000.00; $3,000.00; $6,000.00. 93; Spring City Inn project; $8,000.00; $16,585.17; $24,585.17. 94; Moroni Opera House project; $13,500.00; $13,500.00; $27,000.00. 95; Denver Rio-Grande Depot and Boxcar Motel Project; Subrecipient: Mt. Pleasant City; $10,000.00; $95,000.00; $105,000.00. 96; Patton House Project; Subrecipient: Manti City; $3,750.00; $3,750.00; $7,500.00. 97; Salina CCC/POW Camp Project; Subrecipient: Salina City; $6,400.00; $6,400.00; $12,800.00. 98; Casino-Star Theater Project; Subrecipient: Sanpete County; $15,000.00; $95,000.00; $110,000.00. 99; Pioneer Cemetery Project; Subrecipient: Sanpete County; $6,000.00; $6,000.00; $12,000.00. 100; Mt. Pleasant Pioneer Historical Association Relic House Museum project; Subrecipient: Sanpete County; $10,000.00; $10,000.00; $20,000.00. 101; Sanpete County Courthouse project; Subrecipient: Sanpete County; $20,000.00; $30,000.00; $50,000.00. 102; Marysvale Mercantile Restoration; Subrecipient: Piute County; $37,500.00; $37,500.00; $75,000.00. 103; Historic Maynard Dixon Home project; Subrecipient: Kane County; $25,000.00; $25,900.00; $50,900.00. 104; Casino Star Theatre Project; Casino Star Theatre; $45,000.00; $105,626.00; $150,626.00. 105; Kanab Museum Project; Kanab City; $20,000.00; $26,601.88; $46,601.88. 106; Moroni Opera House project; Moroni City; $6,866.00; $6,442.77; $13,308.77. 107; Mt. Pleasant CDRA Railroad Park Project; Mt. Pleasant CDRA; $27,510.00; $27,510.00; $55,020.00. 108; Mt. Pleasant Railroad Park Project; Mt. Pleasant CDRA; $67,893.00; $67,893.00; $135,786.00. 109; Redmond Town Hall Project; Redmond; $15,000.00; $15,000.00; $30,000.00. 110; Redmond Town Hall Rehab Project; Redmond; $22,000.00; $22,000.00; $44,000.00. 111; Salina CCC/POW Camp Rehab Project; Salina; $10,450.00; $10,450.00; $20,900.00. 112; 1916 Spring City Junior High Project; Spring City; $50,000.00; $97,347.98; $147,347.98. 113; Monroe School Restoration Project; Monroe City; $60,000.00; $93,905.21; $153,905.21. 114; Fountain Green DUP Upgrades Project; Fountain Green DUP; $9,200.00; $59,631.45; $68,831.45. 115; Moroni Cannery Renovation Project; Brad Aldridge (Project is in consultation with SHPO and the City of Moroni); $12,000.00; $12,000.00. 116; Equestrian Center Expansion Project; Mt. Pleasant City Community Development and Renewal Agency (CDRA); $66,000.00; $576,000.00; $642,000.00. 117; Panguitch Tree Removal Project; Panguitch DUP; $1,000.00; $650.00; $1,650.00. 118; Hanksville Rodeo Renovation Project; Wayne County; $10,000.00; $10,000.00; $20,000.00. 119; Historic Marysvale Mercantile Building Project; Justin and Misti Sutherland (This project is in consultation with SHPO and the Town of Marysvale); $37,500.00; $37,500.00; $75,000.00. 120; Train Depot Infrastructure Project; Mt. Pleasant Community Development and Renewal Agency; $19,800.00; $21,412.11; $41,212.11. 121; Discovery Road Series Project; North Star Video; $49,916.68; $38,287.00; $88,203.68. 122; Big Rock Candy Mountain Railroad Interpretive Project; Big Rock Candy Mountain; $25,000.00; $25,415.00; $50,415.00. 123; Piute County Courthouse Façade Restoration Project and Marysvale Visitor Center Operation Project; Piute County; $4,000.00; $4,000.00; $8,000.00. 124; Mt. Pleasant Main Street Program Fund; Mt. Pleasant Main Street Program; $10,000.00; $13,430.00; $23,430.00. 125; Mt. Pleasant Main Street Streetscape Revitalization Project; Mt. Pleasant City; $30,000.00; $90,800.00; $120,800.00. 126; Bridging History Project; Fairview City; $18,250.00; $18,250.00; $36,500.00. 127; Armory Veterans Memorial Project; Mt. Pleasant Community Development and Renewal Agency; $30,000.00; $30,000.00; $60,000.00. 128; Craighead Building Electrical Modernization Project; Wasatch Academy; $20,000.00; $22,980.29; $42,980.29. 129; Panguitch Main Street Floral Project; Panguitch City; $4,000.00; $4,000.00. 130; Salina DUP Cabin Accessibility Enhancement Project; Salina; $3,725.00; $2,825.00; $6,550.00. 131; Mt. Pleasant Main Street Program Fund; Mt. Pleasant Main Street Program; Mt. Pleasant CDRA, Utah Main Street Program, Main Street America; $95,000.00; $83,003.20; $178,003.20. 132; Mt. Pleasant City Historic Hall Restoration; Mt. Pleasant CDRA; Mt. Pleasant City, Utah State Historic Preservation Office (SHPO); $13,000.00; $13,000.00. 133; Mt Pleasant Main Street Historic Preservation and Restoration Fund; Mt. Pleasant Main Street Program; Mt. Pleasant CDRA, Utah Main Street Program, Utah State Historic Preservation Office (SHPO); $38,750.00; $38,750.00; $77,500.00. 134; Train Depot Infrastructure Project; Mt. Pleasant CDRA; Mt. Pleasant City, Sanpete County, Utah State Historic Preservation Office (SHPO); $9,189.00; $9,000.00; $18,189.00. 135; Discovery Road TV Series; North Star Video; MPNHA, Utah Education Network (UEN), participating local communities and heritage sites; $108,753.40; $125,946.60; $234,700.00. 136; Sanpete Messenger Website Project; Sanpete Messenger & MPNHA; MPNHA, regional partner organizations, local contributors; $10,305.00; $10,305.00. 137; Marketing – Web Presence & Regional Partnership; Marketing – Web Presence & Regional Partnership; MPNHA, regional tourism partners, local governments, heritage organizations; $9,500.00; $9,500.00. 138; Mt. Pleasant to Spring City Bike Path Project; Sanpete County; Mt. Pleasant City, Spring City, UDOT, Utah Office of Outdoor Recreation (UORG); $39,500.00; $2,324,955.41; $2,364,455.41. 139; Equestrian Center Expansion Project; Mt. Pleasant CDRA; Mt. Pleasant City, Sanpete County, George S. and Dolores Doré Eccles Foundation; $24,700.00; $23,000.00; $47,700.00. 154; $0.00. $10,946,250.40.

3. Collections: Documentation and Conservation Projects Paintings, Artifacts, Archives, Oral Histories, Video Histories, etc.

Report here the work in which the primary purpose is to document cultural traditions or conserve artifacts. If you are working on projects that use collections to develop interpretive or educational materials, please report these projects under Category 6: Education and Interpretation Programs. If you did not engage in work to develop or conserve cultural collections this year, please skip these metrics and move on to the Category 4: Land, Water and Environmental Conservation Projects.

WORK in PROGRESS. The numbers reported under 3A – 3B capture work that is advancing, but not yet completed.

GRANTS FOR COLLECTIONS DISBURSED 3A.1 Number of collections-related grants disbursed this year 0 3A.2 Total dollar amount disbursed this year $ 0

PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) – Number of projects begun or continued to conserve heritage area artifacts (e.g., condition assessments, plans, research, etc.). The same project can be reported on over multiple years, until it is completed. 3B. Number of collections projects begun or continued: 0

COMPLETED WORK. The information reported under 3C below captures completed work that the coordinating entity funded, led, or partnered-on with other parties.

3C. COLLECTION PROJECTS – Provide the name and a brief description of the collections created, documented, or conserved. Collections include oral histories, paintings, murals, historic documents, textiles, archaeology collections or material culture, such as boats or ships. N/A

OUTCOMES OF COMPLETED WORK. The outcomes reported under question 3D capture the results of your the collections conservation activities. Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred. Outcomes related to individual and cumulative grant activities may be included.

3D. COLLECTIONS OUTCOMES - In the space provided below, please share outcomes that have resulted from your collections related work, including grants, reported this year or unreported in previous years. Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome. N/A

4. Land, Water & Environmental Conservation Projects

Note: Include wetland work under land restoration, instead of waterway restoration. If you did not engage in natural resource conservation work this year, please skip these metrics and move on to category 5: recreation development projects.

WORK in PROGRESS. The numbers reported under 4A – 4B below capture work that is advancing, but not yet completed.

LAND AND WATER CONSERVATION GRANTS AWARDED 4A.1. Number of natural resource conservation grants disbursed this year 0 4A.2 Total dollar amount disbursed this year $0

PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to conserve natural or scenic areas (i.e., surveys, condition assessments, plans, etc.). The same project can be reported on over multiple years, until it is completed. 4B. Number of conservation projects begun or continued: 0

COMPLETED WORK. The numbers reported under 4C – 4D below capture completed work that the coordinating entity funded, led, or partnered-on with other parties.

LAND RESTORATION 4C.1. Number of acres of land restored through invasive species removal, replanting, and toxic site clean-up. (one time) 0 4C.2. Number of acres of land maintained through monitoring and clean-up efforts 0

WATERWAY RESTORATION (Streams, rivers, creeks, canals, etc.) 4D.1. Number of feet of waterways restored through appropriate in-water and bank restoration techniques (one time) 0 4D.2. Number of miles of waterways maintained through monitoring and clean-up efforts (please round to the ¼ mile) 0

OTHER ENVIRONMENTAL CONSERVATION PROJECTS 4E. Provide name and a short description of other environmental conservation projects, such as climate change monitoring. N/A

OUTCOMES OF COMPLETED WORK. The outcomes reported in question 4E capture the results of your conservation activities. Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred. Outcomes related to individual and cumulative grant activities may be included.

4F. CONSERVATION OUTCOMES - In the space provided below, please share outcomes that have resulted from your conservation work, including grants, reported this year or unreported in previous years. Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome. N/A

5. Recreation Development Projects

Note: This category does not include recreational events, programs or marketing materials. Please include recreational events and marketing materials (such as brochures, maps, guides) under Category 7: Outreach and Marketing. If you did not engage in recreation development projects this year, please skip these metrics and move on to Category 6: Education & Interpretation Programs.

WORK in PROGRESS. The numbers reported under 5A – 5B below capture work that is advancing, but not yet completed.

RECREATION GRANTS AWARDED 5A.1 Number of recreation development grants disbursed this year: 3 5A.2 Total dollar amount disbursed this year $ 64,200

PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to enhance recreational amenities (e.g., feasibility studies, plans, engineering, permitting, etc.). The same project can be reported on over multiple years, until it is completed. 5B. Number of recreation projects begun or continued: 2

COMPLETED WORK. The numbers reported under 5C – 5E below capture completed work that the coordinating entity funded, led, or partnered-on with other parties.

NEW TRAILS COMPLETED - Number of new miles of on or off road trails developed 5C.1. On-road miles: 0 5C.2. Off-road miles: 0

TRAILS MAINTAINED - Number of miles of on or off-road trails maintained through monitoring, clean-up and maintenance projects construction 5D.1. On-road miles: 4 5D.2. Off-road miles: 43, Sanpete County and US Forest Service and Counties maintained off-road trails

OTHER RECREATION DEVELOPMENT PROJECTS 5E. Provide name and a short description of other trail or park enhancement projects, such as parking, signage, trail heads, lighting, etc. or trail designation projects. For trail designations please identify the mileage. Sanpete County; Mt. Pleasant to Spring City Bike Path Project; $39,500.00; $2,324,955.41; $2,364,455.41. Mt. Pleasant CDRA; Equestrian Center Expansion Project; $24,700.00; $23,000.00; $47,700.00.

OUTCOMES OF COMPLETED WORK. The outcomes reported under question 5G capture the results of your recreation work. Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred. Outcomes related to individual and cumulative grant activities may be included.

5F. RECREATION OUTCOMES - In the space provided below, please share outcomes that have resulted from your recreation work, including grants, reported this year or unreported in previous years. Provide a short description with the project name, year project was completed, project partners and indicator and data source for outcome. Sanpete County; Mt. Pleasant to Spring City Bike Path Project; $39,500.00; $2,324,955.41; $2,364,455.41. Mt. Pleasant CDRA; Equestrian Center Expansion Project; $24,700.00; $23,000.00; $47,700.00.

6. Education and Interpretation Programs

The goal of education and interpretation programs is to increase people’s understanding of heritage area sites and stories. Note: Do not include annual meetings, conference presentations, awards ceremonies, open houses, annual fundraisers, and events. These activities are reported under category 7: outreach and marketing. If you did not conduct interpretation work this year, please skip these metrics and move on to category 7: outreach and marketing.

WORK in PROGRESS. The numbers reported under 6A - 6B capture work that is advancing, but not yet ready to be offered to the public.

EDUCATION GRANTS AWARDED 6A.1 Number of education and interpretation related grants disbursed this year: 4 6A.2 Total dollar amount disbursed this year: $ 108,753.40

PROJECTS in DEVELOPMENT (Do Not Include Grant Projects Reported Above) - Number of education and interpretation projects in development (e.g., assessments, research, etc.). The same project can be reported on over multiple years, until it is offered or made available to the public. 6B. Number of education and interpretation projects in development: 1

OFFERED PROGRAMS AND PRODUCTS. The information reported under 6C – 6D below captures the work that the coordinating entity funded, led, or partnered with other parties to offer this year.

6C. PROGRAMS OFFERED - In the space below, provide name and a short description of the interpretive or educational programs supported by the NHA coordinating entity this year. - Discovery Road TV Series – In cooperation with the Utah Education Network (UEN) and BYUtv, this series explores the history and culture of the Mormon Pioneer National Heritage Area. We are now actively expanding distribution to a national audience through partnerships with additional networks and streaming platforms. - Town Track and Sanpete Art and History Tour – A local heritage tour highlighting key cultural and historical sites within the heritage area. - Mt. Pleasant Main Street Program – Offers various community-based events and interpretive activities related to the preservation and revitalization of historic sites.

6D. PRODUCTS OFFERED - In the space below, provide name and a short description of the interpretive or educational products (print, web, or multi-media) supported by the NHA coordinating entity this year. - Discovery Road TV Series Products – 65 TV episodes completed, with seven produced and distributed this year to TV stations and schools via UEN and BYUtv. Efforts are underway to expand distribution to national platforms. - Discovery Road DVDs – Episodes available for purchase and educational use. - MPNHA Books – Including Legends, Lore, and True Tales in Mormon Country, published by Arcadia Publishing/History Press, available in Utah libraries and for purchase. - MPNHA YouTube Channel – Features various videos related to the heritage area: MPNHA YouTube Channel. - MPNHA Website – Provides comprehensive information on the heritage area and its projects: MormonPioneerHeritage.org. - Blackhawk War: Cultures in Conflict DVD – An educational tool distributed to schools and organizations to highlight the historical conflict between Native Americans and settlers in the area. - Heritage Trails and Interpretive Signage: - Interpretive signage at the Historic Denver Rio Grande Depot in Mt. Pleasant, providing historical insights into the railroad's impact on the area. - Interpretive signage inside the new Mt. Pleasant City Hall (formerly the Wells Fargo Bank building), offering historical context and educational displays. - Development of a new Mt. Pleasant Historic Walking Tour Guide, offering self-guided exploration of key historical sites within the community. - Interpretive signage and displays at the Salina CCC/POW Camp Memorial, telling the story of German prisoners of war and the Civilian Conservation Corps. - The Chief Sanpitch Statue as part of the Mt. Pleasant Railroad Park Project, which includes educational signage on the region's indigenous heritage. - The Mt. Pleasant Armory Veterans Memorial Project, featuring interpretive signage recognizing veterans from Utah’s Blackhawk War and other historical conflicts. - Marysvale Visitor Center Interpretive Panels, providing insights into the area's cultural and historical significance. - Heritage Trail Project - Mt. Pleasant to Spring City, featuring signage and interpretive elements along a key historic route. - Sanpete Recreation Infrastructure Projects, including trail signage, cultural surveys, and historical interpretive materials.

OUTCOMES of PROGRAM AND PRODUCTS OFFERED. The outcomes reported under question 6E capture the results of your education work. Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred. Outcomes related to individual and cumulative grant activities may be included.

6E. EDUCATION OUTCOMES - In the space provided below, please share any outcomes that have resulted from heritage area educational work, including grants, reported this year or unreported in previous years. Provide a short description with the project name, year project was completed, project partners and indicator and data source for outcome. - Discovery Road TV Series - The Discovery Road TV series has completed 65 episodes, with seven produced and distributed this year via UEN and BYUtv. The series is expanding to national distribution through partnerships with additional networks and streaming platforms. Schools, libraries, and museums across Utah utilize the series as an educational tool, and it is available via the MPNHA YouTube channel and DVD distribution. The series continues to attract new audiences and promote heritage tourism by showcasing the region’s history and culture. - Blackhawk War: Cultures in Conflict DVD - This educational DVD has been distributed to schools, libraries, and community organizations, providing valuable insights into the history of the Blackhawk War and its impact on settlers and Native American communities. It remains a widely used resource for educators teaching Utah history and has contributed to increased awareness of the complexities of pioneer-native relations in the region. - Mt. Pleasant Main Street Program - The Mt. Pleasant Main Street Program plays a critical role in guiding and approving nearly all projects within the MPNHA's focus area in Mt. Pleasant. The program supports a range of community-driven preservation and revitalization initiatives, contributing to the economic and cultural development of the city. Key outcomes include: - Interpretive signage at the Historic Denver Rio Grande Depot, providing historical insights into the railroad’s significance and impact on local economic development. - Interpretive signage inside the new Mt. Pleasant City Hall, formerly the Wells Fargo Bank building, offering educational displays detailing the financial and historical heritage of the area. - Development of the Mt. Pleasant Historic Walking Tour Guide, which offers self-guided exploration of key historical sites, buildings, and landmarks throughout the community. - Installation of the Chief Sanpitch Statue at the Mt. Pleasant Railroad Park, accompanied by educational signage that tells the story of the region's indigenous heritage and its connection to pioneer settlers. - Completion of the Mt. Pleasant Armory Veterans Memorial Project, honoring local veterans from Utah’s Blackhawk War and subsequent conflicts with educational signage detailing their contributions. - The Heritage Trail Project - Mt. Pleasant to Spring City, featuring interpretive signage along the historic route connecting these two National Register communities, educating visitors on the area’s early settlement and development. - Salina CCC/POW Camp Memorial - Interpretive signage and displays have been installed at the Salina CCC/POW Camp Memorial, educating visitors about the history of the German prisoners of war and the Civilian Conservation Corps stationed there during World War II. These exhibits have attracted school groups, veterans’ organizations, and heritage tourists seeking to learn about this unique aspect of Utah’s history. - Marysvale Visitor Center Interpretive Panels - Educational panels installed at the Marysvale Visitor Center provide insights into the area's rich mining heritage, early settlement patterns, and cultural contributions. These panels have enhanced the visitor experience by offering context and historical narratives that support heritage tourism in the region. - Sanpete Historic Trails Interpretive Signage - The Sanpete Historic Trails Project has implemented interpretive signage that provides educational information about key trails, landmarks, and historical events along recreational routes throughout the county. Visitors exploring these equestrian, ATV, hiking, and driving trails now have access to contextual history and cultural narratives that connect them with the pioneers and indigenous peoples who once traveled the area. - Sanpete Recreation Infrastructure Projects - Trailheads and recreational areas throughout Sanpete County have been enhanced with signage, cultural surveys, and interpretive materials that provide historical context to outdoor enthusiasts. The trails support a variety of recreational activities, including equestrian, ATV, hiking, and driving tours, offering educational insights about the region’s landscape and historical significance. - Casino Star Theatre Restoration - The restoration of the historic Casino Star Theatre in Gunnison has resulted in a revitalized cultural venue that now hosts community events, film screenings, and educational programs focused on the area's history and performing arts. - Ephraim Granary Arts Center - The renovation of the historic granary has created a thriving arts and cultural center that offers workshops, art exhibitions, and educational events, fostering a greater appreciation of local heritage and artistic expression. - Track 89 Boxcar Restoration and Train Depot Project - This project has preserved historical railroad elements in Mt. Pleasant, repurposing them into an educational space that informs visitors about the role of railroads in the development of the region while providing a unique heritage tourism attraction. - Fairview Museum of History and Art - Support for the museum has allowed for the expansion of exhibits and educational programming, including hands-on activities for school groups and tourists to engage with Sanpete County’s pioneer and artistic heritage. - Gunnison Legacy Wall and Clarion Interpretive Signs - This project has created educational displays that commemorate the Jewish immigrant community that settled in Clarion, providing insight into their contributions to the region’s agricultural history and cultural diversity. - Butch Cassidy Cabin Restoration - The preservation and interpretation of the Butch Cassidy Cabin in Piute County have provided an educational resource for visitors interested in the legendary outlaw and his connection to the local area, fostering heritage tourism. - Panguitch Main Street Floral Project - This beautification effort has included interpretive signage that connects visitors to the city’s historic roots, enhancing the cultural and visual appeal of the downtown area while providing historical context. - Big Rock Candy Mountain Railroad Interpretive Project - Educational signage at this site provides visitors with insights into the history of the region’s railroad development and its impact on commerce and settlement patterns in central Utah. - Historic Spring City Firehouse Restoration - This project has preserved the historic firehouse while incorporating educational displays that inform visitors about the role of firefighting and community resilience in pioneer settlements. - Ephraim Pioneer Park and DUP Museum Project - The park and museum have been enhanced with educational displays and interactive exhibits that teach visitors about the daily lives and contributions of early pioneers in the region. - Kanab Heritage Center - This restored historic building now serves as an educational and cultural hub, offering exhibits and programs that highlight the diverse history of Kanab and surrounding areas, drawing tourists and researchers alike. - Ephraim Carnegie Library Restoration - The preservation of this historic library has allowed for continued educational programming and public access to resources detailing the history of the area and its early settlers. - Historic Denver Rio Grande Depot in Mt. Pleasant - The restored depot serves as both a transportation hub and an educational site, offering interpretive displays that share the story of the railroad’s influence on local development and commerce.

7. Outreach and Marketing (include presentations, sponsorships, and other outreach activities here)

Note: Include economic impact studies under products offered. If you did not conduct outreach or marketing work this year, please skip these metrics and move on to Category 8: Community Engagement.

WORK in PROGRESS. The numbers reported under 7A – 7B capture work that is advancing, but not yet ready to be offered to the public.

OUTREACH & MARKETING GRANTS AWARDED 7A.1 Number of outreach and marketing grants disbursed this year 11 7A.2 Total dollar amount disbursed this year $ 208,921.29

PROJECTS in DEVELOPMENT (Do Not Include Grant Projects Reported Above) - Number of promotion and marketing projects in development (e.g., assessments, research, etc.). The same project can be reported on over multiple years, until it is offered or made available to the public. 7B. Number of promotion and marketing projects in development: 2

OFFERED EVENTS AND PRODUCTS. The numbers reported under 7C – 7D below capture work that the coordinating entity funded, led, or partnered with other parties to offer to the public this year.

7C. EVENTS OFFERED (RACES, CELEBRATIONS, AWARDS CEREMONIES, FAM TOURS, ETC.) - In the space below, provide name and a short description of promotional activities supported by the coordinating entity. - Western Legends Roundup - Scandinavian Days - Mormon Pioneer Heritage Festival - Spring City Heritage Days - Everett Ruess Festival - Jacob Hamblin Days - Butch Cassidy Days - Panguitch Quilt Walk - Map N Tour Project - Mt. Pleasant Historic Walking Tour

7D. PRODUCTS OFFERED (BROCHURES, ECONOMIC IMPACT STUDIES, WEBSITES, ETC.) - In the space below, provide name and a short description of promotional products supported by the coordinating entity. - MPNHA website – https://www.mormonpioneerheritage.org - MPNHA YouTube Channel – https://www.youtube.com/channel/UCwY8IF4uHOhMHopvi-DQkdQ - Travel planner – Printed and distributed to visitors and organizations. - Discovery Road TV Series – Distributed via internet and broadcast. - DVDs of Discovery Road episodes – Available for purchase and educational use. - MPNHA Books – Legends, Lore, and True Tales in Mormon Country, published by Arcadia Publishing/History Press, available in Utah libraries and for purchase. - Blackhawk War: Cultures in Conflict educational DVD – Distributed to schools and other entities. - Map N Tour mobile tourism application – Enhancing tourism experiences within the heritage area. - Mt. Pleasant Historic Walking Tour Guide (in development) – A guide offering self-guided exploration of key historical sites within the community. - MPNHA Management Plan – Available on mormonpioneerheritage.org. - 10-Year Report (2017) – Available on mormonpioneerheritage.org. - Annual Reports: Available on mormonpioneerheritage.org.

OUTCOMES of EVENTS AND PRODUCTS OFFERED. The outcomes reported under question 7E capture the results of your promotion and marketing work. Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred. Outcomes related to individual and cumulative grant activities may be included.

7E. OUTREACH & MARKETING OUTCOMES - In the space provided below, please share outcomes that have resulted from heritage area marketing activities reported this year or offered in previous years. Outcomes could include increases in visitation to heritage area sites generated by marketing products. Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome. - Discovery Road TV Series Expansion – The show continues to be broadcast on UEN and BYUtv, with efforts in progress to expand distribution to a national audience. - MPNHA Website Usage – The MPNHA website serves as a resource for information about events, travel itineraries, and heritage sites. The site provides downloadable travel planners and other resources to help visitors plan their experiences. - Travel Planner Distribution – MPNHA continues to print and distribute travel planners to visitor centers and events, providing tourists with key heritage information. - Event Support and Participation – MPNHA supports multiple heritage-themed events across the five districts, promoting local heritage and encouraging tourism.

8. Community Engagement

The numbers captured here reflect the work of the NHA coordinating entity and partnership. Please answer all questions below.

PARTNERSHIPS A partnership is a relationship between parties to accomplish a common goal, such as developing or implementing a heritage area project or offering heritage area programs. Partnerships are characterized by mutual interest, commitment, and communication. Please count partners one time, either as formal or informal partners. 8A.1 Formal Partners are the organizations who you directly collaborate with on heritage area projects and programs and who are substantially involved in those projects or programs. You may have an agreement in place to formalize your partnership with these organizations, but having an agreement is not a requirement for being a formal partner. Number of formal partners substantially engaged in National Heritage Area activities this year: 17 8A.2 Informal Partners are those organizations who you cooperate or coordinate with on projects and programs. These organizations are not substantially involved in your projects or programs. Number of informal partners engaged in National Heritage Area activities this year: 75

VOLUNTEERISM Volunteer Count. Please count volunteers who are working on projects or programs that are coordinated and/or funded by the national heritage area coordinating entity. Do not include volunteers at park units or other sites for which there was no investment of heritage area staff time or funding. 8B.1 Total number of volunteers engaged in heritage area projects, programs or activities 298 8B.2 Total number of volunteer hours 5,796 (please round-up to the nearest hour) 8B.3 Hourly value of volunteer time for your state or region (refer to www.independentsector.org/volunteer_time for your region) $ 33.46 8B.4 Total dollar value of volunteer hours $ 193,934.16

PROGRAM & EVENT PARTICIPANTS Program and Event Participant Count. Please count participants who attended events or programs that were coordinated and/or funded by the national heritage area coordinating entity. Do not include participants in programs at parks or other sites where there was no investment of heritage area staff time or funding. 8C.1 Number of people who participated in heritage area educational programs this year: 24,500 8C.2 Number of people who participated in heritage area events (races, celebrations, ceremonies, etc.) this year: 35,000

OTHER ACTIVITIES 8D.1 In the space below, identify any other activities including community development, economic development or community engagement projects that do not fit into the seven categories above. N/A

Best Practice: Highlight a Successful Project or Program

In the space below, please describe a creative, successful project or program undertaken or completed this year. Please include images with captions and credit information. Also, include numbers if applicable – dollars invested and leveraged, communities or residents involved or impacted, properties preserved, miles of trails improved, etc. Word count recommendation is 200 words.

DISCOVERY ROAD TELEVISION SHOW Best Practice: Heritage Storytelling Through National Television We are honored to have a longstanding working relationship with the Mormon Pioneer National Heritage Area (MPNHA) that brings forward history, culture, and heritage in the American West. The excitement, curiosity, and storytelling power of Discovery Road provide viewers with an entertaining ride to yesterday. The partnership Discovery Road has with the MPNHA and others in bringing history forward is an ever-growing example of how different groups and organizations can cooperate, bond, and work together to achieve goals and overcome barriers. Hardy Redd looks out over the Home of Truth compound in southeastern Utah. Redd was well acquainted with the woman who ran the religious commune in the 1930s. He visited the property with our show producer during production of The Untold episode. Photo courtesy of Discovery Road. Many people have appeared in Discovery Road episodes and consistently share positive feedback about the experience. Others who view the shows find new excitement and opportunity in the history and stories of their own neighborhoods. The cumulative impact Discovery Road has on groups, organizations, and the general public is a renewed understanding that history is important. Each story and every episode feels like a renaissance of the past. Historical documents, on-camera interviews, scrapbooks, photographs, films, journals, century-old homes, restored schoolhouses, and refurbished theaters all seem to take on a special frame when they find their way into a Discovery Road television show. FY2025 Accomplishments and National Distribution During FY2025, one of the most significant accomplishments of Discovery Road was the expansion of national distribution. With a total project investment of $234,700.00, including $108,753.40 in federal funding and $125,946.60 in matching funds, this year’s work focused on sharing heritage stories with audiences far beyond the Mormon Pioneer National Heritage Area. Programming aired through the National Educational Telecommunications Association (NETA) and Weigel Television, allowing Discovery Road to reach viewers across multiple states and connect national audiences to local history and lived experience. 60 National Heritage Areas. One Television Show. It is a real accomplishment that Discovery Road and the MPNHA have partnered to highlight history, culture, and heritage for more than a decade. It is even more remarkable that Discovery Road remains the only television program associated with a National Heritage Area. Because of this unique position, many other heritage areas across the country have reached out to us for development and production of Discovery Road in their own regions. Image caption: Ute spiritual leader Larry Cesspooch on location with our television news crew. Cesspooch has appeared in numerous Discovery Road shows. Photo courtesy of Discovery Road. Ute spiritual leader Larry Cesspooch on location with our television news crew. Cesspooch has appeared in numerous Discovery Road shows. Photo courtesy of Discovery Road. Our television series has produced shows in the Sangre de Cristo National Heritage Area, the Santa Cruz Valley National Heritage Area, and the Northern Rio Grande National Heritage Area. In addition, we have developed programming in more than a dozen states. The National Educational Telecommunications Association has embraced our television road series, and Weigel Television regularly schedules and broadcasts our shows. This special way of communicating with the public about important heritage stories, events, and people has grown into a powerful educational and outreach tool that crosses borders and connects communities. Discovery Road is proud to hear people from across our great nation continue to beckon us to come tell their stories. James Nelson Discovery Road

NOTICES

Privacy Act Statement

General:  This information is provided pursuant to Public Law 93-579 (Privacy Act of 1974), December 21, 1984, for individuals completing this form.

Authority:  54 USC Ch. 3201, Historic Sites Act of 1935, as amended; 44 U.S.C. 3501, et seq., Paperwork Reduction Act of 1995; and individual pieces of legislation and associated amendments in 54 USC 100702 that enable the NPS, on behalf of the Secretary of the Interior, to provide federal financial, technical, and other assistance for the preservation of natural, cultural, historic, and scenic resources.

Purposes and Uses:  The NPS intends to track the progress of each heritage area on implementing its management plan and meeting performance goals. The information collected is used by the NHA program office in monitoring the progress of each heritage area. The collection of this information is necessary to allow for national oversight, analysis, coordination, technical and financial assistance, and support to National Heritage Areas to ensure consistency and accountability across the country.

Effects of Nondisclosure:  Financial disclosure is in accordance with 54 USC Ch. 3201, Pub. L. 113–291, div. B, title XXX, §3052(a)(2), Dec. 19, 2014, 128 Stat. 3802.

Information Regarding Disclosure of Your Social Security Number Under Public Law 93-579 Section 7(b): Your Social Security Number is not needed to complete this form.

Paperwork Reduction Act Statement

We are collecting this information subject to the Paperwork Reduction Act (44 U.S.C. 3501) in response to the NHAs individual authorizing legislation requiring annual reporting as mandated by Congress. The information provided by NHA Coordinating Entities allows the NHA program office to allocate funding to heritage area management, prepare NPS budget justifications, and track management planning and implementation across NHAs. We may not conduct or sponsor and you are not required to respond to a collection of information unless it displays a currently valid OMB Control Number. OMB has reviewed and approved this survey and assigned OMB Control Number 1024-###, which expires ##/##/####.

Estimated Burden Statement

Public Reporting burden for this form is estimated to average 42 minutes per response, including the time it takes for reviewing instructions, gathering and maintaining data, and completing and reviewing the form. Comments regarding this burden estimate or any aspect of this form should be sent to the Information Collection Clearance Officer, National Park Service, 1201 Oakridge Drive, Fort Collins, CO 80525.

Disbursed is defined as funds that have left the heritage area’s account and gone to a grant recipient.