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Purpose 
The information collected through this form will be used by the National Park Service (NPS), National Heritage Areas (NHA) Program Office and regional program offices to track each heritage area management or coordinating entity’s (coordinating entity) progress on management plan implementation.  The progress measures outlined in the categories below capture information about the diverse heritage area activities and approaches to these activities (process measures), direct products or services offered (output measures), and the results of the products or services (outcome measures).  

The NPS will use the responses to the questions reported here in annual program reports and publications and to inform individual heritage area evaluations.  

Reporting Instructions 
The progress measures in this form are grouped under eight categories, capturing the diverse work of the coordinating entities throughout the country.  We recognize that each heritage area and coordinating entity is unique.  Therefore, not all of the categories or measures presented below will apply.   

· The data reported here shall reflect the work that the coordinating entity led, funded or partnered with others to complete this year.  

· Report all work that the coordinating entity was involved in to implement the National Heritage Area Management Plan.  Include work supported by Heritage Partnership Program (HPP) funding and other heritage area funding sources.  

· Report data for the same 12-month cycle (calendar, federal, and fiscal) that you reported last year.  
 
· Measures under categories 2 – 7 are sequenced to capture work in progress, work that is completed, and the outcomes of completed work.  
   
· Follow the specific instructions for each category and measure.  Please be consistent in how you categorize your work.  When deciding how to categorize a specific project or program, it may be helpful to consider the project or program purpose in relation to your NHA goals. 

· If you are implementing or funding multicomponent projects, please count each component separately.  For example, you might be working on a project that involves the preservation of a building or site, site interpretation, and an event.  Using this example, each component would be counted as a separate project under the preservation, education and interpretation, and promotion categories.  If it is not possible to separate project components, please report on the project under the category that is most appropriate given the funding amount.      

· Retain all supporting documentation used in filling out this form in your office files until a program evaluation has been completed for your heritage area.  Per 2CFR Part 215.53, the NPS, as well as the Inspector General or Comptroller General, reserve the right to review supporting documents.  The NPS NHA Program Office reviews these forms and may contact you periodically to insure consistent and accurate reporting.  



Form Submittal 
Identify the name of the heritage area you represent at the top of this page.  The complete form includes your NHA name, goals, responses to applicable categories and metrics, and your name, signature, and date verifying the accuracy of the information provided.  

Sign and scan in or save as PDF and sign electronically. Email this form to the NHA Program Office at NHA@nps.gov and copy your regional coordinator and agreements technical representative by close-of-business on the date listed at the top of this form.  

Assurance Statement
As the authorized representative of the local coordinating entity, I certify that the progress indicators reported below are supported by documentation that is verifiable in our records.  

	Name: Monte Bona
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	Date: 9 January 2026



Heritage Area Goals
In the space below please identify the heritage area goals that appear in your management plan or management plan update. 

Please identify your reporting cycle here by name (Federal fiscal, state, calendar, etc.): Click here to enter text. 
	1.  Financial Assistance and Capacity Building

	The numbers captured here reflect the work of the coordinating entity only.  Leverage metrics are intended to capture the economic contribution of NHAs.     

	LEVERAGE
Leverage is using what you already have, in this case HPP funding, to bring about more support than would be possible otherwise.  Include all sources that you secured this past fiscal year that you would not have had unless HPP funds were available. Other federal funds (not including HPP funds) may be included.     
1A.1 Total amount of funding leveraged, including other Federal funds, to implement heritage area activities this year $ 2,653,888.81
1A.2 Provide a breakdown of leveraged funds, include cash and in-kind donations in totals. 
State $ 2,237,853.00
Local Government $ 290,089.21
Private $ 125,946.60 
Other Federal Funding (not HPP, but include other NPS funding) 
(Specify funding source): Click here to enter text. $ 0
Other (please specify): Click here to enter text. $ 0 
· Mat

	GRANTS
Grants are the transfer of money from a national heritage area coordinating entity to a recipient whose project proposal is selected through a review process.  Grants are awarded to recipients to accomplish the goals of the national heritage area.  Grants do not include sponsorships, contracts, or donations. 
1B.1 Total number of grants disbursed[footnoteRef:1] this year 31  [1:  Disbursed is defined as funds that have left the heritage area’s account and gone to a grant recipient. 
] 

1B.2 Total grant dollars disbursed this year $ 500,000
Please provide a breakdown of the grant funds distributed this year under the categories (2 - 7) below.

	
CAPACITY BUILDING
Capacity building assistance includes guidance related to historic preservation, education, heritage tourism, natural resource conservation, etc., or the organizational capacity of a partner organization.  Capacity building assistance does not include oversight related to administration of sub grants, phone calls directing the individuals to resources or informational meetings, etc.  
Count the number of organizations, not people.  For example, if one person represents two organizations, the number of organizations is two. 


1C.1 Number of organizations to which you provided capacity building assistance through trainings, workshops, onsite assessments, etc.  0
1C.2 Number of capacity building grants awarded this year 0
1C.3 Total dollar amount awarded $ 0
1C.4 In the space provided below, share any outcomes that have resulted from your capacity building assistance this year or in previous years.  Provide a short description with the project name, year project was completed, and indicator and data source for outcome.  N/A


	2.  Historic Preservation & Other Community Enhancement Projects 

	If you did not engage in historic preservation or community enhancement work this year, please skip these metrics and move on to Category 3: Collections.

	WORK in PROGRESS.  The numbers reported under 2A – 2B below capture work that is advancing, but not yet completed.

	HISTORIC PRESERVATION GRANTS DISBURSED 
2A.1 Number of historic or cultural resource preservation grants disbursed this year 5
2A.2 Total dollar amount disbursed $ 72,939.00

	PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to enhance listed or eligible National Register properties (e.g., condition assessments, plans, research, etc.).  The same project can be reported on over multiple years, until it is completed.  
2B. Number of historic preservation projects begun or continued: 5

	COMPLETED WORK.  The numbers and information reported under 2C – 2F below captures completed work that the coordinating entity funded, led, or partnered-on with other parties.    

	2C. NOMINATIONS COMPLETED - Number of historic or cultural resources nominated to the National Register of Historic Places 0

	SITES PRESERVED - Historic sites (i.e. those listed or eligible for listing on the National Register of Historic Places) preserved through restoration, rehabilitation or adaptive reuse, and reconstruction 
2D.1 Number of sites preserved 9 (for a grouping of buildings indicate 1 district/number of contributing buildings)
2D.2 Total acreage of preserved landscapes, such as battlefields, etc. 0 

	SITES MAINTAINED – Historic properties (i.e. listed or eligible for listing on the National Register of Historic Places) maintained through monitoring and small-scale maintenance projects.  Note: If you own or manage historic building(s) or site(s) this is where you can capture your on-going maintenance efforts. 
2E.1 Number of sites maintained 19 (for a grouping of buildings indicate 1 district/number of contributing buildings)
2E.2 Total acreage of preserved landscapes, such as battlefields, etc. 0

	2F. OTHER COMMUNITY ENHANCEMENT PROJECTS COMPLETED – In the space provided, provide name and a short description of streetscape or façade improvement projects, as well as other projects that are intended to enhance communities (e.g., art projects or business development projects).  
	Mt. Pleasant Main Street Program
	Mt. Pleasant Main Street Program Fund
	$95,000.00
	$83,003.20
	$178,003.20

	Mt. Pleasant CDRA
	Mt. Pleasant City Historic Hall Restoration
	$13,000.00
	 
	$13,000.00

	Mt. Pleasant Main Street Program
	Mt Pleasant Main Street Historic Preservation and Restoration Fund
	$38,750.00
	$38,750.00
	$77,500.00

	Mt. Pleasant CDRA
	Train Depot Infrastructure Project
	$9,189.00
	$9,000.00
	$18,189.00




	OUTCOMES OF COMPLETED WORK.  The outcomes reported under question 2G captures the results of your historic preservation and community development activities.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	2G. HISTORIC PRESERVATION & COMMUNITY ENHANCEMENT OUTCOMES - In the space provided below, please share outcomes that have resulted from your historic preservation work, including grant work, reported this year or in previous years.  Provide a short description that includes the project name, year project was completed, project partners, and indicator and data source for outcome. 
	#
	Project Title
	Recipients and partners
	Other entities
	Federal Funds
	Matching Funds
	Total Project

	1
	Restoration of Historic Presbyterian Church - Manti
	 Manti City
	 Veterans Groups
	
	
	$9,600.00

	2
	Casino Star Theater Restoration
	 Casino Star Theater Foundation
	 State of Utah, Utah Division of State History
	
	
	$31,000.00

	3
	Restoration of historic Mt. Carmel Church
	 Kane County
	 State of Utah
	
	
	$20,000.00

	4
	Wayne County-Teasdale Daughters of Utah Pioneers Museum
	 Teasdale Town
	 Wayne County
	
	
	$13,000.00

	5
	Centerfield Historic Social Hall
	 Centerfield Town
	
	
	
	$10,000.00

	6
	Historic Panguitch City Grandstand
	 Panguitch
	 Garfield County
	
	
	$10,000.00

	7
	Historic Presbyterian Building
	 Sanpete County Economic Development
	 American Legion
	
	
	$9,600.00

	8
	Fountain Green Social Hall and Theater
	 Fountain Green City
	
	
	
	$14,000.00

	9
	Wayne County Cemetery Restoration Project
	 Wayne County Commission
	
	
	
	$12,600.00

	10
	Snow College Alpine Station
	 Snow College
	
	
	
	$16,500.00

	11
	Spring City School
	 Spring City Historic Preservation Commission,  Save America's Treasures, numerous other donors 
	 George S. and Dolores Dore' Eccles Foundation
	
	
	$25,000.00

	12
	Manti Main Street historic building restoration
	 Manti City
	 Sanpete County Economic Development
	
	
	$7,000.00

	13
	Manti historic City Hall
	 Manti City
	 Sanpete County Economic Development
	
	
	$14,450.00

	19
	Ephraim Co-op historic building
	 Ephraim City
	 Sanpete County Economic Development
	 
	
	$6,650.00

	20
	Manti Daughters of Utah Pioneers Museum
	 Manti City
	
	 
	
	$1,900.00

	21
	Manti Carnegie Library restoration
	 Manti City
	 George S. and Delores Dore' Eccles Foundation
	 
	
	$25,000.00

	22
	Fairview Social Hall
	 Fairview City
	 Community Impact Board, numerous other donors
	 
	
	$25,000.00

	23
	Ephraim Carnegie Library restoration
	 Ephraim City
	 George S. and Delores Dore' Eccles Foundation
	 
	
	$20,000.00

	24
	Mt. Pleasant Carnegie Library restoration
	 George S. and Delores Dore' Eccles Foundation
	 US Department of Agriculture Rural Development grant, Utah Division of State History
	 
	
	 

	25
	Mt. Pleasant Armory
	 Mt. Pleasant Main Street Program
	 Preserve America grant, Utah Division of State History
	 
	
	 

	26
	Lizzie and Charlie's Rag Rug Factory
	 Monroe Preservation Society
	
	 
	
	$25,000.00

	27
	Marysvale Town Old Rock School House
	 Marysvale City
	
	 
	
	$4,800.00

	28
	Carol Theater
	 Monroe
	 Scenic Canyons Preservation Society
	 
	
	$15,000.00

	29
	Orson Hyde Office/Allred School
	 Spring City
	 Allred Family
	 
	
	$9,000.00

	30
	Old General Store
	 Spring City
	
	 
	
	$5,000.00

	31
	Wasatch Academy Music Conservatory
	 Wasatch Academy
	
	
	
	

	32
	Gunnison Legacy Wall and Clarion Interpretive Signs
	 Gunnison City
	 American Jewish Preservation Society
	
	
	$30,000.00

	33
	Gem Theater
	 Panguitch City Main Street Program
	 Scenic Canyons Preservation Society
	
	
	$55,000.00

	34
	Heritage Rag Museum
	 Marysvale and Piute County
	
	 
	
	$11,475.00

	35
	Kanab Heritage Center
	 Kanab City
	
	 
	
	$60,000.00

	36
	Wayne County Visitors Center
	 Wayne County
	
	 
	
	$30,000.00

	37
	Mt. Pleasant Equestrian Center
	 Mt. Pleasant City
	
	 
	
	$125,000.00

	38
	Wasatch Academy Pierce Hall
	 Wasatch Academy
	
	 
	
	$305,000.00

	39
	Casino Star Theater Restoration
	 Casino Star Theater Foundation
	
	 
	
	$137,625.00

	40
	Panguitch Main Street Project
	 Panguitch Main Street Project
	
	 
	
	$26,465.00

	41
	Salina CCC/POW Restoration
	 Salina City
	
	 
	
	$103,000.00

	42
	Miss Mary's Museum Restoration
	 Salina City
	
	 
	
	$20,000.00

	43
	Ephraim City Granary Project
	 Ephraim City
	
	 
	
	$11,300.00

	44
	Restoration/Renovation of Wasatch Academy Historic Administration Building
	 Wasatch Academy
	
	 
	
	$26,182.00

	45
	Restoration work on Mt. Pleasant City Hall and Armory Building
	 Mt. Pleasant City
	 Utah Division of State History
	 
	
	$51,500.00

	46
	Hanksville Community Hall Restoration
	 Hanksville Town
	
	 
	
	$322,000.00

	47
	Bicknell Theater and Community Center
	 Bicknell Town
	
	 
	
	$65,000.00

	48
	Spring City School Restoration/Renovation Phase III
	 George S. and Delores Dore' Eccles Foundation
	 Spring City Historic Preservation Commission
	 
	
	$575,000.00

	49
	Save America's Treasures and numerous other donors
	 Garfield and Piute Counties
	 State of Utah, Utah Division of State History
	
	
	$219,141.00

	50
	CCC/Pow Camp Building/Site Restoration
	 Salina City
	 Utah Division of State History, non-profits and private donors
	
	$50,000.00

	51
	Spring City Victory Hall Restoration
	 Spring City
	 Utah Division of State History
	
	
	$7,000.00

	52
	Monroe Carol Theater Restoration
	 Carol Theater Restoration Committee
	
	$18,475.00
	$190,000.00
	$208,475.00

	53
	Jacob Hamblin Heritage Park
	 Kanab City
	 Kane County, State of Utah
	
	
	$190,000.00

	54
	Wayne County DIP Project
	 Wayne County
	
	
	
	$36,000.00

	55
	Bicknell People's Mere Restoration
	 People's Mere Restoration Partner
	
	
	
	$24,000.00

	56
	Spring City Historic School Restoration
	 Friends of Spring City
	 State of Utah, George S. and Dolores Dare's Eccles Foundation
	
	$459,843.00

	57
	Denver Rio Grande 1890's Depot Restoration
	 Mt. Pleasant City
	 Scenic Canyons Preservation Society
	
	
	$50,000.00

	58
	Mt. View DUP Historic Building Restoration
	 Mt. View Daughters of Utah Pioneers
	
	
	
	$8,000.00

	59
	Miss Mary's Historic School/Museum Restoration
	 Salina City
	 Miss Mary's Museum Committee
	
	
	$22,618.00

	60
	Kanab Carnegie Library
	 Kane County
	 Kanab City
	
	
	$37,000.00

	61
	Fremont School Bell
	 Fremont chapter of the Daughters of Utah Pioneers
	
	
	$10,000.00

	62
	Historic Presbyterian Church Building
	 local American Legion
	
	
	
	$9,000.00

	63
	Wayne County DUP records project
	 
	
	
	
	$8,000.00

	64
	Marysvale Historic Outdoor Dance Hall Restoration
	 Marysvale Town
	
	
	
	$140,000.00

	65
	Garfield County Historic Fairgrounds Grandstand restoration
	 Garfield County
	
	
	
	$10,000.00

	66
	Wayne County DUP Historic Records Building Restoration
	 
	
	
	
	$8,000.00

	67
	Sanpete County Fairgrounds project
	 Sanpete County
	
	
	
	$160,000.00

	68
	Casino Star Theater restoration
	 Casino Star Theater Foundation
	 George S. and Dolores Dore' Eccles Foundation
	
	
	$92,000.00

	69
	Wasatch Academy Craighead vocational building restoration
	 Wasatch Academy
	 George S. and Dolores Dore' Eccles Foundation
	
	
	$180,000.00

	70
	Historic Denver Rio Grande Project
	 Mt. Pleasant City CDRA
	
	
	
	$13,000.00

	71
	Sanpete County CLG historic Homes Restoration project
	 Sanpete County Certified Local Government
	 building owners
	
	
	$26,000.00

	72
	Wayne County Teasdale Restoration Project
	
	
	$20,000.00
	$105,000.00
	$125,000.00

	73
	Garfield County Historic Fairgrounds Restoration Project
	
	
	$20,000.00
	$58,900.00
	$78,900.00

	74
	Casino Star Theatre “Take a Seat” Project
	
	
	$20,000.00
	$85,564.00
	$105,564.00

	75
	Bishop’s Storehouse project
	
	
	$30,000.00
	$38,000.00
	$68,000.00

	76
	Historic Manti City Hall
	
	
	$1,500.00
	$1,500.00
	$3,000.00

	77
	Wayne County Heritage Park project
	
	
	$18,000.00
	$22,000.00
	$40,000.00

	78
	The Scout House project
	
	
	$25,000.00
	$35,000.00
	$60,000.00

	79
	Moroni Veterans’ Memorial
	
	
	$5,000.00
	$62,000.00
	$67,000.00

	80
	Mt. Pleasant Depot project
	
	
	$10,000.00
	$11,500.00
	$21,500.00

	81
	Mining Museum project
	
	
	$20,000.00
	$20,000.00
	$40,000.00

	82
	Wayne County Fairgrounds Project
	
	
	$20,000.00
	$180,000.00
	$200,000.00

	83
	Monroe City Hot Springs Park Project
	
	
	$25,000.00
	$34,418.00
	$59,418.00

	84
	Miss Mary’s Museum Project
	
	
	$10,000.00
	$12,678.82
	$22,678.82

	85
	Historic Spring City Firehouse
	
	
	$4,439.00
	$4,438.00
	$8,877.00

	86
	Mt. Pleasant Relic House Project
	
	
	$5,000.00
	$7,370.00
	$12,370.00

	87
	Ephraim City DUP Pioneer Park and DUP Museum Project
	
	
	$25,000.00
	$31,427.50
	$56,427.50

	88
	Track 89 Boxcar Restoration and Train Depot project
	
	
	$10,000.00
	$1,453.65
	$11,453.65

	89
	Boxcar Motel Visitor Experience Project
	
	
	$10,000.00
	$125,108.79
	$135,108.79

	90
	Mt. Pleasant and Fairview Historic Preservation Projects
	
	
	$1,671.49
	$0.00
	$1,671.49

	91
	Mt. Pleasant Relic House project
	
	
	$5,000.00
	$18,351.00
	$23,351.00

	92
	Sindi’s Salon project
	
	
	$3,000.00
	$3,000.00
	$6,000.00

	93
	Spring City Inn project
	
	
	$8,000.00
	$16,585.17
	$24,585.17

	94
	Moroni Opera House project
	
	
	$13,500.00
	$13,500.00
	$27,000.00

	95
	Denver Rio-Grande Depot and Boxcar Motel Project
	Subrecipient: Mt. Pleasant City
	
	$10,000.00
	$95,000.00
	$105,000.00

	96
	Patton House Project
	Subrecipient: Manti City
	
	$3,750.00
	$3,750.00
	$7,500.00

	97
	Salina CCC/POW Camp Project
	Subrecipient: Salina City
	
	$6,400.00
	$6,400.00
	$12,800.00

	98
	Casino-Star Theater Project
	Subrecipient: Sanpete County
	
	$15,000.00
	$95,000.00
	$110,000.00

	99
	Pioneer Cemetery Project
	Subrecipient: Sanpete County
	
	$6,000.00
	$6,000.00
	$12,000.00

	100
	Mt. Pleasant Pioneer Historical Association Relic House Museum project
	Subrecipient: Sanpete County
	
	$10,000.00
	$10,000.00
	$20,000.00

	101
	Sanpete County Courthouse project
	Subrecipient: Sanpete County
	
	$20,000.00
	$30,000.00
	$50,000.00

	102
	Marysvale Mercantile Restoration
	Subrecipient: Piute County
	
	$37,500.00
	$37,500.00
	$75,000.00

	103
	Historic Maynard Dixon Home project
	Subrecipient: Kane County
	
	$25,000.00
	$25,900.00
	$50,900.00

	104
	Casino Star Theatre Project 
	Casino Star Theatre
	
	$45,000.00
	$105,626.00
	$150,626.00

	105
	Kanab Museum Project
	Kanab City
	
	$20,000.00
	$26,601.88
	$46,601.88

	106
	Moroni Opera House project
	Moroni City
	
	$6,866.00
	$6,442.77
	$13,308.77

	107
	Mt. Pleasant CDRA Railroad Park Project
	Mt. Pleasant CDRA
	
	$27,510.00
	$27,510.00
	$55,020.00

	108
	Mt. Pleasant Railroad Park Project
	Mt. Pleasant CDRA
	
	$67,893.00
	$67,893.00
	$135,786.00

	109
	Redmond Town Hall Project
	Redmond
	
	$15,000.00
	$15,000.00
	$30,000.00

	110
	Redmond Town Hall Rehab Project
	Redmond
	
	$22,000.00
	$22,000.00
	$44,000.00

	111
	Salina CCC/POW Camp Rehab Project
	Salina
	
	$10,450.00
	$10,450.00
	$20,900.00

	112
	1916 Spring City Junior High Project
	Spring City
	
	$50,000.00
	$97,347.98
	$147,347.98

	113
	Monroe School Restoration Project
	Monroe City
	
	$60,000.00
	$93,905.21
	$153,905.21

	114
	Fountain Green DUP Upgrades Project
	Fountain Green DUP
	
	$9,200.00
	$59,631.45
	$68,831.45

	115
	Moroni Cannery Renovation Project
	Brad Aldridge (Project is in consultation with SHPO and the City of Moroni)
	$12,000.00
	
	$12,000.00

	116
	Equestrian Center Expansion Project
	Mt. Pleasant City Community Development and Renewal Agency (CDRA)
	$66,000.00
	$576,000.00
	$642,000.00

	117
	Panguitch Tree Removal Project
	Panguitch DUP
	
	$1,000.00
	$650.00
	$1,650.00

	118
	Hanksville Rodeo Renovation Project
	Wayne County
	
	$10,000.00
	$10,000.00
	$20,000.00

	119
	Historic Marysvale Mercantile Building Project
	Justin and Misti Sutherland (This project is in consultation with SHPO and the Town of Marysvale)
	$37,500.00
	$37,500.00
	$75,000.00

	120
	Train Depot Infrastructure Project
	Mt. Pleasant Community Development and Renewal Agency
	$19,800.00
	$21,412.11
	$41,212.11

	121
	Discovery Road Series Project
	North Star Video
	
	$49,916.68
	$38,287.00
	$88,203.68

	122
	Big Rock Candy Mountain Railroad Interpretive Project
	Big Rock Candy Mountain
	
	$25,000.00
	$25,415.00
	$50,415.00

	123
	Piute County Courthouse Façade Restoration Project and Marysvale Visitor Center Operation Project
	Piute County
	
	$4,000.00
	$4,000.00
	$8,000.00

	124
	Mt. Pleasant Main Street Program Fund
	Mt. Pleasant Main Street Program
	
	$10,000.00
	$13,430.00
	$23,430.00

	125
	Mt. Pleasant Main Street Streetscape Revitalization Project
	Mt. Pleasant City
	
	$30,000.00
	$90,800.00
	$120,800.00

	126
	Bridging History Project
	Fairview City
	
	$18,250.00
	$18,250.00
	$36,500.00

	127
	Armory Veterans Memorial Project
	Mt. Pleasant Community Development and Renewal Agency
	$30,000.00
	$30,000.00
	$60,000.00

	128
	Craighead Building Electrical Modernization Project
	Wasatch Academy
	
	$20,000.00
	$22,980.29
	$42,980.29

	129
	Panguitch Main Street Floral Project
	Panguitch City
	
	$4,000.00
	
	$4,000.00

	130
	Salina DUP Cabin Accessibility Enhancement Project
	Salina
	
	$3,725.00
	$2,825.00
	$6,550.00

	131
	Mt. Pleasant Main Street Program Fund
	Mt. Pleasant Main Street Program
	Mt. Pleasant CDRA, Utah Main Street Program, Main Street America
	$95,000.00
	$83,003.20
	$178,003.20

	132
	Mt. Pleasant City Historic Hall Restoration
	Mt. Pleasant CDRA
	Mt. Pleasant City, Utah State Historic Preservation Office (SHPO)
	$13,000.00
	
	$13,000.00

	133
	Mt Pleasant Main Street Historic Preservation and Restoration Fund
	Mt. Pleasant Main Street Program
	Mt. Pleasant CDRA, Utah Main Street Program, Utah State Historic Preservation Office (SHPO)
	$38,750.00
	$38,750.00
	$77,500.00

	134
	Train Depot Infrastructure Project
	Mt. Pleasant CDRA
	Mt. Pleasant City, Sanpete County, Utah State Historic Preservation Office (SHPO)
	$9,189.00
	$9,000.00
	$18,189.00

	135
	Discovery Road TV Series
	North Star Video
	MPNHA, Utah Education Network (UEN), participating local communities and heritage sites
	$108,753.40
	$125,946.60
	$234,700.00

	136
	Sanpete Messenger Website Project
	Sanpete Messenger & MPNHA
	MPNHA, regional partner organizations, local contributors
	$10,305.00
	
	$10,305.00

	137
	Marketing – Web Presence & Regional Partnership
	Marketing – Web Presence & Regional Partnership
	MPNHA, regional tourism partners, local governments, heritage organizations
	$9,500.00
	
	$9,500.00

	138
	Mt. Pleasant to Spring City Bike Path Project
	Sanpete County
	Mt. Pleasant City, Spring City, UDOT, Utah Office of Outdoor Recreation (UORG)
	$39,500.00
	$2,324,955.41
	$2,364,455.41

	139
	Equestrian Center Expansion Project
	Mt. Pleasant CDRA
	Mt. Pleasant City, Sanpete County, George S. and Dolores Doré Eccles Foundation
	$24,700.00
	$23,000.00
	$47,700.00

	154
	
	
	
	
	
	$0.00

	
	
	
	
	
	
	$10,946,250.40




	3.  Collections: Documentation and Conservation Projects
Paintings, Artifacts, Archives, Oral Histories, Video Histories, etc.

	Report here the work in which the primary purpose is to document cultural traditions or conserve artifacts.  If you are working on projects that use collections to develop interpretive or educational materials, please report these projects under Category 6: Education and Interpretation Programs.  

If you did not engage in work to develop or conserve cultural collections this year, please skip these metrics and move on to the Category 4: Land, Water and Environmental Conservation Projects. 

	WORK in PROGRESS.  The numbers reported under 3A – 3B capture work that is advancing, but not yet completed.

	GRANTS FOR COLLECTIONS DISBURSED
3A.1 Number of collections-related grants disbursed this year 0
3A.2 Total dollar amount disbursed this year $ 0

	PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) – Number of projects begun or continued to conserve heritage area artifacts (e.g., condition assessments, plans, research, etc.).  The same project can be reported on over multiple years, until it is completed.  
3B. Number of collections projects begun or continued: 0

	COMPLETED WORK.  The information reported under 3C below captures completed work that the coordinating entity funded, led, or partnered-on with other parties.    

	3C. COLLECTION PROJECTS – Provide the name and a brief description of the collections created, documented, or conserved.  Collections include oral histories, paintings, murals, historic documents, textiles, archaeology collections or material culture, such as boats or ships.  
N/A

	OUTCOMES OF COMPLETED WORK.  The outcomes reported under question 3D capture the results of your the collections conservation activities.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	3D. COLLECTIONS OUTCOMES - In the space provided below, please share outcomes that have resulted from your collections related work, including grants, reported this year or unreported in previous years.  Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome.  
N/A

	4.  Land, Water & Environmental Conservation Projects

	Note: Include wetland work under land restoration, instead of waterway restoration.   
If you did not engage in natural resource conservation work this year, please skip these metrics and move on to category 5: recreation development projects.  

	WORK in PROGRESS.  The numbers reported under 4A – 4B below capture work that is advancing, but not yet completed.

	LAND AND WATER CONSERVATION GRANTS AWARDED
4A.1. Number of natural resource conservation grants disbursed this year 0
4A.2 Total dollar amount disbursed this year $0

	PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to conserve natural or scenic areas (i.e., surveys, condition assessments, plans, etc.). The same project can be reported on over multiple years, until it is completed.  
4B. Number of conservation projects begun or continued: 0

	COMPLETED WORK.  The numbers reported under 4C – 4D below capture completed work that the coordinating entity funded, led, or partnered-on with other parties.    

	LAND RESTORATION
4C.1. Number of acres of land restored through invasive species removal, replanting, and toxic site clean-up. (one time) 0
4C.2. Number of acres of land maintained through monitoring and clean-up efforts 0

	WATERWAY RESTORATION (Streams, rivers, creeks, canals, etc.)
4D.1. Number of feet of waterways restored through appropriate in-water and bank restoration techniques (one time) 0
4D.2. Number of miles of waterways maintained through monitoring and clean-up efforts (please round to the ¼ mile) 0

	OTHER ENVIRONMENTAL CONSERVATION PROJECTS
4E. Provide name and a short description of other environmental conservation projects, such as climate change monitoring.  
N/A

	OUTCOMES OF COMPLETED WORK.  The outcomes reported in question 4E capture the results of your conservation activities.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	4F. CONSERVATION OUTCOMES - In the space provided below, please share outcomes that have resulted from your conservation work, including grants, reported this year or unreported in previous years.  Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome. 
N/A

	5.  Recreation Development Projects

	Note: This category does not include recreational events, programs or marketing materials.  Please include recreational events and marketing materials (such as brochures, maps, guides) under Category 7: Outreach and Marketing.   
If you did not engage in recreation development projects this year, please skip these metrics and move on to Category 6: Education & Interpretation Programs.   

	WORK in PROGRESS.  The numbers reported under 5A – 5B below capture work that is advancing, but not yet completed.

	RECREATION GRANTS AWARDED
5A.1 Number of recreation development grants disbursed this year: 3
5A.2 Total dollar amount disbursed this year $ 64,200

	PROJECTS in PROCESS (Do Not Include Grant Projects Reported Above) - Number of projects begun or continued to enhance recreational amenities (e.g., feasibility studies, plans, engineering, permitting, etc.).  The same project can be reported on over multiple years, until it is completed.  
5B. Number of recreation projects begun or continued: 2

	COMPLETED WORK.  The numbers reported under 5C – 5E below capture completed work that the coordinating entity funded, led, or partnered-on with other parties.    

	NEW TRAILS COMPLETED - Number of new miles of on or off road trails developed 
5C.1. On-road miles: 0
5C.2. Off-road miles: 0

	TRAILS MAINTAINED - Number of miles of on or off-road trails maintained through monitoring, clean-up and maintenance projects construction
5D.1. On-road miles: 4
5D.2. Off-road miles: 43, Sanpete County and US Forest Service and Counties maintained off-road trails

	OTHER RECREATION DEVELOPMENT PROJECTS 
5E. Provide name and a short description of other trail or park enhancement projects, such as parking, signage, trail heads, lighting, etc. or trail designation projects.  For trail designations please identify the mileage. 
	Sanpete County
	Mt. Pleasant to Spring City Bike Path Project
	$39,500.00
	$2,324,955.41
	$2,364,455.41

	Mt. Pleasant CDRA
	Equestrian Center Expansion Project
	$24,700.00
	$23,000.00
	$47,700.00




	OUTCOMES OF COMPLETED WORK.  The outcomes reported under question 5G capture the results of your recreation work.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	5F. RECREATION OUTCOMES - In the space provided below, please share outcomes that have resulted from your recreation work, including grants, reported this year or unreported in previous years.  Provide a short description with the project name, year project was completed, project partners and indicator and data source for outcome. 
	Sanpete County
	Mt. Pleasant to Spring City Bike Path Project
	$39,500.00
	$2,324,955.41
	$2,364,455.41

	Mt. Pleasant CDRA
	Equestrian Center Expansion Project
	$24,700.00
	$23,000.00
	$47,700.00




	6. Education and Interpretation Programs 

	The goal of education and interpretation programs is to increase people’s understanding of heritage area sites and stories.    
Note: Do not include annual meetings, conference presentations, awards ceremonies, open houses, annual fundraisers, and events.  These activities are reported under category 7: outreach and marketing.   
If you did not conduct interpretation work this year, please skip these metrics and move on to category 7: outreach and marketing.


	WORK in PROGRESS.  The numbers reported under 6A - 6B capture work that is advancing, but not yet ready to be offered to the public.

	EDUCATION GRANTS AWARDED
6A.1 Number of education and interpretation related grants disbursed this year: 4
6A.2 Total dollar amount disbursed this year:  $ 108,753.40

	PROJECTS in DEVELOPMENT (Do Not Include Grant Projects Reported Above) - Number of education and interpretation projects in development (e.g., assessments, research, etc.).  The same project can be reported on over multiple years, until it is offered or made available to the public.  
6B. Number of education and interpretation projects in development: 1

	OFFERED PROGRAMS AND PRODUCTS.  The information reported under 6C – 6D below captures the work that the coordinating entity funded, led, or partnered with other parties to offer this year.  

	6C. PROGRAMS OFFERED - In the space below, provide name and a short description of the interpretive or educational programs supported by the NHA coordinating entity this year.  
1. Discovery Road TV Series – In cooperation with the Utah Education Network (UEN) and BYUtv, this series explores the history and culture of the Mormon Pioneer National Heritage Area. We are now actively expanding distribution to a national audience through partnerships with additional networks and streaming platforms.
2. Town Track and Sanpete Art and History Tour – A local heritage tour highlighting key cultural and historical sites within the heritage area.
3. Mt. Pleasant Main Street Program – Offers various community-based events and interpretive activities related to the preservation and revitalization of historic sites.

	6D. PRODUCTS OFFERED - In the space below, provide name and a short description of the interpretive or educational products (print, web, or multi-media) supported by the NHA coordinating entity this year. 
1. Discovery Road TV Series Products – 65 TV episodes completed, with seven produced and distributed this year to TV stations and schools via UEN and BYUtv. Efforts are underway to expand distribution to national platforms.
2. Discovery Road DVDs – Episodes available for purchase and educational use.
3. MPNHA Books – Including Legends, Lore, and True Tales in Mormon Country, published by Arcadia Publishing/History Press, available in Utah libraries and for purchase.
4. MPNHA YouTube Channel – Features various videos related to the heritage area: MPNHA YouTube Channel.
5. MPNHA Website – Provides comprehensive information on the heritage area and its projects: MormonPioneerHeritage.org.
6. Blackhawk War: Cultures in Conflict DVD – An educational tool distributed to schools and organizations to highlight the historical conflict between Native Americans and settlers in the area.
7. Heritage Trails and Interpretive Signage:
· Interpretive signage at the Historic Denver Rio Grande Depot in Mt. Pleasant, providing historical insights into the railroad's impact on the area.
· Interpretive signage inside the new Mt. Pleasant City Hall (formerly the Wells Fargo Bank building), offering historical context and educational displays.
· Development of a new Mt. Pleasant Historic Walking Tour Guide, offering self-guided exploration of key historical sites within the community.
· Interpretive signage and displays at the Salina CCC/POW Camp Memorial, telling the story of German prisoners of war and the Civilian Conservation Corps.
· The Chief Sanpitch Statue as part of the Mt. Pleasant Railroad Park Project, which includes educational signage on the region's indigenous heritage.
· The Mt. Pleasant Armory Veterans Memorial Project, featuring interpretive signage recognizing veterans from Utah’s Blackhawk War and other historical conflicts.
· Marysvale Visitor Center Interpretive Panels, providing insights into the area's cultural and historical significance.
· Heritage Trail Project - Mt. Pleasant to Spring City, featuring signage and interpretive elements along a key historic route.
· Sanpete Recreation Infrastructure Projects, including trail signage, cultural surveys, and historical interpretive materials.


	OUTCOMES of PROGRAM AND PRODUCTS OFFERED.  The outcomes reported under question 6E capture the results of your education work.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	6E. EDUCATION OUTCOMES - In the space provided below, please share any outcomes that have resulted from heritage area educational work, including grants, reported this year or unreported in previous years.  Provide a short description with the project name, year project was completed, project partners and indicator and data source for outcome.  
1. Discovery Road TV Series
· The Discovery Road TV series has completed 65 episodes, with seven produced and distributed this year via UEN and BYUtv. The series is expanding to national distribution through partnerships with additional networks and streaming platforms. Schools, libraries, and museums across Utah utilize the series as an educational tool, and it is available via the MPNHA YouTube channel and DVD distribution. The series continues to attract new audiences and promote heritage tourism by showcasing the region’s history and culture.
2. Blackhawk War: Cultures in Conflict DVD
· This educational DVD has been distributed to schools, libraries, and community organizations, providing valuable insights into the history of the Blackhawk War and its impact on settlers and Native American communities. It remains a widely used resource for educators teaching Utah history and has contributed to increased awareness of the complexities of pioneer-native relations in the region.
3. Mt. Pleasant Main Street Program
· The Mt. Pleasant Main Street Program plays a critical role in guiding and approving nearly all projects within the MPNHA's focus area in Mt. Pleasant. The program supports a range of community-driven preservation and revitalization initiatives, contributing to the economic and cultural development of the city. Key outcomes include: 
· Interpretive signage at the Historic Denver Rio Grande Depot, providing historical insights into the railroad’s significance and impact on local economic development.
· Interpretive signage inside the new Mt. Pleasant City Hall, formerly the Wells Fargo Bank building, offering educational displays detailing the financial and historical heritage of the area.
· Development of the Mt. Pleasant Historic Walking Tour Guide, which offers self-guided exploration of key historical sites, buildings, and landmarks throughout the community.
· Installation of the Chief Sanpitch Statue at the Mt. Pleasant Railroad Park, accompanied by educational signage that tells the story of the region's indigenous heritage and its connection to pioneer settlers.
· Completion of the Mt. Pleasant Armory Veterans Memorial Project, honoring local veterans from Utah’s Blackhawk War and subsequent conflicts with educational signage detailing their contributions.
· The Heritage Trail Project - Mt. Pleasant to Spring City, featuring interpretive signage along the historic route connecting these two National Register communities, educating visitors on the area’s early settlement and development.
4. Salina CCC/POW Camp Memorial
· Interpretive signage and displays have been installed at the Salina CCC/POW Camp Memorial, educating visitors about the history of the German prisoners of war and the Civilian Conservation Corps stationed there during World War II. These exhibits have attracted school groups, veterans’ organizations, and heritage tourists seeking to learn about this unique aspect of Utah’s history.
5. Marysvale Visitor Center Interpretive Panels
· Educational panels installed at the Marysvale Visitor Center provide insights into the area's rich mining heritage, early settlement patterns, and cultural contributions. These panels have enhanced the visitor experience by offering context and historical narratives that support heritage tourism in the region.
6. Sanpete Historic Trails Interpretive Signage
· The Sanpete Historic Trails Project has implemented interpretive signage that provides educational information about key trails, landmarks, and historical events along recreational routes throughout the county. Visitors exploring these equestrian, ATV, hiking, and driving trails now have access to contextual history and cultural narratives that connect them with the pioneers and indigenous peoples who once traveled the area.
7. Sanpete Recreation Infrastructure Projects
· Trailheads and recreational areas throughout Sanpete County have been enhanced with signage, cultural surveys, and interpretive materials that provide historical context to outdoor enthusiasts. The trails support a variety of recreational activities, including equestrian, ATV, hiking, and driving tours, offering educational insights about the region’s landscape and historical significance.
8. Casino Star Theatre Restoration
· The restoration of the historic Casino Star Theatre in Gunnison has resulted in a revitalized cultural venue that now hosts community events, film screenings, and educational programs focused on the area's history and performing arts.
9. Ephraim Granary Arts Center
· The renovation of the historic granary has created a thriving arts and cultural center that offers workshops, art exhibitions, and educational events, fostering a greater appreciation of local heritage and artistic expression.
10. Track 89 Boxcar Restoration and Train Depot Project
· This project has preserved historical railroad elements in Mt. Pleasant, repurposing them into an educational space that informs visitors about the role of railroads in the development of the region while providing a unique heritage tourism attraction.
11. Fairview Museum of History and Art
· Support for the museum has allowed for the expansion of exhibits and educational programming, including hands-on activities for school groups and tourists to engage with Sanpete County’s pioneer and artistic heritage.
12. Gunnison Legacy Wall and Clarion Interpretive Signs
· This project has created educational displays that commemorate the Jewish immigrant community that settled in Clarion, providing insight into their contributions to the region’s agricultural history and cultural diversity.
13. Butch Cassidy Cabin Restoration
· The preservation and interpretation of the Butch Cassidy Cabin in Piute County have provided an educational resource for visitors interested in the legendary outlaw and his connection to the local area, fostering heritage tourism.
14. Panguitch Main Street Floral Project
· This beautification effort has included interpretive signage that connects visitors to the city’s historic roots, enhancing the cultural and visual appeal of the downtown area while providing historical context.
15. Big Rock Candy Mountain Railroad Interpretive Project
· Educational signage at this site provides visitors with insights into the history of the region’s railroad development and its impact on commerce and settlement patterns in central Utah.
16. Historic Spring City Firehouse Restoration
· This project has preserved the historic firehouse while incorporating educational displays that inform visitors about the role of firefighting and community resilience in pioneer settlements.
17. Ephraim Pioneer Park and DUP Museum Project
· The park and museum have been enhanced with educational displays and interactive exhibits that teach visitors about the daily lives and contributions of early pioneers in the region.
18. Kanab Heritage Center
· This restored historic building now serves as an educational and cultural hub, offering exhibits and programs that highlight the diverse history of Kanab and surrounding areas, drawing tourists and researchers alike.
19. Ephraim Carnegie Library Restoration
· The preservation of this historic library has allowed for continued educational programming and public access to resources detailing the history of the area and its early settlers.
20. Historic Denver Rio Grande Depot in Mt. Pleasant
· The restored depot serves as both a transportation hub and an educational site, offering interpretive displays that share the story of the railroad’s influence on local development and commerce.

	7.  Outreach and Marketing (include presentations, sponsorships, and other outreach activities here)

	Note: Include economic impact studies under products offered.   
If you did not conduct outreach or marketing work this year, please skip these metrics and move on to Category 8: Community Engagement.  

	WORK in PROGRESS.  The numbers reported under 7A – 7B capture work that is advancing, but not yet ready to be offered to the public.

	OUTREACH & MARKETING GRANTS AWARDED
7A.1 Number of outreach and marketing grants disbursed this year 11
7A.2 Total dollar amount disbursed this year $ 208,921.29 

	PROJECTS in DEVELOPMENT (Do Not Include Grant Projects Reported Above) - Number of promotion and marketing projects in development (e.g., assessments, research, etc.).  The same project can be reported on over multiple years, until it is offered or made available to the public.  
7B. Number of promotion and marketing projects in development: 2

	OFFERED EVENTS AND PRODUCTS.  The numbers reported under 7C – 7D below capture work that the coordinating entity funded, led, or partnered with other parties to offer to the public this year.  

	7C. EVENTS OFFERED (RACES, CELEBRATIONS, AWARDS CEREMONIES, FAM TOURS, ETC.) - In the space below, provide name and a short description of promotional activities supported by the coordinating entity. 
1. Western Legends Roundup
2. Scandinavian Days
3. Mormon Pioneer Heritage Festival
4. Spring City Heritage Days
5. Everett Ruess Festival
6. Jacob Hamblin Days
7. Butch Cassidy Days
8. Panguitch Quilt Walk
9. Map N Tour Project
10. Mt. Pleasant Historic Walking Tour

	7D. PRODUCTS OFFERED (BROCHURES, ECONOMIC IMPACT STUDIES, WEBSITES, ETC.) - In the space below, provide name and a short description of promotional products supported by the coordinating entity.  
1. MPNHA website – https://www.mormonpioneerheritage.org
2. MPNHA YouTube Channel – https://www.youtube.com/channel/UCwY8IF4uHOhMHopvi-DQkdQ
3. Travel planner – Printed and distributed to visitors and organizations.
4. Discovery Road TV Series – Distributed via internet and broadcast.
5. DVDs of Discovery Road episodes – Available for purchase and educational use.
6. MPNHA Books – Legends, Lore, and True Tales in Mormon Country, published by Arcadia Publishing/History Press, available in Utah libraries and for purchase.
7. Blackhawk War: Cultures in Conflict educational DVD – Distributed to schools and other entities.
8. Map N Tour mobile tourism application – Enhancing tourism experiences within the heritage area.
9. Mt. Pleasant Historic Walking Tour Guide (in development) – A guide offering self-guided exploration of key historical sites within the community.
10. MPNHA Management Plan – Available on mormonpioneerheritage.org.
11. 10-Year Report (2017) – Available on mormonpioneerheritage.org.
12. Annual Reports: Available on mormonpioneerheritage.org.

	OUTCOMES of EVENTS AND PRODUCTS OFFERED.  The outcomes reported under question 7E capture the results of your promotion and marketing work.  Outcomes do not need to reflect the work that was completed this year, unless outcomes occurred.  Outcomes related to individual and cumulative grant activities may be included.  

	7E. OUTREACH & MARKETING OUTCOMES - In the space provided below, please share outcomes that have resulted from heritage area marketing activities reported this year or offered in previous years.  Outcomes could include increases in visitation to heritage area sites generated by marketing products.  Provide a short description with the project name, year project was completed, project partners, and indicator and data source for outcome.  
1. Discovery Road TV Series Expansion – The show continues to be broadcast on UEN and BYUtv, with efforts in progress to expand distribution to a national audience.
2. MPNHA Website Usage – The MPNHA website serves as a resource for information about events, travel itineraries, and heritage sites. The site provides downloadable travel planners and other resources to help visitors plan their experiences.
3. Travel Planner Distribution – MPNHA continues to print and distribute travel planners to visitor centers and events, providing tourists with key heritage information.
4. Event Support and Participation – MPNHA supports multiple heritage-themed events across the five districts, promoting local heritage and encouraging tourism.


	8.  Community Engagement

	The numbers captured here reflect the work of the NHA coordinating entity and partnership.  Please answer all questions below.      

	PARTNERSHIPS   
A partnership is a relationship between parties to accomplish a common goal, such as developing or implementing a heritage area project or offering heritage area programs.  Partnerships are characterized by mutual interest, commitment, and communication.  Please count partners one time, either as formal or informal partners. 
8A.1 Formal Partners are the organizations who you directly collaborate with on heritage area projects and programs and who are substantially involved in those projects or programs.  You may have an agreement in place to formalize your partnership with these organizations, but having an agreement is not a requirement for being a formal partner.  
Number of formal partners substantially engaged in National Heritage Area activities this year: 17

8A.2 Informal Partners are those organizations who you cooperate or coordinate with on projects and programs.  These organizations are not substantially involved in your projects or programs. 
Number of informal partners engaged in National Heritage Area activities this year: 75


	VOLUNTEERISM
Volunteer Count. Please count volunteers who are working on projects or programs that are coordinated and/or funded by the national heritage area coordinating entity.  Do not include volunteers at park units or other sites for which there was no investment of heritage area staff time or funding. 

8B.1 Total number of volunteers engaged in heritage area projects, programs or activities 298
8B.2 Total number of volunteer hours 5,796  (please round-up to the nearest hour)
8B.3 Hourly value of volunteer time for your state or region (refer to www.independentsector.org/volunteer_time for your region) $ 33.46 
8B.4 Total dollar value of volunteer hours $ 193,934.16

	PROGRAM & EVENT PARTICIPANTS 
Program and Event Participant Count.  Please count participants who attended events or programs that were coordinated and/or funded by the national heritage area coordinating entity.  Do not include participants in programs at parks or other sites where there was no investment of heritage area staff time or funding. 
8C.1 Number of people who participated in heritage area educational programs this year: 24,500
8C.2 Number of people who participated in heritage area events (races, celebrations, ceremonies, etc.) this year: 35,000


	OTHER ACTIVITIES  
8D.1 In the space below, identify any other activities including community development, economic development or community engagement projects that do not fit into the seven categories above.
N/A

	Best Practice: Highlight a Successful Project or Program

	In the space below, please describe a creative, successful project or program undertaken or completed this year.  Please include images with captions and credit information.  
Also, include numbers if applicable – dollars invested and leveraged, communities or residents involved or impacted, properties preserved, miles of trails improved, etc.  Word count recommendation is 200 words.

	[image: ][image: ]
DISCOVERY ROAD TELEVISION SHOW
Best Practice: Heritage Storytelling Through National Television
[image: ]We are honored to have a longstanding working relationship with the Mormon Pioneer National Heritage Area (MPNHA) that brings forward history, culture, and heritage in the American West. The excitement, curiosity, and storytelling power of Discovery Road provide viewers with an entertaining ride to yesterday. The partnership Discovery Road has with the MPNHA and others in bringing history forward is an ever-growing example of how different groups and organizations can cooperate, bond, and work together to achieve goals and overcome barriers.
Many people have appeared in Discovery Road episodes and consistently share positive feedback about the experience. Others who view the shows find new excitement and opportunity in the history and stories of their own neighborhoods. The cumulative impact Discovery Road has on groups, organizations, and the general public is a renewed understanding that history is important. Each story and every episode feels like a renaissance of the past. Historical documents, on-camera interviews, scrapbooks, photographs, films, journals, century-old homes, restored schoolhouses, and refurbished theaters all seem to take on a special frame when they find their way into a Discovery Road television show.Hardy Redd looks out over the Home of Truth compound in southeastern Utah. Redd was well acquainted with the woman who ran the religious commune in the 1930s. He visited the property with our show producer during production of The Untold episode. Photo courtesy of Discovery Road.

FY2025 Accomplishments and National Distribution
During FY2025, one of the most significant accomplishments of Discovery Road was the expansion of national distribution. With a total project investment of $234,700.00, including $108,753.40 in federal funding and $125,946.60 in matching funds, this year’s work focused on sharing heritage stories with audiences far beyond the Mormon Pioneer National Heritage Area. Programming aired through the National Educational Telecommunications Association (NETA) and Weigel Television, allowing Discovery Road to reach viewers across multiple states and connect national audiences to local history and lived experience.
60 National Heritage Areas. One Television Show.
[image: ]It is a real accomplishment that Discovery Road and the MPNHA have partnered to highlight history, culture, and heritage for more than a decade. It is even more remarkable that Discovery Road remains the only television program associated with a National Heritage Area. Because of this unique position, many other heritage areas across the country have reached out to us for development and production of Discovery Road in their own regions.
Image caption:
Ute spiritual leader Larry Cesspooch on location with our television news crew. Cesspooch has appeared in numerous Discovery Road shows.
Photo courtesy of Discovery Road.
Our television series has produced shows in the Sangre de Cristo National Heritage Area, the Santa Cruz Valley National Heritage Area, and the Northern Rio Grande National Heritage Area. In addition, we have developed programming in more than a dozen states. The National Educational Telecommunications Association has embraced our television road series, and Weigel Television regularly schedules and broadcasts our shows. This special way of communicating with the public about important heritage stories, events, and people has grown into a powerful educational and outreach tool that crosses borders and connects communities.Ute spiritual leader Larry Cesspooch on location with our television news crew. Cesspooch has appeared in numerous Discovery Road shows.
Photo courtesy of Discovery Road.

Discovery Road is proud to hear people from across our great nation continue to beckon us to come tell their stories.
James Nelson
Discovery Road



NOTICES


PRIVACY ACT STATEMENT

General:  This information is provided pursuant to Public Law 93-579 (Privacy Act of 1974), December 21, 1984, for individuals completing this form.

Authority:  54 USC Ch. 3201, Historic Sites Act of 1935, as amended; 44 U.S.C. 3501, et seq., Paperwork Reduction Act of 1995; and individual pieces of legislation and associated amendments in 54 USC 100702 that enable the NPS, on behalf of the Secretary of the Interior, to provide federal financial, technical, and other assistance for the preservation of natural, cultural, historic, and scenic resources.

Purposes and Uses:  The NPS intends to track the progress of each heritage area on implementing its management plan and meeting performance goals. The information collected is used by the NHA program office in monitoring the progress of each heritage area. The collection of this information is necessary to allow for national oversight, analysis, coordination, technical and financial assistance, and support to National Heritage Areas to ensure consistency and accountability across the country.

Effects of Nondisclosure:  Financial disclosure is in accordance with 54 USC Ch. 3201, Pub. L. 113–291, div. B, title XXX, §3052(a)(2), Dec. 19, 2014, 128 Stat. 3802.

Information Regarding Disclosure of Your Social Security Number Under Public Law 93-579 Section 7(b): Your Social Security Number is not needed to complete this form.  


PAPERWORK REDUCTION ACT STATEMENT

We are collecting this information subject to the Paperwork Reduction Act (44 U.S.C. 3501) in response to the NHAs individual authorizing legislation requiring annual reporting as mandated by Congress. The information provided by NHA Coordinating Entities allows the NHA program office to allocate funding to heritage area management, prepare NPS budget justifications, and track management planning and implementation across NHAs. We may not conduct or sponsor and you are not required to respond to a collection of information unless it displays a currently valid OMB Control Number. OMB has reviewed and approved this survey and assigned OMB Control Number 1024-###, which expires ##/##/####.

ESTIMATED BURDEN STATEMENT

Public Reporting burden for this form is estimated to average 42 minutes per response, including the time it takes for reviewing instructions, gathering and maintaining data, and completing and reviewing the form. Comments regarding this burden estimate or any aspect of this form should be sent to the Information Collection Clearance Officer, National Park Service, 1201 Oakridge Drive, Fort Collins, CO 80525. 
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